## Investment Project Main Info
Investment Project Main Information
PRJ Code | PRJ Name | PRJ Status | Code | Project Name | Country | Promoter | Maturity Status | PCI 3rd List | PCI 3rd List Code | Intention to apply to 5th PCI List | Project Commissioning Year First | Project Commissioning Year Last | Project CAPEX Confidential | Project CAPEX (in million €) | Project Alternative CAPEX (in million €) | Project OPEX Confidential | Project OPEX (in million € per year) | Project Alternative OPEX (in million € per year) | Project Website | Is Part of a NDP | NDP Number
PRJ-G-001 | Physical Reverse Flow at Moffat interconnection point (IE/UK) | Less-Advanced | TRA-A-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | Ireland | Gas Networks Ireland | Advanced | Yes | 5.1.1 | Yes | 2022 | 2022 | Non-Confidential | 119 |  | Non-Confidential | 3.3 |  | URL | Yes | PCI 5.1.1
|  |  | TRA-N-1064 | Moffat Physical Reverse Flow | United Kingdom | National Grid Gas plc | Less-Advanced | Yes | 5.1.1 | Yes | 2020 | 2020 | Non-Confidential | 10 |  | Non-Confidential | 0.1 |  |  | No | N/A
PRJ-G-002 | Bidirectional Austrian - Czech Interconnection (BACI) | Advanced | TRA-A-21 | Bidirectional Austrian-Czech Interconnector (BACI) | Austria | GAS CONNECT AUSTRIA GmbH | Advanced | Yes | 6.4 | Yes | 2024 | 2024 | Non-Confidential | 176 |  | Non-Confidential | 8 |  | URL | Yes | GCA 2015/01a
|  |  | TRA-A-133 | Bidirectional Austrian Czech Interconnection (BACI) | Czechia | NET4GAS, s.r.o. | Advanced | Yes | 6.4 | Yes | 2024 | 2024 | Non-Confidential | 20 |  | Non-Confidential | 0.12 |  | URL | Yes | TRA-N-133
PRJ-G-003 | Interconnection Slovenia-Croatia (Gas pipeline Lučko-Zabok-Rogatec) | Less-Advanced | TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla) | Croatia | Plinacro Ltd | Advanced | Yes | 6.26.1.1 | Yes | 2021 | 2023 | Confidential |  | 76.05 | Confidential |  | 1.37 | URL | Yes | 1.9, 1.10, 1.11
|  |  | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.26.6 | Yes | 2021 | 2023 | Confidential |  | 12.4 | Confidential |  | 0.08 | URL | Yes | C12
PRJ-G-004 | Krk LNG terminal with connecting and evacuation pipelines towards Hungary and beyond | Less-Advanced | LNG-F-82 | LNG terminal Krk | Croatia | LNG Hrvatska d.o.o. | FID | Yes | 6.5.1; 6.5.6 | Yes | 2020 | 2027 | Non-Confidential | 233.6 |  | Non-Confidential | 13 |  | URL | Yes | LNG terminal on the island of Krk
|  |  | TRA-F-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Croatia | Plinacro Ltd | FID | Yes | 6.5.1 | Yes | 2020 | 2020 | Confidential |  | 27.29 | Confidential |  | 0.49 | URL | Yes | 1.18
|  |  | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Croatia | Plinacro Ltd | Less-Advanced | Yes | 6.5.6 | Yes | 2027 | 2027 | Confidential |  | 198.4 | Confidential |  | 3.57 | URL | Yes | 1.19, 1.20, 1.21
|  |  | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Croatia | Plinacro Ltd | Less-Advanced | Yes | 6.5.6 | Yes | 2027 | 2027 | Confidential |  | 141.08 | Confidential |  | 2.54 | URL | Yes | 1.32
PRJ-G-008 | Poland – Slovakia Gas Interconnection | FID | TRA-F-190 | Poland - Slovakia interconnection | Slovakia | eustream,a.s. (a joint-stock company) | FID | Yes | 6.2.1 | Yes | 2021 | 2021 | Confidential |  | 143.4 | Confidential |  | 0.67 | URL | Yes | 4.1.1.1.-PL-SK gas interconnection
|  |  | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | FID | Yes | 6.2.1 | Yes | 2021 | 2021 | Confidential |  | 680 | Confidential |  | 16 | URL | Yes | N/A
PRJ-G-010 | Latvia - Lithuania interconnection | Advanced | TRA-A-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | Lithuania | AB Amber Grid | Advanced | Yes | 8.2.1 | Yes | 2023 | 2023 | Non-Confidential | 4.7 |  | Non-Confidential | 0.3 |  | URL | Yes | n/a
|  |  | TRA-A-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | Latvia | JSC "Conexus Baltic Grid" | Advanced | Yes | 8.2.1 | Yes | 2023 | 2023 | Non-Confidential | 5.5 |  | Non-Confidential | 0.04 |  | URL | No | N/A
PRJ-G-011 | Interconnection Estonia – Finland | FID | TRA-F-895 | Balticconnector | Estonia | Elering AS | FID | Yes | 8.1.1 | No | 2019 | 2020 | Non-Confidential | 131 |  | Non-Confidential | 1.5 |  | URL | Yes | paragraph 3.2
|  |  | TRA-F-928 | Balticconnector Finnish part | Finland | Baltic Connector Oy | FID | Yes | 8.1.1 | No | 2019 | 2020 | Non-Confidential | 128.5 |  | Non-Confidential | 1.5 |  | URL | No | N/A
PRJ-G-013 | North Interconnection of BiH and Croatia | Less-Advanced | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Croatia | Plinacro Ltd | Less-Advanced | No |  | Yes | 2025 | 2025 | Non-Confidential | 9 |  | Non-Confidential | 0.01 |  | URL | Yes | 1.15
|  |  | TRA-N-224 | Gaspipeline Brod - Zenica | Bosnia Herzegovina | BH-Gas d.o.o. | Less-Advanced | No |  | Yes | 2025 | 2025 | Non-Confidential | 85 |  | Non-Confidential | 1 |  | URL | Yes | PTG1
PRJ-G-014 | South Interconnection of BiH and Croatia | Less-Advanced | TRA-A-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Croatia | Plinacro Ltd | Advanced | No |  | Yes | 2023 | 2023 | Confidential |  | 16.12 | Confidential |  | 0.29 | URL | Yes | 1.13
|  |  | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | Bosnia Herzegovina | BH-GAS d.o.o. | Less-Advanced | No |  | Yes | 2023 | 2023 | Non-Confidential | 101 |  | Non-Confidential | 1 |  | URL | Yes | No 10 in Framework Energy Strategy BiH until 2035 and PTG2 in SPP
PRJ-G-015 | West Interconnection of BiH and Croatia | Less-Advanced | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Croatia | Plinacro Ltd | Less-Advanced | No |  | No | 2026 | 2026 | Confidential |  |  | Confidential |  |  | URL | Yes | 1.35 and 1.36
|  |  | TRA-N-910 | West Interconnection BiH/CRO | Bosnia Herzegovina | BH-Gas d.o.o. | Less-Advanced | No |  | No | 2026 | 2026 | Non-Confidential | 33 |  | Non-Confidential | 1 |  | URL | Yes | No 11 - Framework Energy Strategy of BiH until 2035 and PTG4 - Strategic Plan and Program of Development Energy Sector in FBiH 2009
PRJ-G-017 | Gas Interconnection Poland-Lithuania (GIPL) | FID | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | Poland | GAZ-SYSTEM S.A. | FID | Yes | 8.5 | Yes | 2021 | 2021 | Confidential |  | 430 | Confidential |  | 11 | URL | Yes | N/A
|  |  | TRA-F-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | Lithuania | AB Amber Grid | FID | Yes | 8.5 | Yes | 2021 | 2021 | Non-Confidential | 136 |  | Non-Confidential | 1.83 |  | URL | Yes | n/a
PRJ-G-018 | Additional capacity at Oude Statenzijl from Germany to the Netherlands | Less-Advanced | TRA-F-307 | H-gas exit OSZ GTG Nord | Netherlands | Gasunie Transport Services B.V. | FID | No |  | No | 2020 | 2027 | Non-Confidential | 4.4 |  | Non-Confidential | 0 |  |  | Yes | 6.5.1
|  |  | TRA-A-496 | Increase of Gas Transport to the Netherlands | Germany | Gasunie Deutschland Transport Service GmbH | Advanced | No |  | Yes | 2022 | 2022 | Non-Confidential | 1.25 |  | Non-Confidential | 0.15 |  |  | No | N/A
|  |  | TRA-A-808 | Additional transport of gas volumes to the Netherlands | Germany | Gasunie Deutschland Transport Services GmbH | Advanced | No |  | No | 2025 | 2025 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | TRA-N-809 | Reallocation H-Gas towards NL: Bunde/Oude to Zone Oude Statenzijl H | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | No |  | Yes | 2022 | 2022 | Non-Confidential | 13 |  | Non-Confidential | 0.7 |  |  | Yes | ID504-01a; ID504-01b; ID504-01c
|  |  | TRA-N-873 | Additional import at Oude StatenZijl area | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | No |  | Yes | 2022 | 2025 | Non-Confidential | 0.6 |  | Non-Confidential | 0 |  |  | Yes | 6.5.4.
|  |  | TRA-N-882 | Transferring L-gas infrastructure to H-gas | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | No |  | No | 2020 | 2030 | Non-Confidential | 8 |  | Non-Confidential | 0 |  |  | Yes | 6.5.1
PRJ-G-021 | Baltic Pipe Project | Advanced | TRA-F-780 | Baltic Pipe project – onshore section in Denmark | Denmark | Energinet | FID | Yes | 8.3.1 | Yes | 2022 | 2022 | Non-Confidential | 629 |  | Non-Confidential | 22.9 |  | URL | No | N/A
|  |  | TRA-A-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | Poland | GAZ-SYSTEM S.A. | Advanced | Yes | 8.3.2 | Yes | 2022 | 2022 | Confidential |  | 620 | Confidential |  | 22 | URL | Yes | N/A
|  |  | TRA-A-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | Poland | GAZ-SYSTEM S.A. | Advanced | Yes | 8.3.2 | Yes | 2022 | 2022 | Confidential |  | 340 | Confidential |  | 8 | URL | Yes | N/A
PRJ-G-022 | Poland - Czech Republic Interconnection | Advanced | TRA-A-136 | Czech-Polish Gas Interconnector (CPI) | Czechia | NET4GAS, s.r.o. | Advanced | Yes | 6.2.10; 6.2.12 | Yes | 2023 | 2023 | Non-Confidential | 257.14 |  | Non-Confidential | 0.52 |  | URL | Yes | TRA-N-136
|  |  | TRA-A-273 | Poland - Czech Republic Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | Advanced | Yes | 6.2.10 | Yes | 2023 | 2023 | Confidential |  | 70 | Confidential |  | 1 | URL | Yes | N/A
PRJ-G-023 | LNG Terminal Brunsbuettel | Advanced | LNG-A-1198 | LNG Terminal Brunsbuettel | Germany | GermanLNG Terminal GmbH | Advanced | No |  | No | 2023 | 2023 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | TRA-A-1199 | LNG Terminal Brunsbuettel - Grid Integration | Germany | Gasunie Deutschland Transport Service GmbH | Advanced | No |  | No | 2023 | 2023 | Confidential |  |  | Confidential |  |  | URL | Yes | ID300-01
PRJ-G-028 | Poland - Ukraine Gas Interconnection | Advanced | TRA-A-561 | Poland-Ukraine Interconnector (Ukrainian section) | Ukraine | PJSC UKRTRANSGAZ | Advanced | No |  | No | 2022 | 2022 | Non-Confidential | 150 |  | Non-Confidential | 1 |  |  | No | N/A
|  |  | TRA-A-621 | Poland - Ukraine Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | Advanced | No |  | Yes | 2022 | 2022 | Confidential |  | 10 | Confidential |  | 1 | URL | Yes | N/A
PRJ-G-030 | Transferring L-gas infrastructure to H-gas | Less-Advanced | TRA-F-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Germany | Gastransport Nord GmbH | FID | No |  | No | 2020 | 2027 | Confidential |  |  | Confidential |  |  |  | Yes | 432-02b
|  |  | TRA-A-951 | Embedding CS Folmhusen in H-Gas | Germany | Gasunie Deutschland Transport Services GmbH | Advanced | No |  | No | 2020 | 2020 | Non-Confidential | 0.2 |  | Non-Confidential | 0.01 |  |  | Yes | ID 300-02
|  |  | TRA-N-955 | GUD: Complete conversion to H-gas | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | No |  | No | 2021 | 2030 | Non-Confidential | 24 |  | Non-Confidential | 1.39 |  |  | Yes | ID 221-01 ID; ID 222-02; ID 223-01
PRJ-G-034 | More capacity – DE/CZ Capacity4Gas Project | FID | TRA-F-752 | Capacity4Gas – DE/CZ | Czechia | NET4GAS, s.r.o. | FID | No |  | No | 2019 | 2021 | Non-Confidential | 515 |  | Non-Confidential | 11 |  | URL | Yes | TRA-F-752
|  |  | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | Germany | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | FID | No |  | No | 2019 | 2022 | Non-Confidential | 2620 |  | Non-Confidential | 40.1 |  | URL | Yes | 412-03, 507-01a,b,c,d,e,f
|  |  | TRA-F-814 | Upgrade for IP Deutschneudorf et al. for More Capacity | Germany | ONTRAS Gastransport GmbH | FID | No |  | No | 2023 | 2023 | Non-Confidential | 90.4 |  | Non-Confidential | 4.8 |  | URL | Yes | 507-01 g, 507-01 h, ID 507-02 i, 507-01 j, 507-01 m
PRJ-G-036 | Interconnection ES-PT (3rd interconnection) | Less-Advanced | TRA-A-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | Portugal | REN-Gasodutos, S.A. | Advanced | Yes | 5.4.1 | Yes | 2025 | 2025 | Non-Confidential | 115 |  | Non-Confidential | 1.83 |  | URL | Yes | -
|  |  | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Spain | Enagas Transporte S.A.U. | Less-Advanced | Yes | 5.4.1 | Yes | 2025 | 2025 | Non-Confidential | 74.8 |  | Non-Confidential | 1.4 |  |  | No | N/A
PRJ-G-039 | STEP (South Transit East Pyrenees) | Advanced | TRA-A-161 | South Transit East Pyrenees (STEP) - ENAGAS | Spain | Enagas Transporte S.A.U. | Advanced | Yes | 5.5.1 | Yes | 2024 | 2024 | Non-Confidential | 152 |  | Non-Confidential | 4.25 |  | URL | Yes | No code in the NDP
|  |  | TRA-A-252 | South Transit East Pyrenees (STEP) - TEREGA | France | TEREGA | Advanced | Yes | 5.5.1 | Yes | 2024 | 2024 | Non-Confidential | 290 |  | Non-Confidential | 3 |  | URL | Yes | No number
PRJ-G-041 | Pipeline system from Bulgaria via Romania and Hungary to Slovakia [currently known as "Eastring“ | Advanced | TRA-A-628 | Eastring - Slovakia | Slovakia | eustream, a.s. (a joint stock company) | Advanced | Yes | 6.25.1 | Yes | 2025 | 2030 | Non-Confidential | 146.1 |  | Non-Confidential | 7 |  | URL | Yes | None
|  |  | TRA-A-654 | Eastring - Bulgaria | Bulgaria | Bulgartransgaz EAD | Advanced | Yes | 6.25.1 | Yes | 2025 | 2030 | Non-Confidential | 626.4 |  | Non-Confidential | 21.8 |  | URL | Yes | Section 5.1 (5.1.2)
|  |  | TRA-A-655 | Eastring - Romania | Romania | SNTGN Transgaz SA | Advanced | Yes | 6.25.1 | Yes | 2025 | 2030 | Non-Confidential | 1297 |  | Non-Confidential | 18.1 |  | URL | No | N/A
|  |  | TRA-A-656 | Eastring - Hungary | Hungary | FGSZ Ltd. | Advanced | Yes | 6.25.1 | Yes | 2025 | 2030 | Non-Confidential | 530.9 |  | Non-Confidential | 8.3 |  | URL | Yes | 12.13.
PRJ-G-045 | Enhancement of the capacity at SK-HU interconnector | Less-Advanced | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Hungary | FGSZ Ltd. | Less-Advanced | Yes | 6.2.13 | Yes | 2022 | 2022 | Confidential |  | 58 | Confidential |  | 0.11 | URL | Yes | TRA-N-524 (new nr will be received once project is approved)
|  |  | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Hungary | FGSZ Ltd. | Less-Advanced | Yes | 6.2.13 | Yes | 2022 | 2022 | Confidential |  | 0.64 | Confidential |  | 6.6 | URL | Yes | TRA-N-636
|  |  | TRA-N-1235 | Firm transmission capacity increase at the IP Veľké Zlievce | Slovakia | eustream,a.s. | Less-Advanced | Yes | 6.2.13 | Yes | 2022 | 2022 | Confidential |  | 26.18 | Confidential |  | 1.95 | URL | Yes | 4.1.1.3 a) Firm transmission capacity increase at the IP Veľké Zlievce
PRJ-G-047 | RO-HU Transmission Corridor | Advanced | TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | Hungary | FGSZ Ltd. | FID | Yes | 6.24.1.1 | No | 2019 | 2019 | Confidential |  |  | Confidential |  |  | URL | Yes | 12.5.
|  |  | TRA-A-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | Hungary | FGSZ Ltd. | Advanced | Yes | 6.24.4.6 | Yes | 2022 | 2022 | Confidential |  | 14.4 | Confidential |  | 3.7 | URL | Yes | 12.5
|  |  | TRA-A-1322 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase II | Romania | SNTGN Transgaz SA | Advanced | Yes | 6.24.4.4 | Yes | 2022 | 2022 | Non-Confidential | 68.8 |  | Non-Confidential | 7.85 |  |  | Yes | 7.1.2
PRJ-G-049 | Fos Cavaou LNG Terminal Expansion | Less-Advanced | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | France | Fosmax LNG | Less-Advanced | No |  | Yes | 2023 | 2025 | Confidential |  | 300 | Confidential |  | 15 | URL | Yes | Fos Cavaou Extension
|  |  | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | France | GRTgaz | Less-Advanced | No |  | No | 2026 | 2026 | Non-Confidential | 1571 |  | Confidential |  |  | URL | Yes | Extension du terminal de Fos Cavaou à 16,5 Gm³/an
PRJ-G-050 | Montoir LNG Terminal Expansion | Less-Advanced | LNG-N-225 | Montoir LNG Terminal Expansion | France | Elengy | Less-Advanced | No |  | Yes | 2023 | 2025 | Confidential |  | 250 | Confidential |  | 13 | URL | Yes | Montoir Extension
|  |  | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | France | GRTgaz | Less-Advanced | No |  | No | 2023 | 2023 | Non-Confidential | 500 |  | Non-Confidential | 1.35 |  | URL | Yes | Augmentation des capacités d’entrée à partir du terminal de Montoir de 10 à 12,5 Gm³/an
PRJ-G-054 | LNG | Less-Advanced | LNG-A-50 | Gate terminal phase 3 | Netherlands | Gate | Advanced | No |  | No | 2022 | 2024 | Confidential |  |  | Confidential |  |  | URL | Yes | unknown see GTS
|  |  | TRA-N-192 | Entry capacity expansion GATE terminal | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | No |  | No | 2022 | 2022 | Non-Confidential | 40 |  | Non-Confidential | 0.1 |  |  | Yes | 6.5.2
PRJ-G-055 | LNG terminal in northern Greece / Alexandroupolis | Advanced | LNG-A-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Greece | Gastrade S.A. | Advanced | Yes | 6.9.1 | Yes | 2022 | 2022 | Non-Confidential | 290 |  | Non-Confidential | 19 |  | URL | No | N/A
|  |  | TRA-A-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Greece | Gastrade S.A. | Advanced | Yes | 6.9.1 | Yes | 2022 | 2022 | Non-Confidential | 80 |  | Non-Confidential | 0.01 |  | URL | No | N/A
PRJ-G-060 | Hungary – Slovenia interconnection | Less-Advanced | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.23 | Yes | 2023 | 2025 | Confidential |  | 112.8 | Confidential |  | 1.28 | URL | Yes | C3
|  |  | TRA-N-325 | Slovenian-Hungarian interconnector | Hungary | FGSZ Ltd. | Less-Advanced | Yes | 6.23 | Yes | 2023 | 2025 | Confidential |  | 205 | Confidential |  | 10 | URL | Yes | 12.12.
PRJ-G-066 | Bidirectional gas route Austria-Slovenia | Less-Advanced | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | Austria | GAS CONNECT AUSTRIA GmbH | Less-Advanced | Yes | 6.26.1.4 | Yes | 2023 | 2023 | Non-Confidential | 100 |  | Non-Confidential | 6 |  | URL | Yes | GCA 2015/08
|  |  | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.26.1.5 | Yes | 2023 | 2023 | Confidential |  | 6 | Confidential |  | 0.03 | URL | Yes | C4
PRJ-G-105 | Hydrogen network northwest Europe | Less-Advanced | ETR-N-322 | North Sea Wind Power Hub | Netherlands | N.V. Nederlandse Gasunie | Less-Advanced | No |  | No | 2032 | 2032 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | ETR-N-370 | Hydrogen transmission backbone Netherlands | Netherlands | N.V. Nederlandse Gasunie | Less-Advanced | No |  | No | 2030 | 2030 | Non-Confidential | 1700 |  | Non-Confidential | 70 |  |  | No | N/A
|  |  | ETR-N-396 | Djewels | Netherlands | Nouryon | Less-Advanced | No |  | No | 2030 | 2030 | Confidential |  |  | Confidential |  |  |  | No | N/A
PRJ-G-107 | UGS Velke Kapusany | Advanced | ETR-A-312 | P2G Velke Kapusany | Slovakia | NAFTA a.s. (joint stock company) | Advanced | No |  | No | 2023 | 2023 | Non-Confidential | 78 |  | Non-Confidential | 2.5 |  | URL | No | N/A
|  |  | UGS-A-356 | Underground Gas Storage Velke Kapusany | Slovakia | NAFTA a.s. (joint stock company) | Advanced | No |  | Yes | 2023 | 2023 | Non-Confidential | 161 |  | Non-Confidential | 3 |  | URL | Yes | chapter 3.3
PRJ-G-108 | LNG terminal in Latvia | Less-Advanced | LNG-N-912 | Skulte LNG | Latvia | AS Skulte LNG Terminal | Less-Advanced | No |  | Yes | 2023 | 2023 | Non-Confidential | 110 |  | Non-Confidential | 3 |  | URL | No | N/A
|  |  | TRA-N-1181 | Connecting pipe to LNG terminal in Latvia | Latvia | JSC "Conexus Baltic Grid" | Less-Advanced | No |  | Yes | 2021 | 2021 | Non-Confidential | 26 |  | Non-Confidential | 0.46 |  | URL | No | N/A
PRJ-G-115 | CCS/U Netherlands | Less-Advanced | ETR-A-430 | Porthos | Netherlands | N.V. Nederlandse Gasunie | Advanced | No |  | No | 2023 | 2023 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | ETR-N-432 | Athos | Netherlands | N.V. Nederlandse Gasunie | Less-Advanced | No |  | No | 2026 | 2026 | Confidential |  |  | Confidential |  |  |  | No | N/A
PRJ-G-118 | Biomethane: reverse flow projets in France | Less-Advanced | ETR-F-587 | West Grid Synergy | France | GRTgaz | FID | No |  | No | 2019 | 2019 | Non-Confidential | 8.5 |  | Confidential |  |  | URL | No | N/A
|  |  | ETR-N-624 | Biomethane: Reverse flow projects | France | GRTgaz | Less-Advanced | No |  | No | 2028 | 2028 | Non-Confidential | 435 |  | Confidential |  |  | URL | No | N/A
PRJ-G-121 | Romania - Ukraine Gas Interconnection | Less-Advanced | TRA-N-502 | Interconnector Romania - Ukraine | Ukraine | Joint-Stock Company | Less-Advanced | No |  | No | 2025 | 2025 | Non-Confidential | 40 |  | Non-Confidential | 1 |  |  | No | N/A
|  |  | TRA-N-596 | Interconnection between the RO and the UA gas transmission systems | Romania | SNTGN Transgaz SA | Less-Advanced | No |  | Yes | 2025 | 2025 | Non-Confidential | 125 |  | Non-Confidential | 2 |  |  | Yes | 7.9
PRJ-G-122 | Incremental capacity between Greece and Italy | Less-Advanced | TRA-N-14 | Komotini-Thesprotia pipeline | Greece | DESFA S.A. | Less-Advanced | No |  | Yes | 2025 | 2025 | Non-Confidential | 1800 |  | Non-Confidential | 65 |  | URL | Yes | 2.2.1.5
|  |  | TRA-N-1129 | Compressor Station Kipi Increment | Greece | DESFA S.A. | Less-Advanced | No |  | Yes | 2024 | 2024 | Non-Confidential | 39 |  | Non-Confidential | 5.85 |  | URL | Yes | 2.2.1.2
|  |  | TRA-N-1246 | Greece - Italy interconnection | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | No | 2025 | 2025 | Confidential |  |  | Confidential |  |  | URL | Yes | not applicable
PRJ-G-127 | Italian biomethane production | Less-Advanced | ETR-F-523 | Biomethane plants development | Italy | Snam4mobility | FID | No |  | No | 2023 | 2023 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | ETR-N-617 | Project to facilitate biomethane production plants inteconnection | Italy | Snam Rete Gas | Less-Advanced | No |  | No | 2022 | 2022 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | TRA-F-51 | Trans Adriatic Pipeline | Greece | Trans Adriatic Pipeline AG | FID | Yes | 7.1.3 | Yes | 2020 | 2020 | Confidential |  | 4500 | Confidential |  | 55 | URL | No | N/A
|  |  | TRA-F-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | Romania | SNTGN Transgaz SA | FID | Yes | 6.24.10.1 | Yes | 2020 | 2020 | Non-Confidential | 79.44 |  | Non-Confidential | 12.55 |  | URL | Yes | 7.3
|  |  | LNG-F-163 | Gran Canaria LNG Terminal | Spain | Gascan | FID | No |  | No | 2029 | 2029 | Non-Confidential | 271.5 |  | Non-Confidential | 0 |  |  | Yes | No code in the NDP
|  |  | LNG-F-178 | Musel LNG terminal | Spain | Enagas Transporte S.A.U. | FID | No |  | No | 2021 | 2021 | Non-Confidential | 0.1 |  | Non-Confidential | 0 |  |  | Yes | No code in the NDP
|  |  | LNG-F-183 | Tenerife LNG Terminal | Spain | Gascan | FID | No |  | No | 2022 | 2022 | Non-Confidential | 271.5 |  | Non-Confidential | 0 |  |  | Yes | No code in the NDP
|  |  | TRA-F-208 | Reverse Flow TENP Germany | Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | FID | Yes | 5.10 | No | 2020 | 2020 | Confidential |  |  | Confidential |  |  | URL | Yes | 305-02
|  |  | TRA-F-247 | North - South Gas Corridor in Western Poland | Poland | GAZ-SYSTEM S.A. | FID | Yes | 6.2.11 | No | 2021 | 2021 | Confidential |  |  | Confidential |  |  | URL | Yes | N/A
|  |  | UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | Italy | STOGIT | FID | No |  | No | 2028 | 2028 | Confidential |  |  | Confidential |  |  |  | Yes | not applicable
|  |  | LNG-F-272 | Upgrade of LNG terminal in Świnoujście | Poland | GAZ-SYSTEM S.A. | FID | Yes | 8.7 | Yes | 2023 | 2023 | Confidential |  | 66.8 | Confidential |  | 12.75 | URL | Yes | N/A
|  |  | TRA-F-291 | NOWAL - Nord West Anbindungsleitung | Germany | GASCADE Gastransport GmbH | FID | No |  | No | 2020 | 2020 | Non-Confidential | 4 |  | Non-Confidential | 0.23 |  | URL | Yes | 410-01a and 410-01b
|  |  | TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | Bulgaria | Bulgartransgaz EAD | FID | Yes | 6.8.2 | Yes | 2021 | 2024 | Non-Confidential | 339.59 |  | Non-Confidential | 4.55 |  | URL | Yes | Section 5.5.
|  |  | UGS-F-311 | Bilciuresti daily withdrawal capacity increase | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | FID | No |  | Yes | 2025 | 2025 | Non-Confidential | 59 |  | Non-Confidential | 2.8 |  |  | No | N/A
|  |  | TRA-F-329 | ZEELINK | Germany | Open Grid Europe GmbH and Thyssengas GmbH | FID | No |  | No | 2023 | 2023 | Non-Confidential | 707 |  | Confidential |  |  | URL | Yes | 203-02, 204-02a-d, 205-02a-b, 416-02,
|  |  | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | Croatia | Plinacro Ltd | FID | Yes | 6.5.5 | No | 2019 | 2019 | Confidential |  |  | Confidential |  |  | URL | Yes | 5.1
|  |  | TRA-F-340 | CS Wertingen | Germany | bayernets GmbH | FID | No |  | No | 2019 | 2019 | Non-Confidential | 107 |  | Confidential |  |  | URL | Yes | 036-04
|  |  | TRA-F-357 | NTS developments in North-East Romania | Romania | SNTGN Transgaz SA | FID | No |  | No | 2021 | 2021 | Non-Confidential | 174.25 |  | Non-Confidential | 5.26 |  | URL | Yes | 7.4
|  |  | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase I | Romania | SNTGN Transgaz S.A. | FID | Yes | 6.24.1.2 | Yes | 2020 | 2020 | Non-Confidential | 478.6 |  | Non-Confidential | 11.77 |  | URL | Yes | 7.1.1
|  |  | UGS-F-374 | Enhancement of Incukalns UGS | Latvia | JSC "Conexus Baltic Grid" | FID | Yes | 8.2.4 | Yes | 2019 | 2025 | Non-Confidential | 88 |  | Non-Confidential | 0.9 |  | URL | No | N/A
|  |  | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | Bulgaria | ICGB a.d. | FID | Yes | 6.8.1 | Yes | 2020 | 2025 | Non-Confidential | 240 |  | Non-Confidential | 4.5 |  | URL | Yes | not applicable
|  |  | TRA-F-409 | Larino - Chieti | Italy | SGI S.p.A: | FID | No |  | No | 2022 | 2022 | Non-Confidential | 135 |  | Non-Confidential | 0.5 |  | URL | Yes | 5712
|  |  | TRA-F-424 | SAN MARCO - RECANATI | Italy | SGI S.p.A. | FID | No |  | No | 2022 | 2022 | Non-Confidential | 45 |  | Non-Confidential | 0.3 |  | URL | Yes | 5681
|  |  | TRA-F-500 | L/H Conversion Belgium | Belgium | Fluxys Belgium | FID | Yes | 5.21 | Yes | 2026 | 2026 | Non-Confidential | 50 |  | Non-Confidential | 1 |  | URL | Yes | L/H Conversion
|  |  | ETR-F-516 | CNG and L-CNG stations | Italy | Snam4mobility | FID | No |  | No | 2022 | 2022 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | ETR-F-541 | CORE LNGas hive and LNGHIVE2 Infrastructure and logistic solutions | Spain | Enagas Transporte S.A.U. | FID | No |  | No | 2020 | 2020 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | ETR-F-546 | Jupiter 1000: first industrial demonstrator of Power to Gas in France | France | GRTgaz, Terega | FID | No |  | No | 2020 | 2020 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | TRA-F-592 | Balkan Gas Hub-Necessary expansion of the Bulgarian gas transmission system | Bulgaria | Bulgartransgaz EAD | FID | Yes | 6.25.4 | Yes | 2020 | 2022 | Non-Confidential | 1.415 |  | Non-Confidential | 57.02 |  |  | Yes | Section 5.1. (5.1.1)
|  |  | ETR-F-599 | Sector coupling: hybrid compressor station | Italy | Snam Rete Gas S.p.A. | FID | No |  | No | 2024 | 2024 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | ETR-F-632 | Railway project roadmap. Transformation to LNG | Spain | Enagas Transporte S.A.U. | FID | No |  | No | 2022 | 2022 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | ETR-F-743 | Impulse 2025 | France | Teréga | FID | No |  | No | 2025 | 2025 | Non-Confidential | 18.8 |  | Confidential |  |  |  | No | N/A
|  |  | TRA-F-755 | CS Rimpar | Germany | GRTgaz Deutschland GmbH | FID | No |  | No | 2023 | 2023 | Non-Confidential | 184 |  | Confidential |  |  |  | Yes | 312-02
|  |  | LNG-F-824 | LNG Terminal in Klaipeda | Lithuania | AB Klaipėdos Nafta | FID | No |  | Yes | 2024 | 2024 | Non-Confidential | 160 |  | Non-Confidential | 13 |  | URL | Yes | Action Plan of National Energy Independence strategy, aprroved by the Goverment on 2018-12-05, task 8.1.1.1.
|  |  | TRA-F-902 | Capacity increase at IP Lanžhot entry | Slovakia | eustream,a.s. (a joint-stock company) | FID | No |  | No | 2019 | 2019 | Confidential |  |  | Confidential |  |  | URL | Yes | 4.1.1.3. Lanžhot
|  |  | TRA-F-915 | Enhancement of Estonia-Latvia interconnection | Estonia | Elering AS | FID | Yes | 8.2.2 | No | 2019 | 2019 | Non-Confidential | 37 |  | Non-Confidential | 1 |  | URL | Yes | paragraph 3.2
|  |  | TRA-F-918 | Capacity4Gas – CZ/SK | Czechia | NET4GAS, s.r.o. | FID | No |  | No | 2020 | 2020 | Non-Confidential | 13 |  | Non-Confidential | 0.4 |  | URL | Yes | TRA-F-918
|  |  | TRA-F-937 | Nord Stream 2 | Germany | Nord Stream 2 AG | FID | No |  | No | 2019 | 2019 | Non-Confidential | 8000 |  | Confidential |  |  | URL | No | N/A
|  |  | TRA-F-941 | Metering and Regulating station at Nea Messimvria | Greece | DESFA S.A. | FID | Yes | 7.1.3 | Yes | 2020 | 2020 | Non-Confidential | 12 |  | Non-Confidential | 0.2 |  | URL | Yes | 2.2.1.4
|  |  | TRA-F-954 | TAG Reverse Flow | Austria | Trans Austria Gasleitung GmbH | FID | No |  | No | 2020 | 2020 | Confidential |  |  | Confidential |  |  |  | Yes | TAG 2016-01
|  |  | TRA-F-964 | New NTS developments for taking over gas from the Black Sea shore | Romania | SNTGN Transgaz SA | FID | Yes | 6.24.10.3 | Yes | 2021 | 2021 | Non-Confidential | 9.14 |  | Non-Confidential | 0.56 |  |  | Yes | 7.6
|  |  | TRA-F-1169 | Trans-Balkan Bi-directional Flow | Ukraine | JSC "UKRTRANSGAZ" | FID | No |  | No | 2020 | 2020 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | TRA-F-1193 | TAP interconnection | Italy | Snam Rete Gas S.p.A. | FID | No |  | Yes | 2020 | 2020 | Non-Confidential | 183 |  | Non-Confidential | 0.1 |  | URL | Yes | RN_02
|  |  | TRA-F-1241 | Interconnection with production in Gela | Italy | Snam Rete Gas S.p.A. | FID | No |  | No | 2020 | 2020 | Non-Confidential | 2.7 |  | Non-Confidential | 0.01 |  |  | Yes | RN_17
|  |  | TRA-F-1254 | CS Elten | Germany | Open Grid Europe GmbH and Thyssengas GmbH | FID | No |  | No | 2022 | 2022 | Non-Confidential | 50 |  | Confidential |  |  | URL | Yes | 422/01
|  |  | TRA-F-1267 | Upgrade Sülstorf station | Germany | NGT GmbH / GUD GmbH & Co. KG / Fluxys D GmbH | FID | No |  | No | 2019 | 2019 | Non-Confidential | 3 |  | Non-Confidential | 0.2 |  | URL | Yes | 507-01k
|  |  | TRA-F-1271 | Compressor Station Krummhoern | Germany | Open Grid Europe GmbH | FID | No |  | No | 2022 | 2022 | Non-Confidential | 102 |  | Confidential |  |  | URL | Yes | 414-01 an 415-01
|  |  | TRA-F-1276 | Compressor station at Nea Messimvria (3rd unit) | Greece | DESFA S.A. | FID | No |  | Yes | 2022 | 2022 | Non-Confidential | 15 |  | Non-Confidential | 0.8 |  | URL | Yes | 2.1.2.8
|  |  | TRA-F-1277 | Upgrading GMS Isaccea 1 and GMS Negru Voda 1 | Romania | SNTGN Transgaz SA | FID | No |  | No | 2021 | 2021 | Non-Confidential | 26.65 |  | Non-Confidential | 0.97 |  |  | Yes | 7.8
|  |  | TRA-A-10 | Poseidon Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | Yes | 7.3.3 | Yes | 2022 | 2025 | Non-Confidential | 3400 |  | Non-Confidential | 52 |  | URL | Yes | n.a.
|  |  | TRA-A-12 | GALSI Pipeline Project | Italy | Galsi S.p.A. | Advanced | No |  | Yes | 2022 | 2022 | Confidential |  | 969.98 | Confidential |  | 17.46 | URL | Yes | n.a.
|  |  | LNG-A-30 | Shannon LNG Terminal and Connecting Pipeline | Ireland | Shannon LNG Ltd | Advanced | Yes | 5.3 | No | 2022 | 2029 | Confidential |  |  | Confidential |  |  | URL | Yes | 5.4
|  |  | TRA-A-31 | Melita TransGas Pipeline | Malta | Melita TransGas Co. Ltd. | Advanced | Yes | 5.19 | Yes | 2024 | 2024 | Non-Confidential | 409.8 |  | Non-Confidential | 3.6 |  | URL | Yes | Section 4.3.2
|  |  | LNG-A-32 | Project GO4LNG LNG terminal Gothenburg | Sweden | Swedegas AB | Advanced | Yes | 8.6 | Yes | 2022 | 2022 | Non-Confidential | 105 |  | Non-Confidential | 4.5 |  | URL | No | N/A
|  |  | ETR-A-64 | Biomethane reverse flow Denmark | Denmark | Energinet | Advanced | No |  | No | 2021 | 2021 | Non-Confidential | 29 |  | Non-Confidential | 2 |  |  | No | N/A
|  |  | TRA-A-68 | Ionian Adriatic Pipeline | Croatia | Plinacro Ltd | Advanced | No |  | Yes | 2023 | 2025 | Confidential |  | 576 | Confidential |  | 10.37 | URL | Yes | 1.12, 1.25-1.27, 5.5
|  |  | TRA-A-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Croatia | Plinacro Ltd | Advanced | No |  | Yes | 2023 | 2027 | Confidential |  | 135 | Confidential |  | 0.18 | URL | Yes | 1.30, 1.31, 1.22
|  |  | LNG-A-79 | Paldiski LNG Terminal | Estonia | Balti Gaas plc | Advanced | No |  | Yes | 2025 | 2025 | Non-Confidential | 370 |  | Non-Confidential | 7 |  | URL | Yes | -
|  |  | TRA-A-123 | Városföld CS | Hungary | FGSZ Ltd. | Advanced | Yes | 6.24.4.3 | Yes | 2022 | 2022 | Confidential |  | 20 | Confidential |  | 3.1 | URL | Yes | 12.10.
|  |  | UGS-A-138 | Balkan Gas Hub - UGS Chiren Expansion | Bulgaria | Bulgartransgaz EAD | Advanced | Yes | 6.20.2 | Yes | 2025 | 2025 | Non-Confidential | 237.977 |  | Non-Confidential | 3.08 |  | URL | Yes | Section 5.3 (5.3.1)
|  |  | UGS-A-233 | Depomures | Romania | Engie Romania SA | Advanced | Yes | 6.20.4 | Yes | 2021 | 2024 | Non-Confidential | 87 |  | Non-Confidential | 1.5 |  | URL | Yes | 8.5
|  |  | UGS-A-294 | Islandmagee Gas Storage Facility | United Kingdom | Islandmagee Storage Limited | Advanced | Yes | 5.1.3 | Yes | 2022 | 2026 | Non-Confidential | 325 |  | Non-Confidential | 8 |  | URL | Yes | n.a.
|  |  | LNG-A-295 | Mugardos LNG Terminal: Send-out Increase | Spain | Reganosa | Advanced | No |  | Yes | 2024 | 2024 | Non-Confidential | 36 |  | Non-Confidential | 2 |  | URL | Yes | No Number- Name: Ampliación Planta de Reganosa. Ampliación de Emisión a 825,600 Nm3/h
|  |  | LNG-A-296 | Mugardos LNG Terminal: 2nd Jetty | Spain | Reganosa | Advanced | No |  | Yes | 2024 | 2024 | Non-Confidential | 45 |  | Non-Confidential | 0.2 |  | URL | No | N/A
|  |  | TRA-A-320 | Carregado Compressor Station | Portugal | REN-Gasodutos, S.A. | Advanced | No |  | No | 2025 | 2025 | Non-Confidential | 24 |  | Non-Confidential | 0.89 |  | URL | Yes | -
|  |  | TRA-A-330 | EastMed Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | Yes | 7.3.1 | Yes | 2025 | 2025 | Non-Confidential | 5200 |  | Non-Confidential | 90 |  | URL | No | N/A
|  |  | TRA-A-339 | Trans-Caspian | Turkmenistan | W-Stream Caspian Pipeline Company OU | Advanced | Yes | 7.1.1 | Yes | 2022 | 2023 | Non-Confidential | 1500 |  | Non-Confidential | 16 |  | URL | No | N/A
|  |  | TRA-A-362 | Development on the Romanian territory of the Southern Transmission Corridor | Romania | SNTGN Transgaz SA | Advanced | Yes | 6.24.4.5 | Yes | 2021 | 2021 | Non-Confidential | 360.4 |  | Non-Confidential | 0.83 |  | URL | Yes | 7.2
|  |  | TRA-A-394 | Norwegian tie-in to Danish upstream system | Denmark | Energinet.dk | Advanced | No |  | No | 2022 | 2022 | Non-Confidential | 290 |  | Non-Confidential | 5.96 |  | URL | No | N/A
|  |  | TRA-A-408 | Wilhelmshaven LNG-Terminal Anbindungsleitung | Germany | Open Grid Europe GmbH | Advanced | No |  | No | 2022 | 2022 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | TRA-A-429 | Adaptation L- gas - H-gas | France | GRTgaz and Storengy | Advanced | Yes | 5.21 | Yes | 2025 | 2025 | Non-Confidential | 123 |  | Non-Confidential | 1.5 |  | URL | Yes | Plan de conversion du gaz B en gaz H
|  |  | ETR-A-437 | Supercritical water gasification facilities | Netherlands | N.V. Nederlandse Gasunie | Advanced | No |  | No | 2021 | 2021 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | ETR-A-504 | Sun2Hy | Spain | Enagas S.A. | Advanced | No |  | No | 2023 | 2023 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | ETR-A-519 | Hub Baleares | Spain | Enagas S.A. | Advanced | No |  | No | 2023 | 2023 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | TRA-A-782 | TANAP X- Expansion of Trans Anatolian Natural Gas Pipeline Projec | Turkey | SOCAR (The State Oil Company of the Azerbaijan Republic) | Advanced | Yes | 7.1.1 | Yes | 2025 | 2025 | Non-Confidential | 750 |  | Non-Confidential | 150 |  | URL | No | N/A
|  |  | TRA-A-950 | Guitiriz - Lugo - Zamora pipeline | Spain | Reganosa | Advanced | No |  | Yes | 2024 | 2024 | Non-Confidential | 249 |  | Non-Confidential | 4.7 |  | URL | Yes | N/A.
|  |  | LNG-A-962 | Tallinn LNG | Estonia | Liwathon E.O.S. AS / Port of Tallinn AS | Advanced | No |  | Yes | 2022 | 2022 | Non-Confidential | 250 |  | Non-Confidential | 15 |  | URL | Yes | Paragraph 3 point 7
|  |  | TRA-A-967 | Nea-Messimvria to Evzoni/Gevgelija pipeline (IGNM) | Greece | DESFA S.A. | Advanced | No |  | Yes | 2022 | 2022 | Non-Confidential | 49.1 |  | Non-Confidential | 0.7 |  | URL | Yes | 2.1.2.1
|  |  | TRA-A-980 | Interconnection North Macedonia-Greece (North Macedonian part) | North Macedonia | MER JSC Skopje | Advanced | No |  | No | 2022 | 2022 | Confidential |  |  | Confidential |  |  |  | Yes | Energy sector, no. 2
|  |  | LNG-A-1146 | Cyprus Gas2EU | Cyprus | Ministry of Energy, Commerce and Industry (MECI) | Advanced | Yes | 7.5 | Yes | 2022 | 2022 | Confidential |  | 300 | Confidential |  | 200 | URL | No | N/A
|  |  | TRA-A-1268 | Romania-Serbia Interconnection | Romania | SNTGN Tranzgaz SA | Advanced | No |  | No | 2020 | 2020 | Non-Confidential | 53.76 |  | Non-Confidential | 231 |  |  | Yes | 7.7
|  |  | TRA-A-1303 | IAEF - Vlora ccgt | Albania | Albgaz Sha | Advanced | No |  | Yes | 2020 | 2020 | Confidential |  | 21.86 | Confidential |  | 0.39 | URL | Yes | PiP1
|  |  | TRA-N-7 | Development for new import from the South (Adriatica Line) | Italy | Snam Rete Gas S.p.A. | Less-Advanced | Yes | 7.3.4 | Yes | 2026 | 2026 | Non-Confidential | 1384 |  | Non-Confidential | 4.4 |  | URL | Yes | RN_04
|  |  | TRA-N-8 | Import developments from North-East | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | No | 2034 | 2034 | Confidential |  |  | Confidential |  |  | URL | Yes | RN_06
|  |  | TRA-N-9 | Additional Southern developments | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | No | 2034 | 2034 | Confidential |  |  | Confidential |  |  | URL | Yes | RN_07
|  |  | ETR-N-20 | GNI Renewable Gas Central Grid Injection Project | Ireland | Gas Networks Ireland | Less-Advanced | No |  | No | 2023 | 2028 | Non-Confidential | 110 |  | Non-Confidential | 9.7 |  | URL | No | N/A
|  |  | ETR-N-22 | Ervia Cork CCUS | Ireland | Ervia (parent company of Gas Networks Ireland) | Less-Advanced | No |  | No | 2028 | 2028 | Non-Confidential | 1559 |  | Non-Confidential | 149 |  | URL | No | N/A
|  |  | TRA-N-27 | Physical reverse flow from NI to GB and IE via SNIP pipeline | United Kingdom | Premier Transmission Limited | Less-Advanced | Yes | 5.1.2 | Yes | 2021 | 2021 | Non-Confidential | 60 |  | Non-Confidential | 2.5 |  | URL | Yes | 5.1.2
|  |  | TRA-N-53 | White Stream | Georgia | White Stream Ltd | Less-Advanced | No |  | Yes | 2023 | 2023 | Non-Confidential | 3900 |  | Non-Confidential | 55 |  | URL | No | N/A
|  |  | ETR-N-80 | Power to Gas Production with infrastructure building/enhacement in Latvia | Latvia | JSC "Conexus Baltic Grid" | Less-Advanced | No |  | No | 2025 | 2025 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | Slovenia | Plinovodi d.o.o. | Less-Advanced | No |  | Yes | 2025 | 2025 | Confidential |  | 12.2 | Confidential |  | 1.93 | URL | Yes | C1
|  |  | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.26.1.2 | Yes | 2023 | 2023 | Confidential |  | 80.4 | Confidential |  | 3.97 | URL | Yes | C5
|  |  | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Slovenia | Plinovodi d.o.o. | Less-Advanced | No |  | Yes | 2025 | 2025 | Confidential |  | 33.1 | Confidential |  | 0.14 | URL | Yes | C2
|  |  | ETR-N-125 | Biomethane production with infrastructure building/enhancement in Latvia | Latvia | JSC "Conexus Baltic Grid" | Less-Advanced | No |  | No | 2025 | 2025 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | TRA-N-128 | Compressor Station Kipi | Greece | DESFA S.A. | Less-Advanced | Yes | 6.8.1 | Yes | 2024 | 2024 | Non-Confidential | 19 |  | Non-Confidential | 2.8 |  | URL | Yes | 2.2.1.2
|  |  | TRA-N-137 | Balkan Gas Hub - Interconnection Bulgaria - Serbia | Bulgaria | Bulgartransgaz EAD | Less-Advanced | Yes | 6.10 | Yes | 2022 | 2022 | Non-Confidential | 48 |  | Non-Confidential | 1 |  |  | Yes | Sectin 5.2 (5.2.3)
|  |  | ETR-N-226 | Fos Tonkin LNG Terminal Evolution | France | Elengy | Less-Advanced | No |  | No | 2022 | 2022 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | TRA-N-245 | North - South Gas Corridor in Eastern Poland | Poland | GAZ-SYSTEM S.A. | Less-Advanced | Yes | 6.2.2 | Yes | 2029 | 2029 | Confidential |  | 1020 | Confidential |  | 22 | URL | Yes | N/A
|  |  | LNG-N-297 | Mugardos LNG Terminal: Storage Extension | Spain | Reganosa | Less-Advanced | No |  | No | 2026 | 2026 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | TRA-N-299 | M3/1 Šempeter - Vodice | Slovenia | Plinovodi d.o.o. | Less-Advanced | No |  | Yes | 2026 | 2026 | Confidential |  | 169 | Confidential |  | 0.9 | URL | Yes | C7, C8, C9 (3 sections)
|  |  | ETR-N-300 | HyOffWind Zeebrugge | Belgium | Fluxys, Eoly, Parkwind | Less-Advanced | No |  | No | 2020 | 2020 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | LNG-N-304 | Italy-Sardinia Virtual Pipeline | Italy | Snam S.p.A. | Less-Advanced | No |  | No | 2021 | 2021 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | ETR-N-305 | PEGASUS | Italy | S.G.I. SpA | Less-Advanced | No |  | No | 2024 | 2024 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | ETR-N-306 | Greening of Gas (GoG) | Czechia | NET4GAS, s.r.o. | Less-Advanced | No |  | No | 2023 | 2023 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | ETR-N-315 | G2F - Gas to Future | Slovakia | NAFTA a.s. (joint stock company) | Less-Advanced | No |  | No | 2025 | 2025 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Croatia | Plinacro Ltd | Less-Advanced | No |  | No | 2029 | 2029 | Confidential |  |  | Confidential |  |  | URL | Yes | 1.37
|  |  | UGS-N-347 | Gas storage facility Grubisno Polje | Croatia | Podzemno skladiste plina Ltd | Less-Advanced | No |  | No | 2025 | 2025 | Non-Confidential | 45 |  | Non-Confidential | 0.45 |  | URL | No | N/A
|  |  | TRA-N-354 | Interconnection with Slovenia | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | No | 2023 | 2023 | Confidential |  |  | Confidential |  |  | URL | Yes | RN_03
|  |  | UGS-N-371 | Sarmasel undeground gas storage in Romania | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | Yes | 6.20.6 | Yes | 2024 | 2024 | Confidential |  | 133.22 | Confidential |  | 2.66 | URL | No | N/A
|  |  | UGS-N-385 | South Kavala Underground Gas Storage facility | Greece | Hellenic Republic Asset Development Fund | Less-Advanced | Yes | 6.20.3 | Yes | 2023 | 2023 | Confidential |  | 320 | Confidential |  | 4.8 | URL | No | N/A
|  |  | UGS-N-398 | Ghercesti underground gas storage in Romania | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | No |  | Yes | 2026 | 2026 | Non-Confidential | 122 |  | Non-Confidential | 7 |  | URL | No | N/A
|  |  | UGS-N-399 | Falticeni UGS | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | No |  | No | 2029 | 2029 | Non-Confidential | 80 |  | Non-Confidential | 4.68 |  | URL | No | N/A
|  |  | ETR-N-401 | Antwerp@C | Belgium | Fluxys and Antwerp Port Authority | Less-Advanced | No |  | No | 2026 | 2026 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | TRA-N-402 | TENP Security of Supply | Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | Less-Advanced | No |  | No | 2024 | 2024 | Confidential |  |  | Confidential |  |  |  | Yes | 552-01 / 554-01 / 555-01
|  |  | ETR-N-406 | hybridge - gas grid infrastructure | Germany | Open Grid Europe GmbH | Less-Advanced | No |  | No | 2023 | 2023 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | TRA-N-423 | GCA Mosonmagyaróvár | Austria | GAS CONNECT AUSTRIA GmbH | Less-Advanced | Yes | 6.24.1.3 | Yes | 2024 | 2024 | Non-Confidential | 75 |  | Non-Confidential | 7 |  | URL | Yes | GCA 2015/05
|  |  | ETR-N-427 | P2G integrated in Reganosa NG Transmission Grid | Spain | Reganosa | Less-Advanced | No |  | No | 2024 | 2024 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | TRA-N-439 | Stazione di Spinta "San Marco" | Italy | S.G.I. S.p.A. | Less-Advanced | No |  | No | 2022 | 2022 | Non-Confidential | 44 |  | Non-Confidential | 3.7 |  | URL | Yes | 5515
|  |  | ETR-N-449 | Hydrogen Region Lausitz | Germany | ONTRAS Gastransport GmbH | Less-Advanced | No |  | No | 2021 | 2021 | Non-Confidential | 400 |  | Non-Confidential | 20 |  |  | No | N/A
|  |  | ETR-N-452 | Element Eins | Germany | Thyssengas GmbH, Gasunie Deutschland Transport Services GmbH, Tennet TSO Gm | Less-Advanced | No |  | No | 2022 | 2028 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | ETR-N-483 | L2DG (LNG to Decarbonised Gas) | Spain | Reganosa | Less-Advanced | No |  | No | 2024 | 2024 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | ETR-N-501 | Hub País Vasco | Spain | Enagas S.A. | Less-Advanced | No |  | No | 2023 | 2023 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | ETR-N-521 | Hub Murcia | Spain | Enagas S.A. | Less-Advanced | No |  | No | 2023 | 2023 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | ETR-N-528 | Microliquefaction plants | Italy | Snam4mobility | Less-Advanced | No |  | No | 2022 | 2022 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | ETR-N-537 | Hub Aragon | Spain | Enagas S.A. | Less-Advanced | No |  | No | 2022 | 2022 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | ETR-N-562 | Energy Park Bad Lauchstädt | Germany | ONTRAS Gastransport GmbH | Less-Advanced | No |  | No | 2023 | 2023 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | ETR-N-591 | Power to gas plant in the south of Italy | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | No | 2025 | 2025 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | ETR-N-595 | Transport of hydrogen into natural gas network | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | No | 2025 | 2025 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | TRA-N-598 | NTS developments in North-Vest Romania | Romania | SNTGN Transgaz SA | Less-Advanced | No |  | No | 2026 | 2026 | Non-Confidential | 405 |  | Non-Confidential | 2.8 |  |  | No | N/A
|  |  | ETR-N-616 | Renewable Methane according to NEP2020 | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | No |  | No | 2023 | 2025 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | ETR-N-622 | Renewable Hydrogen according to NEP2020 | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | No |  | No | 2020 | 2025 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | ETR-N-633 | GETH2-ETR 1 | Germany | Nowega GmbH | Less-Advanced | No |  | No | 2022 | 2022 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | ETR-N-728 | Biomethane: connecting production units and reverse flow projects | France | TEREGA | Less-Advanced | No |  | No | 2029 | 2029 | Confidential |  |  | Confidential |  |  |  | No | N/A
|  |  | TRA-N-810 | TAP Expansion | Greece | Trans Adriatic Pipeline AG | Less-Advanced | No |  | Yes | 2025 | 2025 | Non-Confidential | 1035 |  | Non-Confidential | 50 |  | URL | No | N/A
|  |  | UGS-N-914 | UGS Damasławek | Poland | GAZ-SYSTEM S.A. | Less-Advanced | No |  | No | 2026 | 2026 | Confidential |  |  | Confidential |  |  | URL | Yes | N/A
|  |  | LNG-N-947 | FSRU Polish Baltic Sea Coast | Poland | GAZ-SYSTEM S.A. | Less-Advanced | No |  | Yes | 2025 | 2025 | Confidential |  | 620 | Confidential |  | 64 | URL | Yes | N/A
|  |  | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | Romania | SNTGN Transgaz SA | Less-Advanced | Yes | 6.24.10.2 | Yes | 2023 | 2023 | Non-Confidential | 530 |  | Non-Confidential | 0.1 |  |  | Yes | 7.5
|  |  | TRA-N-971 | Compressor station at Nea Messimvria | Greece | DESFA S.A. | Less-Advanced | Yes | 7.1.3 | Yes | 2023 | 2023 | Non-Confidential | 30 |  | Non-Confidential | 0.4 |  | URL | Yes | 2.2.1.4
|  |  | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Croatia | Plinacro Ltd | Less-Advanced | Yes | 6.26.1.3 | No | 2029 | 2029 | Confidential |  |  | Confidential |  |  | URL | Yes | 5.3 and 5.4
|  |  | TRA-N-1063 | Export to Malta | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | Yes | 2024 | 2024 | Non-Confidential | 8 |  | Non-Confidential | 0.01 |  |  | No | N/A
|  |  | TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | Greece | DESFA S.A. | Less-Advanced | Yes | 6.9.1 | Yes | 2022 | 2022 | Non-Confidential | 16 |  | Non-Confidential | 0.4 |  | URL | No | N/A
|  |  | TRA-N-1091 | Metering and Regulating station at Megalopoli | Greece | DESFA S.A. | Less-Advanced | Yes | 7.1.3 | Yes | 2025 | 2025 | Non-Confidential | 7.5 |  | Non-Confidential | 0.15 |  | URL | No | N/A
|  |  | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | Greece | DESFA S.A. | Less-Advanced | Yes | 6.20.3 | Yes | 2023 | 2023 | Non-Confidential | 15 |  | Non-Confidential | 0.4 |  | URL | No | N/A
|  |  | TRA-N-1138 | South Caucasus Pipeline Future Expansion (SCPFX) | Azerbaijan | SOCAR Midstream Operations LLC | Less-Advanced | Yes | 7.1.1 | Yes | 2024 | 2024 | Confidential |  | 1047.5 | Confidential |  | 34.6 | URL | No | N/A
|  |  | TRA-N-1194 | Sardinia Methanization | Italy | ENURA S.p.A. | Less-Advanced | No |  | No | 2020 | 2025 | Confidential |  |  | Confidential |  |  | URL | Yes | RN_09
|  |  | TRA-N-1195 | Matagiola - Massafra pipeline | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | Yes | 2026 | 2026 | Non-Confidential | 240 |  | Non-Confidential | 0.11 |  | URL | Yes | RN_05
|  |  | TRA-N-1202 | GCP GAZ-SYSTEM/ONTRAS - incremental capacity project | Poland | GAZ-SYSTEM S.A. | Less-Advanced | No |  | No | 2023 | 2023 | Confidential |  |  | Confidential |  |  | URL | No | N/A
|  |  | TRA-N-1227 | Gorizia plant upgrade | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | Yes | 2026 | 2026 | Non-Confidential | 3 |  | Non-Confidential | 0.01 |  | URL | Yes | RN_16
|  |  | TRA-N-1265 | Biomethane productions interconnection | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | No | 2022 | 2022 | Confidential |  |  | Confidential |  |  |  | Yes | NA
|  |  | TRA-N-1278 | Compressor station at Ambelia | Greece | DESFA S.A. | Less-Advanced | No |  | Yes | 2023 | 2023 | Non-Confidential | 65 |  | Non-Confidential | 2.4 |  | URL | Yes | 2.1.2.2

## Transmission Projects
Pipelines including Compressor Stations
Type | Code | Project Name | Promoter | Maturity Status | Section | Length (km) | Diameter (mm) | Compressor Power (MW)
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Main onshore section | 773 | 1200 | 90
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Offshore section | 105 | 900
Pipeline including CS | TRA-F-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Plinacro Ltd | FID | Omišalj-Zlobin | 18 | 800
Pipeline including CS | TRA-F-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | SNTGN Transgaz SA | FID | Onesti - Cosmesti |  |  | 9
Pipeline including CS | TRA-F-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | SNTGN Transgaz SA | FID | Onesti - Cosmesti | 66 | 813
Pipeline including CS | TRA-F-190 | Poland - Slovakia interconnection | eustream,a.s. (a joint-stock company) | FID | Slovak section | 106 | 1000 | 0
Pipeline including CS | TRA-F-208 | Reverse Flow TENP Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | FID
Pipeline including CS | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. | FID | GIPL - Polish section | 343 | 700
Pipeline including CS | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. | FID | CS Hołowczyce - modernization
Pipeline including CS | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. | FID | CS Gustorzyn |  |  | 16
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. | FID | Kędzierzyn Node
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. | FID | CS Kędzierzyn |  |  | 30
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. | FID | Zdzieszowice - Wrocław pipeline | 130 | 1000
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. | FID | Tworóg-Kędzierzyn Koźle pipeline | 43 | 1000
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. | FID | Zdzieszowice-Kędzierzyn Koźle | 19 | 1000
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | FID | PL-SK Interconnection - Polish section | 59 | 1000
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | FID | Strachocina - Pogórska Wola pipeline | 98 | 1000
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | FID | Pogórska Wola - Tworzeń pipeline | 168 | 1000
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | FID | Tworóg - Tworzeń pipeline | 56 | 1000
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | FID | CS Strachocina |  |  | 30
Pipeline including CS | TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | FGSZ Ltd. | FID | Csanadpalota |  |  | 9
Pipeline including CS | TRA-F-291 | NOWAL - Nord West Anbindungsleitung | GASCADE Gastransport GmbH | FID
Pipeline including CS | TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | Bulgartransgaz EAD | FID | PF Beglej - VA Dermantsi - VA Batultsi - VA Kalugerovo | 58 | 700
Pipeline including CS | TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | Bulgartransgaz EAD | FID | Valchi Dol - Preselka | 23 | 700
Pipeline including CS | TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | Bulgartransgaz EAD | FID | Lozenets-Nedyalsko | 20 | 1000
Pipeline including CS | TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | Bulgartransgaz EAD | FID | Gorni Bogrov - Novi Iskar | 19 | 700 | 20
Pipeline including CS | TRA-F-307 | H-gas exit OSZ GTG Nord | Gasunie Transport Services B.V. | FID
Pipeline including CS | TRA-F-329 | ZEELINK | Open Grid Europe GmbH and Thyssengas GmbH | FID | CS Würselen |  |  | 39
Pipeline including CS | TRA-F-329 | ZEELINK | Open Grid Europe GmbH and Thyssengas GmbH | FID | ZEELINK 1 | 112 | 1000
Pipeline including CS | TRA-F-329 | ZEELINK | Open Grid Europe GmbH and Thyssengas GmbH | FID | ZEELINK 2 | 115 | 1000
Pipeline including CS | TRA-F-329 | ZEELINK | Open Grid Europe GmbH and Thyssengas GmbH | FID | CS Legden |  |  | 26
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | Plinacro Ltd | FID | CS 1 |  |  | 4
Pipeline including CS | TRA-F-340 | CS Wertingen | bayernets GmbH | FID
Pipeline including CS | TRA-F-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | AB Amber Grid | FID | Border PL/LT - Jauniunai | 165 | 700
Pipeline including CS | TRA-F-357 | NTS developments in North-East Romania | SNTGN Transgaz SA | FID | Onesti - Gheraesti - Letcani | 165 | 711 | 18
Pipeline including CS | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase I | SNTGN Transgaz S.A. | FID | Phase I: Podisor-Recas | 479 | 800 | 28
Pipeline including CS | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | FID | IGB | 182 | 813 | 12
Pipeline including CS | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | FID | IGB | 182 | 813
Pipeline including CS | TRA-F-409 | Larino - Chieti | SGI S.p.A: | FID | Larino - Chieti | 113 | 600
Pipeline including CS | TRA-F-424 | SAN MARCO - RECANATI | SGI S.p.A. | FID | San Marco-Recanati | 35 | 600
Pipeline including CS | TRA-F-500 | L/H Conversion Belgium | Fluxys Belgium | FID
Pipeline including CS | TRA-F-592 | Balkan Gas Hub-Necessary expansion of the Bulgarian gas transmission system | Bulgartransgaz EAD | FID | New gas pipeline from the BG-TR border to GMS Strandzha | 11 | 1200
Pipeline including CS | TRA-F-592 | Balkan Gas Hub-Necessary expansion of the Bulgarian gas transmission system | Bulgartransgaz EAD | FID | New gas pipeline from CS Provadia to the Bulgarian-Serbian border | 474 | 1200 | 64
Pipeline including CS | TRA-F-752 | Capacity4Gas – DE/CZ | NET4GAS, s.r.o. | FID | HSK-Přimda | 2 | 1400 | 25
Pipeline including CS | TRA-F-752 | Capacity4Gas – DE/CZ | NET4GAS, s.r.o. | FID | HSK-Přimda | 150 | 1400
Pipeline including CS | TRA-F-755 | CS Rimpar | GRTgaz Deutschland GmbH | FID | CS Rimpar / MEGAL | 0 | 0 | 30
Pipeline including CS | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | FID | EUGAL | 484 | 1400 | 75
Pipeline including CS | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | FID | AL NEL | 1 | 1000
Pipeline including CS | TRA-F-780 | Baltic Pipe project – onshore section in Denmark | Energinet | FID | Baltic Pipe project – onshore section in Denmark | 210 | 1000 | 36
Pipeline including CS | TRA-F-814 | Upgrade for IP Deutschneudorf et al. for More Capacity | ONTRAS Gastransport GmbH | FID | Connection Kienbaum-EUGAL |  | 700
Pipeline including CS | TRA-F-895 | Balticconnector | Elering AS | FID | EE Onshore | 55 | 700 | 10
Pipeline including CS | TRA-F-895 | Balticconnector | Elering AS | FID | Offshore | 40 | 500
Pipeline including CS | TRA-F-902 | Capacity increase at IP Lanžhot entry | eustream,a.s. (a joint-stock company) | FID | Capacity increase at IP Lanžhot entry |  |  | 46
Pipeline including CS | TRA-F-915 | Enhancement of Estonia-Latvia interconnection | Elering AS | FID | Karksi GMS, Puiatu CS |  |  | 10
Pipeline including CS | TRA-F-918 | Capacity4Gas – CZ/SK | NET4GAS, s.r.o. | FID | Capacity4Gas - CZ/SK
Pipeline including CS | TRA-F-928 | Balticconnector Finnish part | Baltic Connector Oy | FID | Offshore | 40 | 500
Pipeline including CS | TRA-F-928 | Balticconnector Finnish part | Baltic Connector Oy | FID | FI Onshore | 20 | 500 | 10
Pipeline including CS | TRA-F-937 | Nord Stream 2 | Nord Stream 2 AG | FID | Nord Stream 2 | 1200 | 1153
Pipeline including CS | TRA-F-941 | Metering and Regulating station at Nea Messimvria | DESFA S.A. | FID | Nea-Messivria to TAP | 1
Pipeline including CS | TRA-F-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | FID
Pipeline including CS | TRA-F-954 | TAG Reverse Flow | Trans Austria Gasleitung GmbH | FID | CS Eggendorf/Weitendorf
Pipeline including CS | TRA-F-964 | New NTS developments for taking over gas from the Black Sea shore | SNTGN Transgaz SA | FID | Vadu-Gradina | 25 | 508
Pipeline including CS | TRA-N-1169 | Trans-Balkan Bi-directional Flow | JSC "UKRTRANSGAZ" | FID | Phase 1 | 355 | 800 | 0
Pipeline including CS | TRA-F-1193 | TAP interconnection | Snam Rete Gas S.p.A. | FID | Tap Interconnection | 55 | 1400
Pipeline including CS | TRA-F-1241 | Interconnection with production in Gela | Snam Rete Gas S.p.A. | FID | all the project | 1 | 500 | 0
Pipeline including CS | TRA-F-1254 | CS Elten | Open Grid Europe GmbH and Thyssengas GmbH | FID | CS Elten |  |  | 11
Pipeline including CS | TRA-F-1267 | Upgrade Sülstorf station | NGT GmbH / GUD GmbH & Co. KG / Fluxys D GmbH | FID
Pipeline including CS | TRA-F-1271 | Compressor Station Krummhoern | Open Grid Europe GmbH | FID | CS Krummhoern extension step 1 |  |  | 13
Pipeline including CS | TRA-F-1271 | Compressor Station Krummhoern | Open Grid Europe GmbH | FID | CS Krummhoern extension step 2 |  |  | 13
Pipeline including CS | TRA-F-1276 | Compressor station at Nea Messimvria (3rd unit) | DESFA S.A. | FID | Nea Messimvria |  |  | 8
Pipeline including CS | TRA-F-1277 | Upgrading GMS Isaccea 1 and GMS Negru Voda 1 | SNTGN Transgaz SA | FID | A
Pipeline including CS | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | Poseidon onshore section | 770 | 1220 | 75
Pipeline including CS | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | Poseidon offshore section | 210 | 813 | 75
Pipeline including CS | TRA-A-12 | GALSI Pipeline Project | Galsi S.p.A. | Advanced | GALSI International Section | 288 | 660 | 99
Pipeline including CS | TRA-A-12 | GALSI Pipeline Project | Galsi S.p.A. | Advanced | GALSI Italian Section 1 onshore pipeline crossing Sardinia | 285 | 1219
Pipeline including CS | TRA-A-12 | GALSI Pipeline Project | Galsi S.p.A. | Advanced | GALSI Italian Section 2 sealine Sardinia - Tuscany | 288 | 812 | 52
Pipeline including CS | TRA-A-21 | Bidirectional Austrian-Czech Interconnector (BACI) | GAS CONNECT AUSTRIA GmbH | Advanced | Austrian Side | 49 | 800
Pipeline including CS | TRA-A-21 | Bidirectional Austrian-Czech Interconnector (BACI) | GAS CONNECT AUSTRIA GmbH | Advanced | Czech Side | 12 | 800
Pipeline including CS | TRA-A-31 | Melita TransGas Pipeline | Melita TransGas Co. Ltd. | Advanced | Delimara (Malta) to Gela (Sicily) Italy | 159 | 560 | 0
Pipeline including CS | TRA-A-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. | Advanced | Alexandroupolis LNG terminal - M/R Amfitriti | 28 | 762 | 0
Pipeline including CS | TRA-A-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced | IAP - Croatian part | 250 | 800 | 1
Pipeline including CS | TRA-A-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced | IAP- Montenego part | 110 | 800
Pipeline including CS | TRA-A-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced | IAP- Albanian part | 180 | 800
Pipeline including CS | TRA-A-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Plinacro Ltd | Advanced | Negoslavci-Sotin | 10 | 800
Pipeline including CS | TRA-A-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Plinacro Ltd | Advanced | Sotin- Bačko Novo Selo | 5 | 800
Pipeline including CS | TRA-A-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Plinacro Ltd | Advanced | Osijek-Vukovar | 11 | 500
Pipeline including CS | TRA-A-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Plinacro Ltd | Advanced | Slobodnica-Negoslavci | 87 | 800
Pipeline including CS | TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla) | Plinacro Ltd | Advanced | BS Rakitje-Zabok | 26 | 700
Pipeline including CS | TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla) | Plinacro Ltd | Advanced | Lučko-BS Rakitje | 10 | 700
Pipeline including CS | TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla) | Plinacro Ltd | Advanced | Zabok-Jezerisce | 25 | 700
Pipeline including CS | TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla) | Plinacro Ltd | Advanced | Jezerisce-Sotla | 8 | 700
Pipeline including CS | TRA-A-123 | Városföld CS | FGSZ Ltd. | Advanced | Városföld CS |  |  | 6
Pipeline including CS | TRA-A-133 | Bidirectional Austrian Czech Interconnection (BACI) | NET4GAS, s.r.o. | Advanced | Břeclav (CZ) - Poštorná/Reintal (CZ/AT) | 12 | 800
Pipeline including CS | TRA-A-136 | Czech-Polish Gas Interconnector (CPI) | NET4GAS, s.r.o. | Advanced | Tvrdonice (CZ) - Hať (CZ/PL) | 207 | 1000 | 24
Pipeline including CS | TRA-A-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagas Transporte S.A.U. | Advanced | CS Martorell |  |  | 36
Pipeline including CS | TRA-A-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagas Transporte S.A.U. | Advanced | Hostalrich - Figueras | 79 | 900
Pipeline including CS | TRA-A-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagas Transporte S.A.U. | Advanced | Pipeline Figueras - French Border | 28 | 900
Pipeline including CS | TRA-A-252 | South Transit East Pyrenees (STEP) - TEREGA | TEREGA | Advanced | Pipeline Spanish Border-Barbaira | 120 | 900
Pipeline including CS | TRA-A-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | GAZ-SYSTEM S.A. | Advanced | Onshore pipeline connecting offshore pipeline with the national grid | 40 | 1000
Pipeline including CS | TRA-A-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | GAZ-SYSTEM S.A. | Advanced | Baltic Pipe (offshore section) | 280 | 900
Pipeline including CS | TRA-A-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | GAZ-SYSTEM S.A. | Advanced | Onshore receiving terminal in Poland
Pipeline including CS | TRA-A-273 | Poland - Czech Republic Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | PL-CZ Interconnection - Polish section | 53 | 1000
Pipeline including CS | TRA-A-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. | Advanced | Celorico-Spanish border | 162 | 700
Pipeline including CS | TRA-A-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Plinacro Ltd | Advanced | Zagvozd-Imotski-Posušje | 22 | 500
Pipeline including CS | TRA-A-320 | Carregado Compressor Station | REN-Gasodutos, S.A. | Advanced | Setubal - Leiria (Lote 1) |  |  | 14
Pipeline including CS | TRA-A-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | EastMed pipeline: section from Levantine Basin to Cyprus | 165 | 610
Pipeline including CS | TRA-A-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | EastMed pipeline: section from West Greece to Thesprotia | 236 | 1070
Pipeline including CS | TRA-A-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | EastMed pipeline: section from Crete to Peloponnese | 421 | 660 | 120
Pipeline including CS | TRA-A-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | EastMed pipeline: section from Cyprus to Crete | 732 | 660 | 100
Pipeline including CS | TRA-A-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | EastMed: section from Peloponnese to West Greece | 317 | 1070
Pipeline including CS | TRA-A-339 | Trans-Caspian | W-Stream Caspian Pipeline Company OU | Advanced | sub-sea (string 2) | 300 | 915 | 175
Pipeline including CS | TRA-A-339 | Trans-Caspian | W-Stream Caspian Pipeline Company OU | Advanced | sub-sea (string 1) | 300 | 915 | 175
Pipeline including CS | TRA-A-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | AB Amber Grid | Advanced
Pipeline including CS | TRA-A-362 | Development on the Romanian territory of the Southern Transmission Corridor | SNTGN Transgaz SA | Advanced | Black Sea shore - Podișor | 308 | 1200
Pipeline including CS | TRA-A-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | FGSZ Ltd. | Advanced | Csanádpalota |  |  | 4
Pipeline including CS | TRA-A-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | JSC "Conexus Baltic Grid" | Advanced
Pipeline including CS | TRA-A-394 | Norwegian tie-in to Danish upstream system | Energinet.dk | Advanced | Norwegian tie-in to Danish upstream system | 105 | 800 | 0
Pipeline including CS | TRA-A-408 | Wilhelmshaven LNG-Terminal Anbindungsleitung | Open Grid Europe GmbH | Advanced
Pipeline including CS | TRA-A-429 | Adaptation L- gas - H-gas | GRTgaz and Storengy | Advanced | Connection to H-gas grid
Pipeline including CS | TRA-A-429 | Adaptation L- gas - H-gas | GRTgaz and Storengy | Advanced | Arleux interconnection station
Pipeline including CS | TRA-A-429 | Adaptation L- gas - H-gas | GRTgaz and Storengy | Advanced | Bethune area | 8 | 300
Pipeline including CS | TRA-A-429 | Adaptation L- gas - H-gas | GRTgaz and Storengy | Advanced | Taisnieres interconnection station
Pipeline including CS | TRA-A-429 | Adaptation L- gas - H-gas | GRTgaz and Storengy | Advanced | Brouckerque area | 2 | 200
Pipeline including CS | TRA-A-429 | Adaptation L- gas - H-gas | GRTgaz and Storengy | Advanced | Interconnection with Gournay UGS
Pipeline including CS | TRA-A-496 | Increase of Gas Transport to the Netherlands | Gasunie Deutschland Transport Service GmbH | Advanced
Pipeline including CS | TRA-A-561 | Poland-Ukraine Interconnector (Ukrainian section) | PJSC UKRTRANSGAZ | Advanced | Drozdovychi - Bilche Volytsya | 99 | 1000 | 0
Pipeline including CS | TRA-A-621 | Poland - Ukraine Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | Hermanowice Node - PL/UA border pipeline | 2 | 1000
Pipeline including CS | TRA-A-621 | Poland - Ukraine Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | Metering station in Poland
Pipeline including CS | TRA-A-628 | Eastring - Slovakia | eustream, a.s. (a joint stock company) | Advanced | Eastring-SK | 17 | 1400 | 93
Pipeline including CS | TRA-A-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Advanced | Eastring-BG-2 | 262 | 1400 | 93
Pipeline including CS | TRA-A-655 | Eastring - Romania | SNTGN Transgaz SA | Advanced | Eastring RO/Phase 1 | 646 | 1400 | 93
Pipeline including CS | TRA-A-656 | Eastring - Hungary | FGSZ Ltd. | Advanced | Eastring - HU | 28284 | 1400
Pipeline including CS | TRA-A-782 | TANAP X- Expansion of Trans Anatolian Natural Gas Pipeline Projec | SOCAR (The State Oil Company of the Azerbaijan Republic) | Advanced | Georgia/Turkey border- Eskishehir | 1347 | 1442 | 125
Pipeline including CS | TRA-A-782 | TANAP X- Expansion of Trans Anatolian Natural Gas Pipeline Projec | SOCAR (The State Oil Company of the Azerbaijan Republic) | Advanced | Eskishehir (Turkey)-Greece Border | 460 | 1219 | 70
Pipeline including CS | TRA-A-808 | Additional transport of gas volumes to the Netherlands | Gasunie Deutschland Transport Services GmbH | Advanced
Pipeline including CS | TRA-A-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | Gas Networks Ireland | Advanced | Interconnector 2 | 194 | 750 | 29
Pipeline including CS | TRA-A-950 | Guitiriz - Lugo - Zamora pipeline | Reganosa | Advanced | Lugo-Zamora | 268 | 750 | 0
Pipeline including CS | TRA-A-950 | Guitiriz - Lugo - Zamora pipeline | Reganosa | Advanced | Guitiriz-Lugo | 50 | 750 | 0
Pipeline including CS | TRA-A-951 | Embedding CS Folmhusen in H-Gas | Gasunie Deutschland Transport Services GmbH | Advanced
Pipeline including CS | TRA-A-967 | Nea-Messimvria to Evzoni/Gevgelija pipeline (IGNM) | DESFA S.A. | Advanced | Nea-Messimvria to Pontoiraklia/Stojakovo | 50 | 700
Pipeline including CS | TRA-A-980 | Interconnection North Macedonia-Greece (North Macedonian part) | MER JSC Skopje | Advanced | Negotino-Gevgelija | 68 | 700 | 0
Pipeline including CS | TRA-A-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | GAZ-SYSTEM S.A. | Advanced | CS Gustorzyn |  |  | 15
Pipeline including CS | TRA-A-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | GAZ-SYSTEM S.A. | Advanced | CS Goleniów |  |  | 12
Pipeline including CS | TRA-A-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | GAZ-SYSTEM S.A. | Advanced | CS Odolanów |  |  | 14
Pipeline including CS | TRA-A-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | GAZ-SYSTEM S.A. | Advanced | Goleniów – Lwówek pipeline | 191 | 1000
Pipeline including CS | TRA-A-1199 | LNG Terminal Brunsbuettel - Grid Integration | Gasunie Deutschland Transport Service GmbH | Advanced | Brunsbuettel-Hetlingen | 57 | 800
Pipeline including CS | TRA-A-1268 | Romania-Serbia Interconnection | SNTGN Tranzgaz SA | Advanced | PETROVASELO-COMLOȘU MARE | 85 | 600
Pipeline including CS | TRA-A-1303 | IAEF - Vlora ccgt | Albgaz Sha | Advanced | IAEF - Vlora CCGT | 40 | 400
Pipeline including CS | TRA-A-1322 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase II | SNTGN Transgaz SA | Advanced | Recaș - Horia | 50 | 800 | 14
Pipeline including CS | TRA-N-7 | Development for new import from the South (Adriatica Line) | Snam Rete Gas S.p.A. | Less-Advanced | Adriatica Line | 430 | 1200 | 33
Pipeline including CS | TRA-N-8 | Import developments from North-East | Snam Rete Gas S.p.A. | Less-Advanced | Section 1 | 15 | 1050 | 0
Pipeline including CS | TRA-N-8 | Import developments from North-East | Snam Rete Gas S.p.A. | Less-Advanced | Section 3 | 0 | 0 | 75
Pipeline including CS | TRA-N-8 | Import developments from North-East | Snam Rete Gas S.p.A. | Less-Advanced | Section 2 | 119 | 1400 | 0
Pipeline including CS | TRA-N-9 | Additional Southern developments | Snam Rete Gas S.p.A. | Less-Advanced | Section 2 | 115 | 1050 | 0
Pipeline including CS | TRA-N-9 | Additional Southern developments | Snam Rete Gas S.p.A. | Less-Advanced | Section 4 | 0 | 0 | 60
Pipeline including CS | TRA-N-9 | Additional Southern developments | Snam Rete Gas S.p.A. | Less-Advanced | Section 3 | 590 | 1200 | 0
Pipeline including CS | TRA-N-9 | Additional Southern developments | Snam Rete Gas S.p.A. | Less-Advanced | Section 1 | 255 | 800 | 0
Pipeline including CS | TRA-N-14 | Komotini-Thesprotia pipeline | DESFA S.A. | Less-Advanced | Komotini-Thesprotia | 620 | 1067 | 126
Pipeline including CS | TRA-N-27 | Physical reverse flow from NI to GB and IE via SNIP pipeline | Premier Transmission Limited | Less-Advanced | SNIP-Scotland to Northern Ireland |  | 600 | 10
Pipeline including CS | TRA-N-53 | White Stream | White Stream Ltd | Less-Advanced | Vale to Supsa | 135 | 1039
Pipeline including CS | TRA-N-53 | White Stream | White Stream Ltd | Less-Advanced | Supsa to Constanta | 1115 | 813 | 375
Pipeline including CS | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd | Less-Advanced | Slobodnica - Bosanski Brod | 6 | 700
Pipeline including CS | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd | Less-Advanced | Kozarac - Sisak | 20 | 800
Pipeline including CS | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd | Less-Advanced | Bosiljevo - Sisak | 102 | 800
Pipeline including CS | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd | Less-Advanced | Zlobin - Bosiljevo | 58 | 800
Pipeline including CS | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | Plinovodi d.o.o. | Less-Advanced | CS Ajdovščina, 1st phase of upgrade |  |  | 5
Pipeline including CS | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade | Plinovodi d.o.o. | Less-Advanced | CS Kidričevo, 2nd phase of upgrade |  |  | 30
Pipeline including CS | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Plinovodi d.o.o. | Less-Advanced | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | 12 | 500
Pipeline including CS | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. | Less-Advanced | R15/1 Pince - Lendava - Kidričevo | 73 | 500 | 6
Pipeline including CS | TRA-N-128 | Compressor Station Kipi | DESFA S.A. | Less-Advanced | Kipi | 0 | 0 | 9
Pipeline including CS | TRA-N-137 | Balkan Gas Hub - Interconnection Bulgaria - Serbia | Bulgartransgaz EAD | Less-Advanced | Bulgarian territory | 62 | 700
Pipeline including CS | TRA-N-137 | Balkan Gas Hub - Interconnection Bulgaria - Serbia | Bulgartransgaz EAD | Less-Advanced | Serbian territory | 108 | 700
Pipeline including CS | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagas Transporte S.A.U. | Less-Advanced | Zamora - Portuguese Border | 86 | 700
Pipeline including CS | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagas Transporte S.A.U. | Less-Advanced | CS Zamora |  |  | 4
Pipeline including CS | TRA-N-192 | Entry capacity expansion GATE terminal | Gasunie Transport Services B.V. | Less-Advanced | Maasvlakte - Wijngaarden | 25 | 1200
Pipeline including CS | TRA-N-224 | Gaspipeline Brod - Zenica | BH-Gas d.o.o. | Less-Advanced | Brod-Zenica | 140 | 500 | 0
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. | Less-Advanced | Rozwadów-Końskowola-Wronów pipeline | 103 | 1000
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. | Less-Advanced | Hermanowice-Jarosław pipeline | 39 | 1000
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. | Less-Advanced | Gustorzyn-Wronów pipeline | 316 | 1000
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. | Less-Advanced | Płońsk-Uniszki Zawadzkie pipeline | 72 | 1000
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. | Less-Advanced | Jarosław - Rozwadów pipeline | 60 | 1000
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. | Less-Advanced | Rembelszczyzna-Wronów pipeline | 135 | 1000
Pipeline including CS | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | GRTgaz | Less-Advanced | Artère du Perche | 63 | 900
Pipeline including CS | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | GRTgaz | Less-Advanced | Artère du Maine | 200 | 1050
Pipeline including CS | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | GRTgaz | Less-Advanced | Auvers-le-Hamon CS |  |  | 0
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | Less-Advanced | Eridan | 220 | 1200
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | Less-Advanced | St-Martin de Crau CS |  |  | 30
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | Less-Advanced | Arc Lyonnais | 150 | 1200
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | Less-Advanced | Palleau CS |  |  | 50
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | Less-Advanced | St-Avit CS |  |  | 15
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | Less-Advanced | Perche | 63 | 900
Pipeline including CS | TRA-N-299 | M3/1 Šempeter - Vodice | Plinovodi d.o.o. | Less-Advanced | M3/1a Šempeter - Ajdovščina | 30 | 800
Pipeline including CS | TRA-N-299 | M3/1 Šempeter - Vodice | Plinovodi d.o.o. | Less-Advanced | M3/1c Kalce - Vodice | 47 | 800
Pipeline including CS | TRA-N-299 | M3/1 Šempeter - Vodice | Plinovodi d.o.o. | Less-Advanced | M3/1b Ajdovščina - Kalce | 24 | 800
Pipeline including CS | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd | Less-Advanced | Rakovica-Bihać | 10 | 500
Pipeline including CS | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd | Less-Advanced | Lička Jesenica-Rakovica | 20 | 500
Pipeline including CS | TRA-N-325 | Slovenian-Hungarian interconnector | FGSZ Ltd. | Less-Advanced | Nagykanizsa-Tornyiszentmiklós | 41 | 600
Pipeline including CS | TRA-N-325 | Slovenian-Hungarian interconnector | FGSZ Ltd. | Less-Advanced | Nagykanizsa-Kozármisleny | 150 | 600 | 12
Pipeline including CS | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Plinacro Ltd | Less-Advanced | Umag - Plovanija (HR)- Koper (SI) | 8 | 300
Pipeline including CS | TRA-N-354 | Interconnection with Slovenia | Snam Rete Gas S.p.A. | Less-Advanced | all the project | 6 | 250 | 0
Pipeline including CS | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | GAS CONNECT AUSTRIA GmbH | Less-Advanced | Loop Murfeld - Cersak | 2 | 500
Pipeline including CS | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | GAS CONNECT AUSTRIA GmbH | Less-Advanced | Loop SOL pipeline | 26 | 600
Pipeline including CS | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Plinovodi d.o.o. | Less-Advanced | Upgrade of Murfeld/Ceršak interconnection | 0 | 800
Pipeline including CS | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Plinovodi d.o.o. | Less-Advanced | Upgrade of Rogatec interconnection | 4 | 800
Pipeline including CS | TRA-N-402 | TENP Security of Supply | Fluxys TENP GmbH & Open Grid Europe GmbH | Less-Advanced | Pipeline Mittelbrunn-Schwanheim | 38 | 1000
Pipeline including CS | TRA-N-402 | TENP Security of Supply | Fluxys TENP GmbH & Open Grid Europe GmbH | Less-Advanced | Connections TENP I - TENP II |  | 600
Pipeline including CS | TRA-N-402 | TENP Security of Supply | Fluxys TENP GmbH & Open Grid Europe GmbH | Less-Advanced | Pipeline Hügelheim-Tannenkirch | 16 | 900
Pipeline including CS | TRA-N-423 | GCA Mosonmagyaróvár | GAS CONNECT AUSTRIA GmbH | Less-Advanced | HAG MS, Baumgarten
Pipeline including CS | TRA-N-439 | Stazione di Spinta "San Marco" | S.G.I. S.p.A. | Less-Advanced | Compression Station |  |  | 3
Pipeline including CS | TRA-N-502 | Interconnector Romania - Ukraine | Joint-Stock Company | Less-Advanced | Ukrainian part | 30 | 700
Pipeline including CS | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | FGSZ Ltd. | Less-Advanced | Hungarian section | 92 | 800
Pipeline including CS | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | FGSZ Ltd. | Less-Advanced | Slovak | 18 | 800
Pipeline including CS | TRA-N-596 | Interconnection between the RO and the UA gas transmission systems | SNTGN Transgaz SA | Less-Advanced | Gheraesti - Siret | 146 | 700 | 10
Pipeline including CS | TRA-N-598 | NTS developments in North-Vest Romania | SNTGN Transgaz SA | Less-Advanced | Horia-Bors | 112 | 700
Pipeline including CS | TRA-N-598 | NTS developments in North-Vest Romania | SNTGN Transgaz SA | Less-Advanced | Huedin-Alesd | 73 | 500 | 10
Pipeline including CS | TRA-N-598 | NTS developments in North-Vest Romania | SNTGN Transgaz SA | Less-Advanced | Bors-Abramut | 28 | 700
Pipeline including CS | TRA-N-598 | NTS developments in North-Vest Romania | SNTGN Transgaz SA | Less-Advanced | Abramut-Mediesu Aurit | 134 | 700
Pipeline including CS | TRA-N-598 | NTS developments in North-Vest Romania | SNTGN Transgaz SA | Less-Advanced | Sarmasel-Mediesu Aurit | 171 | 400
Pipeline including CS | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | FGSZ Ltd. | Less-Advanced | Slovak section | 18 | 800
Pipeline including CS | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | FGSZ Ltd. | Less-Advanced | Hungarian section | 92 | 800
Pipeline including CS | TRA-N-809 | Reallocation H-Gas towards NL: Bunde/Oude to Zone Oude Statenzijl H | Gasunie Deutschland Transport Services GmbH | Less-Advanced
Pipeline including CS | TRA-N-810 | TAP Expansion | Trans Adriatic Pipeline AG | Less-Advanced | TAP Expansion |  |  | 275
Pipeline including CS | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | BH-GAS d.o.o. | Less-Advanced | Posusje - Novi Travnik with branch to Mostar | 162 | 500 | 0
Pipeline including CS | TRA-N-873 | Additional import at Oude StatenZijl area | Gasunie Transport Services B.V. | Less-Advanced
Pipeline including CS | TRA-N-882 | Transferring L-gas infrastructure to H-gas | Gasunie Transport Services B.V. | Less-Advanced
Pipeline including CS | TRA-N-910 | West Interconnection BiH/CRO | BH-Gas d.o.o. | Less-Advanced | Trzac - Bosanska Krupa | 35 | 500 | 0
Pipeline including CS | TRA-N-955 | GUD: Complete conversion to H-gas | Gasunie Deutschland Transport Services GmbH | Less-Advanced
Pipeline including CS | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | SNTGN Transgaz SA | Less-Advanced | Onesti - Nadlac | 843 | 813 | 82
Pipeline including CS | TRA-N-971 | Compressor station at Nea Messimvria | DESFA S.A. | Less-Advanced | Nea Messimvria to TAP |  |  | 27
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Plinacro Ltd | Less-Advanced | Compressor station 2 | 0 | 0 | 10
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Plinacro Ltd | Less-Advanced | Compressor station 3 | 0 | 0 | 10
Pipeline including CS | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Plinacro Ltd | Less-Advanced | Kozarac-Slobodnica | 128 | 800
Pipeline including CS | TRA-N-1063 | Export to Malta | Snam Rete Gas S.p.A. | Less-Advanced | all the project
Pipeline including CS | TRA-N-1064 | Moffat Physical Reverse Flow | National Grid Gas plc | Less-Advanced
Pipeline including CS | TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | DESFA S.A. | Less-Advanced
Pipeline including CS | TRA-N-1091 | Metering and Regulating station at Megalopoli | DESFA S.A. | Less-Advanced
Pipeline including CS | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | DESFA S.A. | Less-Advanced
Pipeline including CS | TRA-N-1129 | Compressor Station Kipi Increment | DESFA S.A. | Less-Advanced | 1 |  |  | 20
Pipeline including CS | TRA-N-1138 | South Caucasus Pipeline Future Expansion (SCPFX) | SOCAR Midstream Operations LLC | Less-Advanced | South Caucasus Pipeline Future Expansion | 93 | 1219 | 80
Pipeline including CS | TRA-N-1181 | Connecting pipe to LNG terminal in Latvia | JSC "Conexus Baltic Grid" | Less-Advanced
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 1 | 17 | 250
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 3 | 54 | 400
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 1 | 32 | 650
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 2 | 75 | 650
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 2 | 29 | 150
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 5 | 26 | 150
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 7 | 26 | 150
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 5 | 8 | 250
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 4 | 7 | 200
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 6 | 17 | 200
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 1 | 43 | 400
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 4 | 1 | 150
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 7 | 105 | 400
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 3 | 50 | 650
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 4 | 77 | 650
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | phase 6 | 6 | 150
Pipeline including CS | TRA-N-1195 | Matagiola - Massafra pipeline | Snam Rete Gas S.p.A. | Less-Advanced | Matagiola - Massafra | 80 | 1400
Pipeline including CS | TRA-N-1202 | GCP GAZ-SYSTEM/ONTRAS - incremental capacity project | GAZ-SYSTEM S.A. | Less-Advanced | Kiełczów node - modernisation
Pipeline including CS | TRA-N-1202 | GCP GAZ-SYSTEM/ONTRAS - incremental capacity project | GAZ-SYSTEM S.A. | Less-Advanced | Lasow metering station - modernisation
Pipeline including CS | TRA-N-1227 | Gorizia plant upgrade | Snam Rete Gas S.p.A. | Less-Advanced
Pipeline including CS | TRA-N-1235 | Firm transmission capacity increase at the IP Veľké Zlievce | eustream,a.s. | Less-Advanced | Firm capacity increase at the IP Veľké Zlievce |  |  | 10
Pipeline including CS | TRA-N-1246 | Greece - Italy interconnection | Snam Rete Gas S.p.A. | Less-Advanced | All the project
Pipeline including CS | TRA-N-1265 | Biomethane productions interconnection | Snam Rete Gas S.p.A. | Less-Advanced | All the project | 21 | 100
Pipeline including CS | TRA-N-1278 | Compressor station at Ambelia | DESFA S.A. | Less-Advanced | Ambelia |  |  | 20

## LNG Terminals
LNG Terminals
Type | Code | Project Name | LNG Facility | Promoter | Maturity Status | Project Phase | Reloading Ability | Project Yearly Volume (bcm/y) | Project Ship Size (m3 LNG) | Project Storage Capacity (m3 LNG)
LNG Terminal | LNG-F-82 | LNG terminal Krk | The import terminal for the liquefied natural gas(LNG) on the Island of Krk | LNG Hrvatska d.o.o. | FID | 1st phase | Yes | 2.6 | 140000 | 140000
LNG Terminal | LNG-F-82 | LNG terminal Krk | The import terminal for the liquefied natural gas(LNG) on the Island of Krk | LNG Hrvatska d.o.o. | FID | 2nd phase | Yes | 4.4 | 120000 | 160000
LNG Terminal | LNG-F-163 | Gran Canaria LNG Terminal | Gran Canaria | Gascan | FID | Gran Canaria | Yes | 1.3 | 140000 | 150000
LNG Terminal | LNG-F-178 | Musel LNG terminal | Musel | Enagas Transporte S.A.U. | FID | El Musel | Yes | 0 | 266000 | 300000
LNG Terminal | LNG-F-183 | Tenerife LNG Terminal | Tenerife LNG Terminal | Gascan | FID | Tenerife LNG | Yes | 1.3 | 140000 | 150000
LNG Terminal | LNG-F-272 | Upgrade of LNG terminal in Świnoujście | LNG terminal in Świnoujście | GAZ-SYSTEM S.A. | FID | Extension | Yes | 2.5 | 90000 | 180000
LNG Terminal | LNG-F-824 | LNG Terminal in Klaipeda | FSRU Independence | AB Klaipėdos Nafta | FID | Purchase | Yes | 3.7 | 160000 | 170000
LNG Terminal | LNG-A-30 | Shannon LNG Terminal and Connecting Pipeline | Shannon LNG Terminal and connecting pipeline | Shannon LNG Ltd | Advanced | Initial |  | 2.8 | 265000 | 200000
LNG Terminal | LNG-A-30 | Shannon LNG Terminal and Connecting Pipeline | Shannon LNG Terminal and connecting pipeline | Shannon LNG Ltd | Advanced | Phase 2 |  | 2.1 | 0 | 0
LNG Terminal | LNG-A-30 | Shannon LNG Terminal and Connecting Pipeline | Shannon LNG Terminal and connecting pipeline | Shannon LNG Ltd | Advanced | Phase 3 |  | 3.3 | 0 | 0
LNG Terminal | LNG-A-32 | Project GO4LNG LNG terminal Gothenburg | Gothenburg LNG terminal | Swedegas AB | Advanced | Development | Yes | 9999 | 75000 | 25000
LNG Terminal | LNG-A-50 | Gate terminal phase 3 | Gate terminal Rotterdam | Gate | Advanced
LNG Terminal | LNG-A-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | LNG terminal in northern Greece / Alexandroupolis | Gastrade S.A. | Advanced | LNG terminal | Yes | 8.3 | 170000 | 170000
LNG Terminal | LNG-A-79 | Paldiski LNG Terminal | Paldiski LNG terminal | Balti Gaas plc | Advanced | Paldiski LNG Terminal | Yes | 2 | 160000 | 160000
LNG Terminal | LNG-A-295 | Mugardos LNG Terminal: Send-out Increase | Mugardos LNG Terminal | Reganosa | Advanced | Send-out | Yes | 3.6 | 0 | 0
LNG Terminal | LNG-A-296 | Mugardos LNG Terminal: 2nd Jetty | Mugardos LNG Terminal | Reganosa | Advanced | 2nd jetty | Yes | 0 | 266000 | 0
LNG Terminal | LNG-A-962 | Tallinn LNG | Tallinn LNG | Liwathon E.O.S. AS / Port of Tallinn AS | Advanced | Tallinn LNG | Yes | 4 | 160000 | 160000
LNG Terminal | LNG-A-1146 | Cyprus Gas2EU | CyprusGas2EU | Ministry of Energy, Commerce and Industry (MECI) | Advanced
LNG Terminal | LNG-A-1198 | LNG Terminal Brunsbuettel | LNG Terminal Brunsbüttel (German LNG) | GermanLNG Terminal GmbH | Advanced | One |  | 8 | 267000 | 240000
LNG Terminal | LNG-N-225 | Montoir LNG Terminal Expansion | Montoir LNG Terminal | Elengy | Less-Advanced | small scale | Yes | 0 | 0 | 0
LNG Terminal | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | Fos Cavaou LNG Terminal | Fosmax LNG | Less-Advanced | small scale | Yes | 0 | 0 | 0
LNG Terminal | LNG-N-297 | Mugardos LNG Terminal: Storage Extension | Mugardos LNG Terminal | Reganosa | Less-Advanced | Storage | Yes | 0 | 0 | 190000
LNG Terminal | LNG-N-304 | Italy-Sardinia Virtual Pipeline | Panigaglia LNG plant | Snam S.p.A. | Less-Advanced | Virtual pipe | Yes | 0 | 0 | 0
LNG Terminal | LNG-N-912 | Skulte LNG | FRU | AS Skulte LNG Terminal | Less-Advanced | Pre feed | Yes | 1.5 | 170000 | 700000
LNG Terminal | LNG-N-947 | FSRU Polish Baltic Sea Coast | FSRU Polish Baltic Sea Coast | GAZ-SYSTEM S.A. | Less-Advanced | FSRU project | Yes | 4.5 | 170000 | 170000

## Underground Storages
Underground Storages
Type | Code | Project Name | UGS Facility | Type | Promoter | Maturity Status | Project Phase | WGV (mcm) | Withdrawal Capacity (mcm/d) | Injection Capacity (mcm/d)
Storage Facility | UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | Fiume Treste - Minerbio - Ripalta - Sabbioncello - Sergnano - Alfonsine | Depleted Field | STOGIT | FID | System Enhancements - Stogit - on-shore gas fields | 588 | 2 | 9.5
Storage Facility | UGS-F-311 | Bilciuresti daily withdrawal capacity increase | Bilciuresti | Depleted Field | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | FID | Bilciuresti daily withdrawal capacity increase | 0 | 5 | 0
Storage Facility | UGS-F-374 | Enhancement of Incukalns UGS | Incukalns Underground Gas Storage | Aquifer | JSC "Conexus Baltic Grid" | FID | Inčukalns UGS | 0 | 20 | 40
Storage Facility | UGS-A-138 | Balkan Gas Hub - UGS Chiren Expansion | UGS Chiren | Depleted Field | Bulgartransgaz EAD | Advanced | UGS Chiren Expansion | 450 | 4.6 | 4.8
Storage Facility | UGS-A-233 | Depomures | Targu Mures | Depleted Field | Engie Romania SA | Advanced | Phase 1 | 100 | 1.8 | 1.8
Storage Facility | UGS-A-233 | Depomures | Targu Mures | Depleted Field | Engie Romania SA | Advanced | Phase 2 | 200 | 1.5 | 1.5
Storage Facility | UGS-A-294 | Islandmagee Gas Storage Facility | Islandmagee Gas Storage Facility | Salt Cavern | Islandmagee Storage Limited | Advanced | Project Construction | 420 | 22 | 12
Storage Facility | UGS-A-356 | Underground Gas Storage Velke Kapusany | Underground Gas Storage Velke Kapusany | Depleted Field | NAFTA a.s. (joint stock company) | Advanced | Commissioning | 340 | 3.75 | 3.75
Storage Facility | UGS-N-347 | Gas storage facility Grubisno Polje | Grubisno Polje | Depleted Field | Podzemno skladiste plina Ltd | Less-Advanced | Phase1 | 60 | 2.4 | 1.68
Storage Facility | UGS-N-371 | Sarmasel undeground gas storage in Romania | UGS SARMASEL | Depleted Field | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | Sarmasel underground gas storage in Romania | 650 | 3.21 | 3.96
Storage Facility | UGS-N-385 | South Kavala Underground Gas Storage facility | South Kavala | Depleted Field | Hellenic Republic Asset Development Fund | Less-Advanced | Single-phase Project | 720 | 4 | 5
Storage Facility | UGS-N-398 | Ghercesti underground gas storage in Romania | Ghercesti | Depleted Field | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | Ghercesti underground gas storage in Romania | 450 | 3 | 0
Storage Facility | UGS-N-399 | Falticeni UGS | Falticeni UGS | Depleted Field | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | Falticeni new UGS | 200 | 2 | 1.4
Storage Facility | UGS-N-914 | UGS Damasławek | UGS Damasławek | Salt Cavern | GAZ-SYSTEM S.A. | Less-Advanced | UGS Damaslawek | 800 | 8.9 | 17.7

## ETR
ETR
Type | Code | Project Name | Promoter | Maturity Status | Project Type | Other Project Type | Project Description | Section Name | Technical Parameters
Energy Transition Related Project | ETR-F-516 | CNG and L-CNG stations | Snam4mobility | FID | Other Type | CNG - liquefied CNG stations for automotive | The project consist in the development of about 110 CNG and L-CNG stations along Italy in order to facilitate the energy transition in the transport sector | All the project | The 110 CNG and L-CNG stations will be able to deliver up to 667,2 GWh/y
Energy Transition Related Project | ETR-F-523 | Biomethane plants development | Snam4mobility | FID | Biomethane Production |  | The project consist in the realization of 5 biomethane production plants all over Italy and it us an important contribution to energy transition of the country | All the project | The project consists in the realization of 5 plant with a total production of abount 60 kScm/day
Energy Transition Related Project | ETR-F-541 | CORE LNGas hive and LNGHIVE2 Infrastructure and logistic solutions | Enagas Transporte S.A.U. | FID | Other Type | CORE LNGas hive contributes to the decarbonisation of the European corridors of the Mediterranean and the Atlantic and is a step in the career of reduced emissions, the promotion of clean energy for transportation driven by the European Union | CORE LNGas hive project is part of institutional strategy to deploy LNG supply fuelling in ports in the Iberian Peninsula and develop the associated market, is a step in the career of reduced emissions. Enagás is performing the following activities: Coordination; adaptation of jetties in existing plants in the Iberian Peninsula, these adaptations are made to be able to supply LNG small scales services and supply LNG as marine fuel to ships. These modifications are part of the project CORE LNGas hive and LNGHIVE2 Infrastructure and logistic solutions (hivelogs), which aims to make the necessary adaptations to cover the early stages of pit aims at retrofitting an existing penetration of LNG as propulsion and auxiliary fuel for vessels. Also they englobes different works to improve the air quality and reduce contamination, especially in port domain, as using LNG as fuel in port equipment (crane, tugboat, vessel’s energy supply in port) and the modification of existing barge to supply LNG
Energy Transition Related Project | ETR-F-546 | Jupiter 1000: first industrial demonstrator of Power to Gas in France | GRTgaz, Terega | FID | Power-to-Gas |  | The Jupiter 1000 project is the first industrial demonstrator of Power to Gas with a power rating of 1 MWe for electrolysis and a methanation process with carbon capture. Green hydrogen will be produced using two electrolysers involving different technologies, from 100% renewable energy. The installation will be based on an innovative methanation technology and CO2 will be captured on a nearby industrial site. In the light of the performance levels shown by the demonstrator, GRTgaz and its partners will work on future technical and economic standards of a full-sized installation of this type. Over the longer term, the idea is to launch the Power to Gas activity in France. More than 15 TWh of gas could be produced each year using the Power to Gas system by 2050. | Jupiter 1000 | a power rating of 1 MWe for electrolysis and a methanation process with carbon capture. Green hydrogen will be produced using two electrolysers involving different technologies, from 100% renewable energy.
Energy Transition Related Project | ETR-F-587 | West Grid Synergy | GRTgaz | FID | Reverse flow DSO-TSO |  | The biomethane production is significantly increasing since 2016. In France, hundreds of biomethane upcoming plant projects are registered to inject in the distribution and transmission gas system. However, in many cases, the injection capacity of the local distribution system is not enough to integrate such production. Furthermore, decentralized production has significant impacts on the gas infrastructure operation (monitoring, maintenance, coordination with the stakeholders …). In order to adapt the distribution and transmission system to those structural changes, GRTgaz has launched a demonstrator and a major industrial program. 3 gas utilities (GRTgaz, GRDF and SOREGIES) investigate this issue together with public actors (3 Departmental Offices for Energy : SIéML, SYDEV and Morbihan Energies) through an operational demonstrator named West Grid Synergy and located in the West of France. This demonstrator consists of territories with important biomethane production projects and very | instrumentation and data collection | Around 20 sensors implemented on the 3 experimental territories
Energy Transition Related Project | ETR-F-587 | West Grid Synergy | GRTgaz | FID | Reverse flow DSO-TSO |  | The biomethane production is significantly increasing since 2016. In France, hundreds of biomethane upcoming plant projects are registered to inject in the distribution and transmission gas system. However, in many cases, the injection capacity of the local distribution system is not enough to integrate such production. Furthermore, decentralized production has significant impacts on the gas infrastructure operation (monitoring, maintenance, coordination with the stakeholders …). In order to adapt the distribution and transmission system to those structural changes, GRTgaz has launched a demonstrator and a major industrial program. 3 gas utilities (GRTgaz, GRDF and SOREGIES) investigate this issue together with public actors (3 Departmental Offices for Energy : SIéML, SYDEV and Morbihan Energies) through an operational demonstrator named West Grid Synergy and located in the West of France. This demonstrator consists of territories with important biomethane production projects and very | Infrastructures implementation - Pouzauges | Installation of a reverse flow unit with a 5000 Nm3/h maximum flow
Energy Transition Related Project | ETR-F-587 | West Grid Synergy | GRTgaz | FID | Reverse flow DSO-TSO |  | The biomethane production is significantly increasing since 2016. In France, hundreds of biomethane upcoming plant projects are registered to inject in the distribution and transmission gas system. However, in many cases, the injection capacity of the local distribution system is not enough to integrate such production. Furthermore, decentralized production has significant impacts on the gas infrastructure operation (monitoring, maintenance, coordination with the stakeholders …). In order to adapt the distribution and transmission system to those structural changes, GRTgaz has launched a demonstrator and a major industrial program. 3 gas utilities (GRTgaz, GRDF and SOREGIES) investigate this issue together with public actors (3 Departmental Offices for Energy : SIéML, SYDEV and Morbihan Energies) through an operational demonstrator named West Grid Synergy and located in the West of France. This demonstrator consists of territories with important biomethane production projects and very | Infrastructures implementation - Pontivy | Installation of a reverse flow unit with a 5000 Nm3/h maximum flow
Energy Transition Related Project | ETR-F-587 | West Grid Synergy | GRTgaz | FID | Reverse flow DSO-TSO |  | The biomethane production is significantly increasing since 2016. In France, hundreds of biomethane upcoming plant projects are registered to inject in the distribution and transmission gas system. However, in many cases, the injection capacity of the local distribution system is not enough to integrate such production. Furthermore, decentralized production has significant impacts on the gas infrastructure operation (monitoring, maintenance, coordination with the stakeholders …). In order to adapt the distribution and transmission system to those structural changes, GRTgaz has launched a demonstrator and a major industrial program. 3 gas utilities (GRTgaz, GRDF and SOREGIES) investigate this issue together with public actors (3 Departmental Offices for Energy : SIéML, SYDEV and Morbihan Energies) through an operational demonstrator named West Grid Synergy and located in the West of France. This demonstrator consists of territories with important biomethane production projects and very | Infrastructures implementation - Mauges | Experimentation of dynamic and remote control of the gas pressure at the transmission/distribution interface from 5 to 10 bar at the distribution side
Energy Transition Related Project | ETR-F-587 | West Grid Synergy | GRTgaz | FID | Reverse flow DSO-TSO |  | The biomethane production is significantly increasing since 2016. In France, hundreds of biomethane upcoming plant projects are registered to inject in the distribution and transmission gas system. However, in many cases, the injection capacity of the local distribution system is not enough to integrate such production. Furthermore, decentralized production has significant impacts on the gas infrastructure operation (monitoring, maintenance, coordination with the stakeholders …). In order to adapt the distribution and transmission system to those structural changes, GRTgaz has launched a demonstrator and a major industrial program. 3 gas utilities (GRTgaz, GRDF and SOREGIES) investigate this issue together with public actors (3 Departmental Offices for Energy : SIéML, SYDEV and Morbihan Energies) through an operational demonstrator named West Grid Synergy and located in the West of France. This demonstrator consists of territories with important biomethane production projects and very | Global system optimisation | 3 digital grid modeling 4 simulations to identify the possible adjustment range of the infrastructures, the priority management rules to maximize injection capacity, to calculate the proper gross calorific value at any point of the distribution network and Impact assessment of pressure adjustment on PE-pipe conditions
Energy Transition Related Project | ETR-F-599 | Sector coupling: hybrid compressor station | Snam Rete Gas S.p.A. | FID | Other Type | Sector coupling facilities | The project consists of the installation of two new electro compressor in Malborghetto compressor station for a total of 24 MW in partial substitution of gas compressor power (particularly, the elder turbo compressors). The project makes possible the coupling of electricity and gas sectors activating flexibility resources at the benefit of the overall energy system. | All the project | The project consists of the installation of two new electro compressor in Malborghetto compressor station for a total of 24 MW in partial substitution of gas compressor power
Energy Transition Related Project | ETR-F-632 | Railway project roadmap. Transformation to LNG | Enagas Transporte S.A.U. | FID | Other Type | Railway transport | Automotive Pilot of passengers consists of the development of the necessary studies to develop the engineering of the first commercial line of passengers with LNG in the vicinities of Asturias and the tests of the same one for its extrapolation to commercial lines, 4 units Project raiLNG is developed by the consortium (RENFE, Enagás, Naturgy and Bureau Veritas) consists of the transformation of the S1600 locomotive to generate the hybrid Diesel/GNL tractor composition. The resulting composition will establish a comparison of performance between the two in the same service conditions Project to transform locomotives from manoeuvres to LNG that currently use diesel fuel in port areas, 6 S310 units. LNGhive2: transformation of a heavy haul locomotive in the Huelva-Sevilla corridor. The integral project will include a gas station Project of R+D+ì to promote disruptive technologies and alternatives to the traditional "motor-fuel" binomial that cover the shortcomings of the current platform
Energy Transition Related Project | ETR-F-743 | Impulse 2025 | Teréga | FID | Other Type | Impulse 2025 is a “smart multi-energies system” aiming at interconnecting all grids (gas, power, heat) to create synergies and improve energy efficiency. | Deployment of a “smart multi-energies system” aiming at interconnecting all grids (gas, power, heat) to create synergies and improve energy efficiency. the IMPULSE 2025 project aims at implementing a « smart multi-energies system » to interconnect different networks (including gas and power) and favor their mutualization to make the most of the possible synergies (reducing therefore rhe GHGe and the overall energy consumption). It includes studies and the building of a pilot demonstrator. 2 phases: P1 (2019-2021): development of an modelling and optimization tool to identify the optimal configuration of a smart multi-energies system. Many technological components will be studied and meaningful or priority design studies will be conducted; Phase 2 (2021-2025): study of the operational feasibility to confirm estimated gains. Several partners are associated. This phase aims at improving the demonstrator through the implementation of the technological components identified in phase 1 | Impulse - Pilot Phase | building an optimization and modelling tool relying on different technologies (P2G, P2H) and designs
Energy Transition Related Project | ETR-F-743 | Impulse 2025 | Teréga | FID | Other Type | Impulse 2025 is a “smart multi-energies system” aiming at interconnecting all grids (gas, power, heat) to create synergies and improve energy efficiency. | Deployment of a “smart multi-energies system” aiming at interconnecting all grids (gas, power, heat) to create synergies and improve energy efficiency. the IMPULSE 2025 project aims at implementing a « smart multi-energies system » to interconnect different networks (including gas and power) and favor their mutualization to make the most of the possible synergies (reducing therefore rhe GHGe and the overall energy consumption). It includes studies and the building of a pilot demonstrator. 2 phases: P1 (2019-2021): development of an modelling and optimization tool to identify the optimal configuration of a smart multi-energies system. Many technological components will be studied and meaningful or priority design studies will be conducted; Phase 2 (2021-2025): study of the operational feasibility to confirm estimated gains. Several partners are associated. This phase aims at improving the demonstrator through the implementation of the technological components identified in phase 1 | Impulse - Operational phase | Building and connecting a facility to demonstrate the operational and industrial feasibility of such projects
Energy Transition Related Project | ETR-A-64 | Biomethane reverse flow Denmark | Energinet | Advanced | Reverse flow DSO-TSO |  | The objective of this reverse flow project from DSO grid to TSO grid, is to ensure the integration of excess biomethane in the distribution grid into the transmission grid. The project is a virtual aggregation of three physical projects establishing reverse flows from DSO grid to TSO grid. In Total 746 MWh/h biomethane production capacity is connected to the DSO grid at low pres-sure level (4 bar). When supply exceeds demand, the DSO uses intermediate pressure compres-sors to lift the gas to a higher-pressure distribution grid (from 4 bar to 20/40 bar). When supply of biomethane in the high-pressure distribution grid exceeds demand, high-pressure compres-sors lift the gas to the TSO grid 20/40 bar to 80 bar). step 1: Biomethane -> low pressure distribution grid at 4 bar, supplying local demand step 2: When local demand in the 4 bar distribution grid is saturated. DSO recompress gas from from 4 to 20 or 40 bar. step 3: When local demand in the 20-40 bar distribution grid is satura | Reverse flow Denmark | Reverseflow units: 3 Total biomethane production ab plants: 746 MWh/h Biomethane reverse flow (DSO-TSO) Compressor capacity: 294 MWh/h Metering (quality and quantity) and de-odorisation of gas
Energy Transition Related Project | ETR-A-312 | P2G Velke Kapusany | NAFTA a.s. (joint stock company) | Advanced | CCS/CCU |  | Project P2G Velke Kapusany aims to store renewable energy in form of the hydrogen (H2) in the mixture with natural gas using the new Naftas gas storage. The unique structure as well as the location of the UGS with all the planned interconnection will allow to store and distribute H2 for neighbouring countries. That’s capacity will allow to install and use more renewable energy in region without any negative impact to the electrical grid as well as will provide energy safety of supply. The project counts to install the electrolysis units to transform the electricity to gas (H2). Mixing of the natural gas with the renewable hydrogen could be the possibility how to decrease the CO2 emission from the natural gas. | P2G Velke Kapusany | The projects expects to install P2G technology with power about 78 MW. Produced hydrogen will be injected into planned UGS Velke Kapusany at rate about 1,23 GWh/day. Compressor units as well as other infrastructure will be used from the UGS Velke Kapusany. The power of compressor unit should be around 8400 kW.
Energy Transition Related Project | ETR-A-430 | Porthos | N.V. Nederlandse Gasunie | Advanced | CCS/CCU |  | Development of an open CO2 backbone in the Port of Rotterdam with a offshore (permanent) CO2 storage with total storage capacity of ca 37 MT
Energy Transition Related Project | ETR-A-437 | Supercritical water gasification facilities | N.V. Nederlandse Gasunie | Advanced | Biomethane Production |  | Supercritical water gasification (SCWG) is an innovative technology that converts wet biomass (waste) streams such as manure, biowaste and sewage sludge into sustainable energy and reusable raw materials. Supercritical water gasification is a thermo-chemical conversion technology that makes use of the water component in the wet waste streams. Compressing water, containing the biomass, under high temperature, creates the so-called supercritical phase. SCWG is a multi-feedstock technology, in which all kinds of (wet)biomass can be processed. In addition, the gas is produced under high pressure, without additional costs for compression.
Energy Transition Related Project | ETR-A-504 | Sun2Hy | Enagas S.A. | Advanced | Other Type | X Hydrogen Generation and P2G Max 1 MW electrolysis. Expected production of 200 Nm3/h H2 | Photoelectrochemical hydrogen production and hydrogen injection into the gas grid. This project is considering the production of green hydrogen by PEC technologies. The CAPEX considers a minimum of 1 MW of photoelectrochemical electrolysis and its use in industrial and transport applications. The prefeasibility study, that is under definition, consideres this CAPEX and 20 years (considering the scaling up, the production and the real case application/demostration project) | Sun2Hy | X Hydrogen Generation and P2G Max 1 MW electrolysis. Expected production of 200 Nm3/h H2
Energy Transition Related Project | ETR-A-519 | Hub Baleares | Enagas S.A. | Advanced | Power-to-Gas |  | The project will develop a 10 MW plant to develop green hydrogen from renewable electrical energy (photovoltaic plant) and its use in transport sector (initially for captive fleets: buses and vehicles) and injection into the natural gas grid. This project is considering the production of green hydrogen for its use in islands in order to decarbonize mainly transport and tertiary applications. The CAPEX considers a minimum of 10 MW of electrolysis, a high pressure hydrogen injection plant, residential and transport applications. The prefeasibility study, that is under definition, considers this CAPEX and 15 years. | Phase I | P2G and mobility Phase I: up to 5MW Electrolyser. Phase II: Up to 10 MW electrolyser. 15-17 MW FV plant with 10 MW Electrolyser Final use: H2 as fuel for 20 FCEB (Fuel Cell Electric Buses), FCEV (car rental fleets) plus hydrogen injection to gas grid. Expected production of 2.000 Nm3/h H2
Energy Transition Related Project | ETR-N-20 | GNI Renewable Gas Central Grid Injection Project | Gas Networks Ireland | Less-Advanced | Other Type | Renewable Gas Central Grid Injection point. Production of biogas and upgrading to biomethane will be undertaken by 3rd party producers and transported by road to the CGI faility for injection to the transmission network. | Gas Networks Ireland (GNI) has a strategic plan to achieve 20% renewable gas on the network by 2030. To achieve this, GNI is already progressing with the GRAZE Gas project which has been shortlisted for funding under the Irish Government’s Climate Action Fund. This is a pilot project comprising of one Central Grid Injection (CGI) facility (for injection of agri-based renewable gas onto the gas network), a logistics element, two CNG stations and a vehicle fund. The Renewable Gas Central Grid Injection Project will involve the construction of 5 further agri-based CGI facilities. These facilities will provide centralised locations for renewable gas producers from local AD plants (within a 50 km radius) to inject into GNI’s transmission system. This will help enable the rollout of renewable gas on a national basis and contribute significantly to the decarbonisation of Ireland’s agricultural sector as well as the national gas network. | GNI Renewable Gas Central Grid Injection Project | The first CGI facility will be commissioned in 2023, with an initial capacity of 0.5 GWh/d. A total of 5 CGI physical entry points will come on stream with an eventual entry capacity of 7.7 GWh/d by 2028.
Energy Transition Related Project | ETR-N-22 | Ervia Cork CCUS | Ervia (parent company of Gas Networks Ireland) | Less-Advanced | CCS/CCU |  | This project will involve the development of the necessary infrastructure to transport captured CO2 from a CCUS cluster of heavy industry (oil refinery) and two gas fired CCGTs to enable the CO2 to be transported either to local geological store or if unavailable to another store managed by another CCUS project developer. The import infrastructure and geological store will also be made available as a backup storage facility to other CCUS developments to reduce the risk of cross chain default or as a market maker. Cork has unique attributes which combine to provide an opportunity for the first full chain CCUS project within the European Union. The soon to be depleted Kinsale Energy offshore gas field is due to be decommissioned in 2020/2021. This low pressure field on first look by the SEAI and GSI in 2008 looks to be a suitable reservoir for CO2 storage. Further analysis will take place over the coming years to ensure that it is a suitable, secure storage site. | Ervia Cork CCUS | This project will involve dedicated CO2 pipelines which will transport CO2 from 3 sources initially, from the combustion of gas, for the purpose of permanent geological storage of CO2 pursuant to Directive 2009/31/EC. This will include the repurposing of existing onshore /offshore gas pipelines and the construction of new dedicated CO2 pipelines. In order to provide backup storage for other CCUS projects, will involve the facilities for liquefaction, gasification and buffer storage of CO2 at port facilities in order to prepare CO2 for transportation by ship when either importing or exporting CO2. To ensure the safe and secure operation of the CO2 infrastructure a comprehensive utility system in line with existing gas safety frameworks will be installed and operated during the lifetime of this project. This will encompass the pipeline transportation, compression, liquefaction and gasification processes. This project will store first 60MT of CO2 at a rate of 2.5 MT/yr.
Energy Transition Related Project | ETR-N-80 | Power to Gas Production with infrastructure building/enhacement in Latvia | JSC "Conexus Baltic Grid" | Less-Advanced | Power-to-Gas |  | There are plans to develop wind farms in two regions of Latvia called Kurzeme and Zemgale with total expected installed capacity of 567 MW, where 207 MW has already received building permit and 360 MW is in pipeline with the final phase of the Environmental Impact Assessment. These windfarms are expected to generate 800 TWh a year. In order to use excess wind power, Power to Gas technology will be used and generated hydrogen as also potentially synthetic hydrocarbon will be injected into existing gas transmission grid with possible utilization of existing or creation of new aquifier gas storage. The first steps of the demonstration project will be jeasibility study on the best location and technology as well the impact of hydrogen on aquifier storages. Option of production of the synthetic methan capturing CO2 from industrial site also will be considered.
Energy Transition Related Project | ETR-N-125 | Biomethane production with infrastructure building/enhancement in Latvia | JSC "Conexus Baltic Grid" | Less-Advanced | Biomethane Production |  | The total installed electrical capacity of biogas in Latvia is 60.446 MW, which in 2018 produced 347.93 GWh. However, there is no biomethan production in Latvia. Only these biogas plants, which are close to the transmission grid is feasible to upgrade for biomethan production in order to inject biomethan into the transmission grid. 13 existing biogas production facilities for upgrade to biomethan production are chosen in Latvia: 8 in Zemgale region (Druvas unguri, Daile Agro, Bio Ziedi, Zemgaļi, Lielmežotne, Agro Iecava, Egg Energy) and 5 in Vidzeme region (Baltijas Darzeņi, Zaļās zemes enerģija, Vecsiljāņi, Pilslejas, International Investments). The project will start with the feasibility study resulting in selection of the pilot facility. The operation of the pilot facility will be assessed and based on experience other facilities will be upgraded and connected to the grid. The transmission grid might need to be upgraded for accommodation of the biomethan.
Energy Transition Related Project | ETR-N-226 | Fos Tonkin LNG Terminal Evolution | Elengy | Less-Advanced | Other Type | handling all unavoidable LNG evaporations (boil off gas) up to about 10 000 m3/h, without any flaring, the purpose being to be able to load up to 150 bunker vessels and 10 000 tanker trucks per year under any circumstances. | The project aims to adapt the Fos Tonkin LNG terminal into a small scale LNG hub, fully dedicated to the energy transition for the benefit of its clients in France, the neighbouring countries and beyond. It shall, in particular, allow the terminal to being able to operate without any flaring in all circumstances. Thus, the project will doubly contribute to the energy transition: 1) it will contribute to the development of the use of LNG as an alternative fuel much cleaner and less CO2-emitting than oil-based products, and 2) it will prevent any CO2 emission on the small scale LNG terminal where LNG will be loaded into bunker vessels, tanker trucks and tank wagons.
Energy Transition Related Project | ETR-N-300 | HyOffWind Zeebrugge | Fluxys, Eoly, Parkwind | Less-Advanced | Power-to-Gas |  | Eoly, part of Colruyt Group, Fluxys and Parkwind have set up a collaboration to boost the sustainability of the energy landscape in Belgium. The ambition is to build an industrial-scale power-to-gas installation that converts green electricity into green hydrogen that can be transported and stored in the existing natural gas infrastructure. With the project, Eoly, Parkwind and Fluxys are taking a new step towards solutions for a low-carbon future. In an initial phase the feasibility of the installation will be more closely examined. Unlike demonstration projects elsewhere in Europe, Eoly, Parkwind and Fluxys envisage to realise in Belgium one of the first industrial-scale power-to-gas facilities. The aim is to build a power-to-gas installation that can convert several megawatts of electricity into green hydrogen which can be marketed as carbon-free fuel or feedstock. | Industrial-scale power-to-gas installation | Feasibility study for an industrial scale power-to-gas facility to convert a load of 25 MW electricity from wind into green hydrogen (0.4 GWh/d).
Energy Transition Related Project | ETR-N-305 | PEGASUS | S.G.I. SpA | Less-Advanced | Power-to-Gas |  | Pegasus Project aims to demonstrate the operation on an industrial scale PtG system, one of the technologies that can contribute most to the increase of energy produced 100% from non-programmable renewable sources, for a progressive decarbonisation of the energy system. The aim of the project is to produce 100% renewable methane gas (CH4) on an industrial scale, through an integrated system of conversion of H2O to H2 through RES powered electrolysis and CO₂ supply from biomethane upgrading processes, with subsequent methanation and feeding into SGI transport network with access to all services of the gas system, i.e. export, storage, distribution and liquefaction. | PEGASUS | The project includes: - The project foresees - High voltage interconnection with the electricity grid for renewable energy supply to water electrolysis process - Interconnection with existing biogas plant for CO2 withdrawal, available from biomethane upgrading unit - CO2 storage at 40 bar - Electrolyzer for hydrogen production, nominal power 23 MW - Hydrogen storage at 200 bar - Methanation reactor, nominal power 4,5 MW (according to methane HHV) Capacity increment (production of renewable methane): 0,12 GWh/day
Energy Transition Related Project | ETR-N-306 | Greening of Gas (GoG) | NET4GAS, s.r.o. | Less-Advanced | Power-to-Gas |  | The aim of the project is to realise a demonstration facility of Power2Gas technology and to produce biomethane and synthetic methane for the first time in the Czech Republic thanks to this unique technology. The project consists of a combination of biogas purification technology (bio methanization) with an electrolyser, that is, the production of hydrogen by electrolysis from renewable electricity and the subsequent production of synthetic methane. The operator of the facility has not been decided yet. | Greening of Gas | Production of hydrogen (2400 m3 H2/d) or synthetic metan (1200 m3 CH4/d).
Energy Transition Related Project | ETR-N-315 | G2F - Gas to Future | NAFTA a.s. (joint stock company) | Less-Advanced | Power-to-Gas |  | Project Gas to Future (G2F) aims to store renewable energy in form of the hydrogen (H2) in the mixture with natural gas using the existing Naftas gas storages. The unique structure as well as the location of the UGS with all the interconnection allows to store and distribute H2 for neighbouring countries. The project is split in 2 phases. In the first phase, the H2 will be stored with natural gas continuously increasing the amount of H2 stored in whole NAFTA capacity to the volume of 2% of hydrogen and during the second phase the hydrogen content will increase to 10% of H2 vol. That capacity will allow to install and use more renewable energy without any negative impact to the electrical grid as well as will provide energy safety of supply. The project counts to install the electrolysis units to transform electricity to gas (H2). For storing of the H2 will be used the existing gas infrastructure. The project is consistent with goal to reduce CO2 emissions. | 1st phase | For the 1. phase of the project we would like to use our existing gas storages which are in daily use and therefore mostly we would like to use existing infrastructure, so the investment costs should be lower compared to purchase of the new technology. The injected hydrogen to NAFTA reservoirs should be at the rate of 1.32 GWh/day. In order to produce hydrogen and inject it in system at 2% vol. of hydrogen in NAFTAs capacity. It is expected to install P2G technology with power about 84 MW.
Energy Transition Related Project | ETR-N-315 | G2F - Gas to Future | NAFTA a.s. (joint stock company) | Less-Advanced | Power-to-Gas |  | Project Gas to Future (G2F) aims to store renewable energy in form of the hydrogen (H2) in the mixture with natural gas using the existing Naftas gas storages. The unique structure as well as the location of the UGS with all the interconnection allows to store and distribute H2 for neighbouring countries. The project is split in 2 phases. In the first phase, the H2 will be stored with natural gas continuously increasing the amount of H2 stored in whole NAFTA capacity to the volume of 2% of hydrogen and during the second phase the hydrogen content will increase to 10% of H2 vol. That capacity will allow to install and use more renewable energy without any negative impact to the electrical grid as well as will provide energy safety of supply. The project counts to install the electrolysis units to transform electricity to gas (H2). For storing of the H2 will be used the existing gas infrastructure. The project is consistent with goal to reduce CO2 emissions. | 2nd phase | If successful, the project will continue with Hydrogen production in order to achieve hydrogen volume of 10% in whole NAFTAs storage capacity. The injected hydrogen in this phase should be according to our calculation about 6.6 GWh/day. Once again, project will benefit from existing technology of existing NAFTAs storage facilities. Expected installed P2G technology should be at level of 332 MW.
Energy Transition Related Project | ETR-N-322 | North Sea Wind Power Hub | N.V. Nederlandse Gasunie | Less-Advanced | Power-to-Gas |  | An opportunity for internationally coordinated, large scale, far offshore wind energy from the North Sea. An opportunity which would deliver energy at competitive prices around 2030 and facilitate meeting the Paris agreement. Therefore we are committed to explore and develop regional socio-economic beneficial and reliable offshore infrastructure, including possible conversion into P2G, that supports wind farm operations and interconnections between markets.
Energy Transition Related Project | ETR-N-370 | Hydrogen transmission backbone Netherlands | N.V. Nederlandse Gasunie | Less-Advanced | Other Type | This is a tranmission project which transports hydrogen (for example from P2g) to customers and storage. | This project aims to create a nationwide hydrogen transmission grid. It connects the five largest industrial clusters in the Netherlands, the German Ruhrgebied and Dutch underground gas storage. The hydrogen transmission backbone will be build with existing as well as new gas infrastructure. Transmission capacity can be at least 10 GW (240 GWh/d) in 2030 for all x-border interconnection points.
Energy Transition Related Project | ETR-N-396 | Djewels | Nouryon | Less-Advanced | Power-to-Gas |  | The project is a significant step towards scaling up the electrolysis technology, (co-) develop, own and operate a large scale electrolyser, offering conversion services (electricity à hydrogen) to market parties, contribution to the development of a hydrogen economy in (North-) Netherlands, particularly in the chemical industry and mobility sector.
Energy Transition Related Project | ETR-N-401 | Antwerp@C | Fluxys and Antwerp Port Authority | Less-Advanced | CCS/CCU |  | The climate target of getting Belgian CO2 emissions 35% lower by 2030 is a formidable challenge. In this context Antwerp Port Authority and gas infrastructure operator Fluxys believe strongly that carbon capture, storage and reuse by industry is an important weapon in the fight against climate change. They are therefore teaming up to take further practical steps that will help give shape to the energy transition. After a first opportunity analysis, both project partners have decided to perform a feasibility study for open access CO2 transport and storage infrastructure connecting the Antwerp port region to storage sites abroad and usage sites in the region. Both transport by pipeline and ship are being investigated. If the results of the feasibility study are positive then the aim is to jointly promote practical projects.
Energy Transition Related Project | ETR-N-406 | hybridge - gas grid infrastructure | Open Grid Europe GmbH | Less-Advanced | Power-to-Gas |  | Amprion and OGE want to advance sector coupling. The goal of the project partners is to optimally coordinate the electricity and gas systems. The system-oriented use of a power-to-gas plant can thus avoid bottlenecks in the transmission grid. From 2023, the plant will convert up to 100 MW of electricity into hydrogen. The aim is to trial all future uses of hydrogen. Part of Open Grid Europe's existing gas pipeline system will be converted to transport pure hydrogen. Companies with a need for hydrogen can connect to this network. The mobility sector and converted gas storage facilities can also be integrated. The addition of hydrogen to natural gas grids and methanisation are also part of the hybridge concept. This means that the green gas can also be used for other purposes, such as heating. The project can be considered in two parts, the electrolysis (realized by Amprion) and the gas grid infrastructure (realized by OGE). This project only includes the gas grid infrastructure part.
Energy Transition Related Project | ETR-N-427 | P2G integrated in Reganosa NG Transmission Grid | Reganosa | Less-Advanced | Power-to-Gas |  | Reganosa promotes for TYNDP2020 an energy transition project base on the integration of P2G technologies in Reganosa NG Transmission Grid which has the objective of facilitating the integration of renewables with the NG grid, the achievement of decarbonisation and efficiency targets, the reduction of other air pollutants and improving the sector coupling. | P2G integrated in Reganosa NG Transmission Grid | Renewable energy generation (Photo Voltaic &/or Wind Power) of 100 MW to be installed, producing H2 in a rate around 2 t/h. The project will be located in an area where a coal power station was installed. Therefore, both, a NG pipeline and a High Voltage infrastructure is already in place to be immediately used, being a perfect point of injection for the H2 produced and also an optimal point to be powered supply, if this be the case. Existent high pressure (#600) pipeline is 16 inch.
Energy Transition Related Project | ETR-N-432 | Athos | N.V. Nederlandse Gasunie | Less-Advanced | CCS/CCU |  | Development of an open CO2 backbone and offshore storage in the North sea channel region for large industry
Energy Transition Related Project | ETR-N-449 | Hydrogen Region Lausitz | ONTRAS Gastransport GmbH | Less-Advanced | Other Type | Hydrogen | Hydrogen from a large-scale electrolysis shall be injected into the gas transmission network of ONTRAS. The energy will be commercially offered to reduce the CO2 footprint of private households. At later stages the hydrogen ratio in the gas supply of a community will be increased with the target of eventually switch to a 100% hydrogen. When the project is completed the commercial operators are Enertrag AG, Energiequelle GmbH, ONTRAS Gastransport GmbH (depending on the specific topic). The project CAPEX figures refer to the overall project. In particular investments and operational costs for electricity generation and electrolysis will be covered by non-regulated entities, notably Enertrag AG, Energiequelle GmbH. | Pre-Feasibility | 35 400 MWh/h
Energy Transition Related Project | ETR-N-449 | Hydrogen Region Lausitz | ONTRAS Gastransport GmbH | Less-Advanced | Other Type | Hydrogen | Hydrogen from a large-scale electrolysis shall be injected into the gas transmission network of ONTRAS. The energy will be commercially offered to reduce the CO2 footprint of private households. At later stages the hydrogen ratio in the gas supply of a community will be increased with the target of eventually switch to a 100% hydrogen. When the project is completed the commercial operators are Enertrag AG, Energiequelle GmbH, ONTRAS Gastransport GmbH (depending on the specific topic). The project CAPEX figures refer to the overall project. In particular investments and operational costs for electricity generation and electrolysis will be covered by non-regulated entities, notably Enertrag AG, Energiequelle GmbH. | Pre-Feasibility | 70 800 MWh/h
Energy Transition Related Project | ETR-N-452 | Element Eins | Thyssengas GmbH, Gasunie Deutschland Transport Services GmbH, Tennet TSO Gm | Less-Advanced | Power-to-Gas |  | The grid operators TenneT, Gasunie Deutschland and Thyssengas have put forward detailed plans for coupling the electricity and gas grids and advancing the energy transition. The three grid operators are planning to build a power-to-gas pilot plant in Lower Saxony; at an electrical input of 100 megawatts, it will be one of the largest of its kind in Germany. The “Element Eins” pilot project will give the companies first experiences with power-to-gas facilities on an industrial scale. Starting in 2023, the pilot plant will be connected to the grid gradually. By converting green electricity into gas, it will develop new storage capacities for renewable energies. The partners ultimately hope to achieve a comprehensive coupling of the energy, transport and industrial sectors. Gas that has been produced from green electricity will be transported from the North Sea to the Ruhr region through existing pipelines. It could also be made available to the mobility sector. | using separate infrastructure | electrical input of 100 megawatts new entry point: not defined yet Capacity H2: 1.8 GWh/d
Energy Transition Related Project | ETR-N-452 | Element Eins | Thyssengas GmbH, Gasunie Deutschland Transport Services GmbH, Tennet TSO Gm | Less-Advanced | Power-to-Gas |  | The grid operators TenneT, Gasunie Deutschland and Thyssengas have put forward detailed plans for coupling the electricity and gas grids and advancing the energy transition. The three grid operators are planning to build a power-to-gas pilot plant in Lower Saxony; at an electrical input of 100 megawatts, it will be one of the largest of its kind in Germany. The “Element Eins” pilot project will give the companies first experiences with power-to-gas facilities on an industrial scale. Starting in 2023, the pilot plant will be connected to the grid gradually. By converting green electricity into gas, it will develop new storage capacities for renewable energies. The partners ultimately hope to achieve a comprehensive coupling of the energy, transport and industrial sectors. Gas that has been produced from green electricity will be transported from the North Sea to the Ruhr region through existing pipelines. It could also be made available to the mobility sector. | addition to natural gas | Injektion of hydrogen to existing natural gas pipelines; electrical input of 40 megawatts new entry point: not defined yet Capacity H2: 0,72 GWh/d
Energy Transition Related Project | ETR-N-483 | L2DG (LNG to Decarbonised Gas) | Reganosa | Less-Advanced | Other Type | The project is based on a methane autothermal reforming plant (autoreforming or plasma reforming) for H2 production with NG grid injection which has the objective of achieving the decarbonisation of the LNG entries from the regasification terminals. | Reganosa promotes for TYNDP2020 an energy transition project based on a methane autothermal reforming plant for H2 production with NG grid injection which has the objective of achieving the decarbonisation of the LNG entries from the regasification terminals, reaching at the same time the efficiency targets. | L2DG (LNG to Decarbonised gas) | The methane autothermal reforming plant will produce H2 in rate around 4 t/h. This capacity represents the 5% of the technical send-out capacity of Mugardos LNG terminal. The entry of the authothermal reforming plant will be the natural gas regasificated in the terminal and the H2 obtained will be injected in the natural gas grid owned by Reganosa. This new plant will be located in the existing installation of Mugardos LNG terminal.
Energy Transition Related Project | ETR-N-501 | Hub País Vasco | Enagas S.A. | Less-Advanced | Power-to-Gas |  | Green hydrogen production, P2G and renewable hydrogen for mobility, industry and other applications. This project is considering the production of green hydrogen for its use in refineries and port areas. The CAPEX considers a minimum of 30 MW of electrolysis, a high pressure hydrogen injection plant, residential and transport applications. The prefeasibility study, which is under definition, considers this CAPEX and 15 years. | H2 Valley Biscay | Max. 80MW electrolysis and minimum of 30 MW. Calculations performed with 30 MW; hence 6.000 m3 H2/h are expected.
Energy Transition Related Project | ETR-N-521 | Hub Murcia | Enagas S.A. | Less-Advanced | Power-to-Gas |  | The main objective of the project is the generation of Synthetic Natural Gas (SNG) by a catalytic methanation reaction between green hydrogen obtained by means of electrolysis and CO2, to substitute the natural gas self-consumption in the LNG Terminal of Enagás in Cartagena. This project considers the production of green hydrogen and the synthesis of SNG for its use in LNG terminal and port areas. The CAPEX considers a minimum of 0,2MW and max. of 5 MW of electrolysis, the consumption of the SNG in the LNG terminal grid and other applications. The prefeasibility study, that may change, considers this CAPEX and 15 years. The SNG will be used inside the LNG Plant so it won’t be injected in the transmission grid | P2G Cartagena LNG Terminal | Electrolyser: max 5 MW. Calculations made with 2,1 MW; hence expected production: 420 m3 H2/h H2 injection (The H2 will be injected in the gas grid): 0,00356 GWh/day SNG injection (The SNG will be used inside the LNG Plant so it won’t be injected in the transmission grid): 0,00045 GWh/d
Energy Transition Related Project | ETR-N-528 | Microliquefaction plants | Snam4mobility | Less-Advanced | Other Type | Micro-liquefaction of natural gas and biomethane | The project consists in developing the sustainable mobility by realizing 3/4 microliquefaction plant that would be used to fuel heavy transport also in naval sector. The project will realize also the possibility to produce Bio-LNG (LNG produced by biomethane) | All the project | the project consiste in the construction of 3/4 micloliquefaction plant. The project liquefaction capacity is still confidential as a part of the company strategy.
Energy Transition Related Project | ETR-N-537 | Hub Aragon | Enagas S.A. | Less-Advanced | Power-to-Gas |  | Hydrogen injection into the gas grid is a way to decarbonise this infrastructure through its later use in natural gas admixtures or to use its capacity and extension for the transportation of this energy carrier from the production point to the consumption point. More knowledge is required about the impact of hydrogen injection on current gas grid components and the design of the injection systems. This project will allow in a first phase the demonstration of all parts included in an injection system: hydrogen production technologies, hydrogen quality analysers, hydrogen flowmeters and test bench for their calibration, closed loop for analyse the impact of different concentrations of hydrogen in natural admixtures, hydrogen compression and storage… The information collected will consolidate the basics for the specifications and guidelines that should be taken into account in a real injection system. | Phase 2 | Injection of hydrogen into a high pressure pipeline under real conditions Max 0,5 MW electrolysis Total expected production: 100 Nm3/h H2
Energy Transition Related Project | ETR-N-537 | Hub Aragon | Enagas S.A. | Less-Advanced | Power-to-Gas |  | Hydrogen injection into the gas grid is a way to decarbonise this infrastructure through its later use in natural gas admixtures or to use its capacity and extension for the transportation of this energy carrier from the production point to the consumption point. More knowledge is required about the impact of hydrogen injection on current gas grid components and the design of the injection systems. This project will allow in a first phase the demonstration of all parts included in an injection system: hydrogen production technologies, hydrogen quality analysers, hydrogen flowmeters and test bench for their calibration, closed loop for analyse the impact of different concentrations of hydrogen in natural admixtures, hydrogen compression and storage… The information collected will consolidate the basics for the specifications and guidelines that should be taken into account in a real injection system. | Phase 1 | Demonstration of hydrogen technologies
Energy Transition Related Project | ETR-N-562 | Energy Park Bad Lauchstädt | ONTRAS Gastransport GmbH | Less-Advanced | Power-to-Gas |  | Hydrogen is produced by a 35 MW electrolyzer, which is directly connected to a wind farm. The pure hydrogen is stored in a nearby salt cavern. The transport between the underground storage and the end users for the hydrogen inside an existing industrial area is provided by a converted natural gas pipeline. | Feasibility | capacity increment: 25.000 kWh/h; 0,60 GWh/d
Energy Transition Related Project | ETR-N-591 | Power to gas plant in the south of Italy | Snam Rete Gas S.p.A. | Less-Advanced | Power-to-Gas |  | The project consist in the realization of a power to gas plant in the south of Italy that will allow the production of biosingas by methanation of hydrogen, coming from electrolysis, with CO2. The electric feed will be made by renewable sources. | All the project | The project that will be developed will have a maximum size of about 10 MW, with a dayly production up to about 192 MWh/d
Energy Transition Related Project | ETR-N-595 | Transport of hydrogen into natural gas network | Snam Rete Gas S.p.A. | Less-Advanced | Other Type | The project consist in developing the facilities needed to transport a percentage of hydrogen into Natural gas up to 5%. The first producion of H2 in Italy will come from P2G (see ETR-N-591) | The project consist in the development of the facilities needed to receive a quantity of hydrogen into the gas network up to the 5 % of the mix.
Energy Transition Related Project | ETR-N-616 | Renewable Methane according to NEP2020 | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Biomethane Production |  | The upcoming NDP will include two concrete scenarios for the integration of renewable gas: • For 2025 a market survey was performed by the German TSOs to collect concrete projects for the supply of renewable gas from the use of P2G. Projects could either provide directly hydrogen or methane via an additionl methanation process. • For 2030 a total of 7.5 GW_el of P2G will be considered. The German TSOs see large need for P2G installations for an efficient path towards 2050. This scenario should support the ramp up of the development. This project is covering the renewable methane infeed from P2G as envisioned in the NDP 2020. It covers in the “market survey”-path the total supply from renewable gas projects, that have not been put individually into the TYNDP. | Phase 1 | 100MW PtG; hydrogen + biomethane
Energy Transition Related Project | ETR-N-617 | Project to facilitate biomethane production plants inteconnection | Snam Rete Gas | Less-Advanced | Biomethane Production |  | The project sonsists of developing all the facilities needed to guarantee better conditions to make possible new biomethane production plant to be connected to the gas network
Energy Transition Related Project | ETR-N-622 | Renewable Hydrogen according to NEP2020 | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Power-to-Gas |  | The upcoming NDP will include two concrete scenarios for the integration of renewable gas: • For 2025 a market survey was performed by the German TSOs to collect concrete projects for the supply of renewable gas from the use of P2G. Projects could either provide directly hydrogen or methane via an additionl methanation process. • For 2030 a total of 7.5 GW_el of P2G will be considered. The German TSOs see large need for P2G installations for an efficient path towards 2050. This scenario should support the ramp up of the development. This project is covering the hydrogen infeed as envisioned in the NDP 2020. It covers in the “market survey”-path the total hydrogen supply from renewable gas projects, that have not been put individually into the TYNDP. The “towards 2050”-path is including the (additional) P2G installations considered in the NDP2020 for the 2030 scenario. | Phase 1 | 3 Projects; 94 MW(el)
Energy Transition Related Project | ETR-N-622 | Renewable Hydrogen according to NEP2020 | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Power-to-Gas |  | The upcoming NDP will include two concrete scenarios for the integration of renewable gas: • For 2025 a market survey was performed by the German TSOs to collect concrete projects for the supply of renewable gas from the use of P2G. Projects could either provide directly hydrogen or methane via an additionl methanation process. • For 2030 a total of 7.5 GW_el of P2G will be considered. The German TSOs see large need for P2G installations for an efficient path towards 2050. This scenario should support the ramp up of the development. This project is covering the hydrogen infeed as envisioned in the NDP 2020. It covers in the “market survey”-path the total hydrogen supply from renewable gas projects, that have not been put individually into the TYNDP. The “towards 2050”-path is including the (additional) P2G installations considered in the NDP2020 for the 2030 scenario. | Phase 3 | 8 Projects; 500 MW(el)
Energy Transition Related Project | ETR-N-622 | Renewable Hydrogen according to NEP2020 | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Power-to-Gas |  | The upcoming NDP will include two concrete scenarios for the integration of renewable gas: • For 2025 a market survey was performed by the German TSOs to collect concrete projects for the supply of renewable gas from the use of P2G. Projects could either provide directly hydrogen or methane via an additionl methanation process. • For 2030 a total of 7.5 GW_el of P2G will be considered. The German TSOs see large need for P2G installations for an efficient path towards 2050. This scenario should support the ramp up of the development. This project is covering the hydrogen infeed as envisioned in the NDP 2020. It covers in the “market survey”-path the total hydrogen supply from renewable gas projects, that have not been put individually into the TYNDP. The “towards 2050”-path is including the (additional) P2G installations considered in the NDP2020 for the 2030 scenario. | Phase 4 | 9 Projects; 520 MW(el)
Energy Transition Related Project | ETR-N-622 | Renewable Hydrogen according to NEP2020 | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Power-to-Gas |  | The upcoming NDP will include two concrete scenarios for the integration of renewable gas: • For 2025 a market survey was performed by the German TSOs to collect concrete projects for the supply of renewable gas from the use of P2G. Projects could either provide directly hydrogen or methane via an additionl methanation process. • For 2030 a total of 7.5 GW_el of P2G will be considered. The German TSOs see large need for P2G installations for an efficient path towards 2050. This scenario should support the ramp up of the development. This project is covering the hydrogen infeed as envisioned in the NDP 2020. It covers in the “market survey”-path the total hydrogen supply from renewable gas projects, that have not been put individually into the TYNDP. The “towards 2050”-path is including the (additional) P2G installations considered in the NDP2020 for the 2030 scenario. | Phase 5 | 10 Projects; 570 MW(el)
Energy Transition Related Project | ETR-N-622 | Renewable Hydrogen according to NEP2020 | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Power-to-Gas |  | The upcoming NDP will include two concrete scenarios for the integration of renewable gas: • For 2025 a market survey was performed by the German TSOs to collect concrete projects for the supply of renewable gas from the use of P2G. Projects could either provide directly hydrogen or methane via an additionl methanation process. • For 2030 a total of 7.5 GW_el of P2G will be considered. The German TSOs see large need for P2G installations for an efficient path towards 2050. This scenario should support the ramp up of the development. This project is covering the hydrogen infeed as envisioned in the NDP 2020. It covers in the “market survey”-path the total hydrogen supply from renewable gas projects, that have not been put individually into the TYNDP. The “towards 2050”-path is including the (additional) P2G installations considered in the NDP2020 for the 2030 scenario. | Phase 2 | 7 Projects; 260 MW(el)
Energy Transition Related Project | ETR-N-624 | Biomethane: Reverse flow projects | GRTgaz | Less-Advanced | Reverse flow DSO-TSO |  | The scattered production of renewable gas will take an increasing part in the gas mix. Grid extensions will be required to collect this generation and backhaul facilities will allow the excess energy to be absorbed when supply exceeds local demand. In the framework of the scenario of the Energy Transition law for which renewable gas injections would reach 22 TWh by 2028, the number of producers connected to the distribution network would amount to about 1,300. Under these assumptions, it can be estimated that around 37 backhaul installations and mutualised compressors −90% in D/T (Distribu-tion/Transmission) and 10% in T/T (Regional Transmis-sion/Principal Transmission infrastructures)− would be re-quired, i.e. a financial envelope of €435 million by 2030. These network adaptations will enable to maximize the volume of biomethane injected into the gas system and reach national target for renewable gas (10% of gas consumption in 2030)
Energy Transition Related Project | ETR-N-633 | GETH2-ETR 1 | Nowega GmbH | Less-Advanced | Power-to-Gas |  | Start for the Germany-wide hydrogen infrastructure: Germany has set itself the target of reducing CO2 emissions by 80-95 percent (compared to 1990). In order to achieve the climate targets with the greatest possible efficiency, other key technologies are needed in addition to the expansion of renewable energy generation and the electricity infrastructure. The conversion of electricity from renewables to hydrogen (H2) - power-to-gas - is such a key to a successful energy transition. The principle: - Electricity from renewable energies is converted to H2 - The green H2 is distributed via the existing gas infrastructure - In the industrial, transport, energy and heating sectors, green H2 is used as a CO2-free energy source - H2 that is not used directly is stored in underground caverns especially for dark doldrums | GET H2 | 919,8 GWh/y max
Energy Transition Related Project | ETR-N-728 | Biomethane: connecting production units and reverse flow projects | TEREGA | Less-Advanced | Biomethane Production |  | The scattered production of renewable gas will take an increasing part in the gas mix. Grid extensions will be required to connect this production units to the transmission network. Backhaul facilities will also be needed to allow biomethane injected in the distribution to flow back to the transmission grid when the biomethane injected locally exceeds local demand. These network adaptations will enable to maximize the volume of biomethane injected into the gas system and reach national target for renewable gas (10% of gas consumption in 2030). Teréga expects 28 projects of grid extension to be completed by 2029 for an estimated production of 3 TWh/year. Teréga also expects 8 backhaul projects for an estimated reverse flow of 0,4 TWh/year. | Grid extension | Pipes to connect biomethane production units
Energy Transition Related Project | ETR-N-728 | Biomethane: connecting production units and reverse flow projects | TEREGA | Less-Advanced | Biomethane Production |  | The scattered production of renewable gas will take an increasing part in the gas mix. Grid extensions will be required to connect this production units to the transmission network. Backhaul facilities will also be needed to allow biomethane injected in the distribution to flow back to the transmission grid when the biomethane injected locally exceeds local demand. These network adaptations will enable to maximize the volume of biomethane injected into the gas system and reach national target for renewable gas (10% of gas consumption in 2030). Teréga expects 28 projects of grid extension to be completed by 2029 for an estimated production of 3 TWh/year. Teréga also expects 8 backhaul projects for an estimated reverse flow of 0,4 TWh/year. | Backhaul facilities | Facilities adjustments (compressor power, metering) at the connection point between the distribution and the transmission grids

## Time Schedule
Time Schedule
Type | Code | Project Name | Host Country | Promoter | Maturity Status | PreFeasibility Starts | PreFeasibility Ends | PreFeasibility Info Not Available | Feasibility Starts | Feasibility Ends | Feasibility Info Not Available | FEED Starts | FEED Ends | FEED Info Not Available | Permitting Phase Starts | Permitting Phase Ends | Permitting Info Not Available | Supply Contracts Ends | Supply Contracts Info Not Available | FID | FID Info Not Available | Construction Starts | Construction Ends | Construction Info Not Available | Commissioning Starts | Commissioning Ends | Grant Obtention Date | Schedule Status | Delay Explanation
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Greece | Trans Adriatic Pipeline AG | FID |  |  | Please see more general information below; if necessary, TAP can provide more detailed information |  |  | Please see more general information below; if necessary, TAP can provide more detailed information | 2008-01-01 | 2013-03-25 |  | 2011-09-01 | 2018-11-01 |  | 2015-04-01 |  | 2013-12-17 |  | 2016-05-16 | 2020-10-01 |  | 2020 | 2020 | 2017-08-02 | On time | N/A
LNG Terminal | LNG-F-82 | LNG terminal Krk | Croatia | LNG Hrvatska d.o.o. | FID | 2016-06-08 | 2017-04-28 |  | 2012-07-12 | 2014-01-15 |  | 2017-03-28 | 2017-12-13 |  | 2013-10-01 | 2019-04-09 |  | 2019-01-31 |  | 2019-01-31 |  | 2019-01-31 | 2020-12-31 |  | 2020 | 2027 | 2017-12-18 | Rescheduled | In comparison with last TYNDP, the project is rescheduled with new beginning of operation from 1st January 2021.
Pipeline including CS | TRA-F-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Croatia | Plinacro Ltd | FID |  |  | It is not necessary | 2015-09-01 | 2016-10-01 |  | 2015-10-01 | 2017-03-01 |  | 2009-07-02 | 2019-01-01 |  | 2019-01-01 |  | 2019-06-11 |  | 2019-06-12 | 2020-12-31 |  | 2020 | 2020
Pipeline including CS | TRA-F-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | Romania | SNTGN Transgaz SA | FID | 2014-01-01 | 2014-06-30 |  | 2017-06-07 | 2017-12-07 |  | 2018-01-01 | 2020-12-31 |  | 2017-12-29 | 2019-12-31 |  |  | Multiple contracts | 2018-04-25 |  | 2018-05-01 | 2020-12-31 |  | 2020 | 2020 |  | Delayed | Obtaining the necessary permits, authorizations and agreements, extension of the duration of the tender procedure
LNG Terminal | LNG-F-163 | Gran Canaria LNG Terminal | Spain | Gascan | FID | 2008-01-01 | 2008-01-01 |  | 2008-01-01 | 2008-01-01 |  |  |  | The design of this LNG terminal is currently under review, and therefore the specifications of the final project could differ from the ones reported |  |  | No data |  | Not applicable | 2008-05-01 |  |  |  | The design of this LNG terminal is currently under review, and therefore the specifications of the final project could differ from the ones reported | 2029 | 2029 |  | Rescheduled | The start-up of the Gran Canaria LNG terminal is assumed to take place within the TYNDP period. For practical purposes, the last year of the ten-year period is reported as the start-up date. This does not, however, constitute an estimate of the start-up date. Based on demand estimates, the terminal would already be justified by 2022.
LNG Terminal | LNG-F-178 | Musel LNG terminal | Spain | Enagas Transporte S.A.U. | FID | 2008-01-01 | 2008-01-01 |  | 2008-01-01 | 2008-01-01 |  |  |  | Construction has been completed and Enagás Transporte expects to get the start-up authorization by 2021 |  |  | Construction has been completed and Enagás Transporte expects to get the start-up authorization by 2021 |  | Not applicable | 2008-05-01 |  |  |  | Construction has been completed and Enagás Transporte expects to get the start-up authorization by 2021 | 2021 | 2021 |  | Rescheduled | Construction has been completed and Enagás Transporte expects to get the start-up authorization by 2021
LNG Terminal | LNG-F-183 | Tenerife LNG Terminal | Spain | Gascan | FID | 2008-01-01 | 2008-01-01 |  | 2008-01-01 | 2008-01-01 |  |  |  | The design of this LNG terminal is currently under review, and therefore the specifications of the final project could differ from the ones reported |  |  | The design of this LNG terminal is currently under review, and therefore the specifications of the final project could differ from the ones reported |  | Not applicable | 2008-05-01 |  |  |  | The design of this LNG terminal is currently under review, and therefore the specifications of the final project could differ from the ones reported | 2022 | 2022 |  | Rescheduled | The design of this LNG terminal is currently under review, and therefore the specifications of the final project could differ from the ones reported
Pipeline including CS | TRA-F-190 | Poland - Slovakia interconnection | Slovakia | eustream,a.s. (a joint-stock company) | FID | 2011-03-01 | 2013-05-31 |  | 2011-05-02 | 2013-07-31 |  | 2015-10-01 | 2019-04-30 |  | 2015-08-01 | 2018-09-30 |  | 2019-12-31 |  | 2018-04-19 |  | 2018-05-01 | 2020-12-30 |  | 2021 | 2021 | 2017-12-18 | Delayed | 1)Necessity to prolong public procurement proceeding due to the request of tenderers for extension of time period for submission of the initial tender bids. 2)Prolongation of the tendering process caused by postponement of documentation submission by the winning bidder resulted in delay of detailed engineering. 3) Delay in deliveries of pipelines
Pipeline including CS | TRA-F-208 | Reverse Flow TENP Germany | Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | FID | 2012-10-01 | 2015-01-01 |  | 2012-10-01 | 2015-01-01 |  | 2017-03-01 | 2017-11-30 |  | 2016-12-01 | 2018-10-31 |  | 2018-04-01 |  | 2015-01-01 |  | 2017-06-01 | 2020-10-01 |  | 2020 | 2020 |  | Rescheduled
Pipeline including CS | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | Poland | GAZ-SYSTEM S.A. | FID |  |  | N/A | 2016-12-01 | 2017-09-30 |  | 2015-06-18 | 2019-11-12 |  | 2015-12-09 | 2019-10-11 |  |  | N/A | 2018-05-24 |  | 2019-09-30 | 2021-06-30 |  | 2021 | 2021 |  | On time
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | Poland | GAZ-SYSTEM S.A. | FID |  |  | N/A |  |  | N/A | 2013-09-23 | 2017-08-11 |  | 2014-11-05 | 2017-08-11 |  |  | N/A | 2017-11-05 |  | 2017-11-09 | 2021-03-30 |  | 2021 | 2021 |  | On time
Storage Facility | UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | Italy | STOGIT | FID |  |  | The project is an aggregation of several intervention in 6 different location so it is impossible to give a schedule |  |  | The project is an aggregation of several intervention in 6 different location so it is impossible to give a schedule |  |  | The project is an aggregation of several intervention in 6 different location so it is impossible to give a schedule |  |  | The project is an aggregation of several intervention in 6 different location so it is impossible to give a schedule |  | The project is an aggregation of several intervention in 6 different location so it is impossible to give a schedule | 2011-11-24 | The project is an aggregation of several intervention in 6 different location so it is impossible to give a schedule |  |  | The project is an aggregation of several intervention in 6 different location so it is impossible to give a schedule | 2028 | 2028
LNG Terminal | LNG-F-272 | Upgrade of LNG terminal in Świnoujście | Poland | GAZ-SYSTEM S.A. | FID |  |  | N/A | 2015-04-01 | 2017-12-01 |  | 2017-12-01 | 2018-06-01 |  | 2017-08-21 | 2019-01-23 |  |  | N/A | 2018-05-11 |  | 2018-04-15 | 2023-05-31 |  | 2023 | 2023 |  | On time
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | FID |  |  | N/A | 2011-08-01 | 2013-07-31 |  | 2014-10-21 | 2018-11-16 |  | 2015-10-06 | 2018-06-28 |  |  | N/A | 2018-04-24 |  | 2017-12-12 | 2021-09-18 |  | 2021 | 2021 | 2017-12-18
Pipeline including CS | TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | Hungary | FGSZ Ltd. | FID | 2014-03-01 | 2014-06-01 |  | 2016-09-01 | 2017-07-31 |  | 2018-07-01 | 2018-10-03 |  | 2018-07-01 | 2018-09-30 |  | 2018-12-31 |  | 2017-06-13 |  | 2018-10-01 | 2019-12-31 |  | 2019 | 2019 | 2015-10-14 | On time
Pipeline including CS | TRA-F-291 | NOWAL - Nord West Anbindungsleitung | Germany | GASCADE Gastransport GmbH | FID |  |  | completed |  |  | completed |  |  | completed | 2014-01-01 | 2016-01-01 |  |  | in progress | 2019-05-01 |  | 2020-04-01 | 2020-10-01 |  | 2020 | 2020 |  | On time
Pipeline including CS | TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | Bulgaria | Bulgartransgaz EAD | FID | 2016-01-01 | 2016-12-01 |  | 2008-08-01 | 2017-08-01 |  | 2013-04-01 | 2020-02-01 |  | 2009-09-01 | 2020-10-01 |  | 2021-02-01 |  | 2018-01-11 |  | 2014-09-01 | 2022-06-30 |  | 2021 | 2024 | 2016-04-27 | Delayed | Revision of the PCI Phase 2 implementation schedule to ensure consistency in the execution of construction activities for the sections, sub-sections and compressor stations involved in this phase.
Pipeline including CS | TRA-F-307 | H-gas exit OSZ GTG Nord | Netherlands | Gasunie Transport Services B.V. | FID |  |  | N.a. | 2017-11-01 | 2018-02-21 |  | 2018-04-01 | 2018-12-31 |  | 2019-05-01 | 2019-09-01 |  | 2019-08-05 |  | 2019-02-20 |  | 2019-10-03 | 2020-01-24 |  | 2020 | 2027
Storage Facility | UGS-F-311 | Bilciuresti daily withdrawal capacity increase | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | FID | 2015-02-03 | 2015-12-09 |  | 2016-03-02 | 2017-03-17 |  | 2017-12-08 | 2020-07-03 |  | 2018-05-04 | 2020-12-17 |  | 2023-06-12 |  | 2017-06-02 |  | 2018-05-04 | 2025-09-05 |  | 2025 | 2025 |  | On time
Pipeline including CS | TRA-F-329 | ZEELINK | Germany | Open Grid Europe GmbH and Thyssengas GmbH | FID |  |  | N/A |  |  | N/A | 2015-09-04 | 2020-09-01 |  | 2017-09-18 | 2020-09-01 |  | 2016-08-01 |  | 2018-01-01 |  | 2019-04-01 | 2023-03-31 |  | 2023 | 2023 |  | On time
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | Croatia | Plinacro Ltd | FID |  |  | It was not necessary since the Feasibility Study was drawn up | 2014-11-01 | 2015-03-16 |  | 2016-09-30 | 2017-05-31 |  | 2015-06-16 | 2018-05-31 |  | 2018-01-01 |  | 2017-12-15 |  | 2018-01-01 | 2019-12-31 |  | 2019 | 2019 |  | On time
Pipeline including CS | TRA-F-340 | CS Wertingen | Germany | bayernets GmbH | FID | 2015-06-01 | 2019-06-30 |  | 2015-07-01 | 2015-11-13 |  | 2016-03-01 | 2016-03-31 |  | 2016-04-29 | 2017-04-03 |  | 2017-08-14 |  | 2016-05-23 |  | 2017-09-27 | 2019-12-31 |  | 2019 | 2019 |  | On time
Pipeline including CS | TRA-F-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | Lithuania | AB Amber Grid | FID | 2012-01-01 | 2012-12-01 |  | 2012-02-01 | 2013-02-01 |  | 2015-05-01 | 2016-09-15 |  | 2016-07-01 | 2016-09-27 |  | 2021-06-30 |  | 2018-05-24 |  | 2019-11-30 | 2021-06-30 |  | 2021 | 2021 | 2015-10-15 | On time
Pipeline including CS | TRA-F-357 | NTS developments in North-East Romania | Romania | SNTGN Transgaz SA | FID |  | 2014-02-28 |  | 2014-02-28 | 2018-01-01 |  | 2016-01-01 | 2018-01-01 |  | 2016-01-01 | 2018-01-01 |  |  |  | 2018-12-12 |  |  |  |  | 2021 | 2021 |  | Delayed | Obtaining the necessary endorsements, agreements and permits, extension of the procurement procedure durations.
Pipeline including CS | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase I | Romania | SNTGN Transgaz S.A. | FID | 2013-09-02 | 2013-12-31 |  | 2014-01-01 | 2014-12-31 |  | 2015-07-01 | 2017-02-01 |  | 2014-01-01 | 2018-02-28 |  | 2017-08-04 |  | 2016-11-30 |  | 2017-12-01 | 2020-12-01 |  | 2020 | 2020 | 2016-09-09 | Delayed | Due to delays occurred in the tendering procedures, the promotion of pieces of laws required for the implementation, the discovery of archaeological sites along the pipeline route and the unfavourable weather conditions, it is currently estimated that even if parts of the project will be completed in 2019, the entire project will be completed by 2020.
Storage Facility | UGS-F-374 | Enhancement of Incukalns UGS | Latvia | JSC "Conexus Baltic Grid" | FID | 2011-10-01 | 2012-02-01 |  | 2017-02-20 | 2017-11-28 |  | 2019-09-30 | 2022-07-10 |  | 2014-05-01 | 2020-12-31 |  | 2022-09-30 |  | 2019-03-06 |  | 2019-03-06 | 2025-12-01 |  | 2019 | 2025 | 2017-05-19 | Rescheduled | Change in market conditions.
Pipeline including CS | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | Bulgaria | ICGB a.d. | FID | 2009-02-01 | 2009-04-30 |  | 2009-05-01 | 2009-07-31 |  | 2010-08-01 | 2016-03-31 |  | 2010-08-01 | 2019-06-30 |  | 2019-08-31 |  | 2015-12-10 |  | 2019-06-01 | 2020-12-01 |  | 2020 | 2025 |  | Delayed | ​Appeals against the tender procedures, during the opening phase there are no restriction on the parties who can appeal against the procedures. At the current stage all the tender procedures are completed and award decisions are taken, there is just one appeal outstanding against the award decision for the selected contractor under the tender for Line pipes manufacture and supply. We are waiting for the decision of Supreme Administrative Court, ecpected by the end of July 2019.
Pipeline including CS | TRA-F-409 | Larino - Chieti | Italy | SGI S.p.A: | FID | 2012-01-01 | 2012-06-30 |  | 2013-03-01 | 2013-11-30 |  | 2014-01-01 | 2014-11-30 |  | 2014-12-15 | 2018-06-25 |  | 2019-03-31 |  | 2017-06-01 |  | 2019-04-01 | 2022-06-30 |  | 2022 | 2022 |  | On time
Pipeline including CS | TRA-F-424 | SAN MARCO - RECANATI | Italy | SGI S.p.A. | FID | 2014-01-01 | 2014-06-30 |  | 2014-07-01 | 2014-12-31 |  | 2015-04-01 | 2015-05-31 |  | 2016-06-15 | 2018-04-09 |  | 2019-01-31 |  | 2015-01-01 |  | 2019-03-15 | 2021-09-30 |  | 2022 | 2022 |  | On time
Pipeline including CS | TRA-F-500 | L/H Conversion Belgium | Belgium | Fluxys Belgium | FID | 2013-06-06 | 2017-12-12 |  | 2018-01-01 | 2018-06-01 |  | 2018-07-02 | 2018-10-31 |  | 2019-03-01 | 2019-08-29 |  | 2019-02-01 |  | 2018-12-28 |  | 2019-06-03 | 2026-05-29 |  | 2026 | 2026 |  | On time
Energy Transition Related Project | ETR-F-516 | CNG and L-CNG stations | Italy | Snam4mobility | FID |  |  | The project is an aggregation of 110 station construction so it is impossible to give a schedule |  |  | The project is an aggregation of 110 station construction so it is impossible to give a schedule |  |  | The project is an aggregation of 110 station construction so it is impossible to give a schedule |  |  | The project is an aggregation of 110 station construction so it is impossible to give a schedule |  | The project is an aggregation of 110 station construction so it is impossible to give a schedule | 2018-11-01 |  |  |  | The project is an aggregation of 110 station construction so it is impossible to give a schedule | 2022 | 2022
Energy Transition Related Project | ETR-F-523 | Biomethane plants development | Italy | Snam4mobility | FID |  |  | The project refers to the construction of 5 plants each one with a different schedule. All the plant will be commissioned befor the end of 2022 |  |  | The project refers to the construction of 5 plants each one with a different schedule. All the plant will be commissioned befor the end of 2022 |  |  | The project refers to the construction of 5 plants each one with a different schedule. All the plant will be commissioned befor the end of 2022 |  |  | The project refers to the construction of 5 plants each one with a different schedule. All the plant will be commissioned befor the end of 2022 |  | The project refers to the construction of 5 plants each one with a different schedule. All the plant will be commissioned befor the end of 2022 | 2018-11-01 |  |  |  | The project refers to the construction of 5 plants each one with a different schedule. All the plant will be commissioned befor the end of 2022 | 2023 | 2023
Energy Transition Related Project | ETR-F-541 | CORE LNGas hive and LNGHIVE2 Infrastructure and logistic solutions | Spain | Enagas Transporte S.A.U. | FID |  |  | No data | 2014-01-01 | 2014-03-01 |  | 2015-01-01 | 2018-10-01 |  | 2017-06-01 | 2018-12-01 |  | 2020-04-01 |  | 2014-01-01 |  | 2017-10-01 | 2020-03-01 |  | 2020 | 2020
Energy Transition Related Project | ETR-F-546 | Jupiter 1000: first industrial demonstrator of Power to Gas in France | France | GRTgaz, Terega | FID |  |  | NA | 2014-01-01 | 2016-01-01 |  |  |  | NA | 2016-01-01 | 2017-06-01 |  |  | NA | 2016-04-15 |  | 2017-06-01 | 2020-06-01 |  | 2020 | 2020 |  | Not applicable
Energy Transition Related Project | ETR-F-587 | West Grid Synergy | France | GRTgaz | FID | 2017-01-01 | 2018-01-01 |  | 2018-01-01 | 2019-01-01 |  | 2019-01-01 | 2020-01-01 |  |  |  | na |  | na | 2018-07-01 |  | 2018-08-01 | 2019-04-01 |  | 2019 | 2019 |  | Not applicable
Pipeline including CS | TRA-F-592 | Balkan Gas Hub-Necessary expansion of the Bulgarian gas transmission system | Bulgaria | Bulgartransgaz EAD | FID |  |  | N/A | 2018-03-15 | 2018-11-27 |  | 2018-01-01 | 2020-03-31 |  | 2018-01-01 | 2020-06-30 |  | 2019-10-30 |  | 2019-01-31 |  | 2019-02-01 | 2022-06-01 |  | 2020 | 2022 | 2017-05-17 | On time
Energy Transition Related Project | ETR-F-599 | Sector coupling: hybrid compressor station | Italy | Snam Rete Gas S.p.A. | FID | 2017-01-01 | 2017-12-31 |  | 2017-01-01 | 2017-12-31 |  | 2018-01-01 | 2021-12-31 |  | 2019-01-01 | 2021-12-31 |  | 2024-06-01 |  | 2018-07-02 |  | 2024-06-01 | 2024-12-31 |  | 2024 | 2024
Energy Transition Related Project | ETR-F-632 | Railway project roadmap. Transformation to LNG | Spain | Enagas Transporte S.A.U. | FID | 2016-01-01 | 2016-06-01 |  | 2019-06-01 | 2020-01-01 |  | 2020-01-01 | 2020-01-01 |  | 2020-01-01 | 2020-01-01 |  |  | Not applicable | 2016-01-01 |  | 2019-09-01 | 2022-01-01 |  | 2022 | 2022 |  | Not applicable
Energy Transition Related Project | ETR-F-743 | Impulse 2025 | France | Teréga | FID |  |  | Depends of the outcome of the Pilot phase |  |  | Depends of the outcome of the Pilot phase |  |  | Depends of the outcome of the Pilot phase |  |  | Depends of the outcome of the Pilot phase |  | Depends of the outcome of the Pilot phase | 2019-07-11 |  |  |  | Depends of the outcome of the Pilot phase | 2025 | 2025 |  | Not applicable | N/A
Pipeline including CS | TRA-F-752 | Capacity4Gas – DE/CZ | Czechia | NET4GAS, s.r.o. | FID | 2015-10-26 | 2017-03-07 |  | 2017-03-08 | 2017-10-31 |  | 2017-07-01 | 2019-06-13 |  | 2017-07-20 | 2019-12-31 |  | 2020-01-31 |  | 2017-03-07 |  | 2018-06-01 | 2021-09-30 |  | 2019 | 2021 |  | On time
Pipeline including CS | TRA-F-755 | CS Rimpar | Germany | GRTgaz Deutschland GmbH | FID |  |  | not available |  |  | not available |  |  | not available | 2019-01-01 | 2019-12-31 |  | 2020-04-01 |  | 2018-07-01 |  | 2020-01-01 | 2023-12-01 |  | 2023 | 2023 |  | On time
Pipeline including CS | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | Germany | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | FID |  |  | completed |  |  | completed |  |  | completed |  |  | completed |  | completed | 2018-06-01 |  |  |  | current status | 2019 | 2022 |  | On time
Pipeline including CS | TRA-F-780 | Baltic Pipe project – onshore section in Denmark | Denmark | Energinet | FID |  |  | Not availeble | 2015-09-01 | 2016-12-15 |  | 2018-06-11 | 2020-02-27 |  | 2017-12-21 | 2019-07-01 |  | 2017-10-31 |  | 2018-11-30 |  | 2020-03-10 | 2022-10-01 |  | 2022 | 2022 |  | On time
Pipeline including CS | TRA-F-814 | Upgrade for IP Deutschneudorf et al. for More Capacity | Germany | ONTRAS Gastransport GmbH | FID | 2016-01-01 | 2016-03-31 |  | 2017-07-01 | 2017-10-01 |  | 2017-10-01 | 2017-12-31 |  | 2018-01-01 | 2018-12-31 |  |  | irrelevant | 2018-12-31 |  | 2019-01-01 | 2023-12-31 |  | 2023 | 2023
LNG Terminal | LNG-F-824 | LNG Terminal in Klaipeda | Lithuania | AB Klaipėdos Nafta | FID | 2011-01-01 | 2017-11-13 |  | 2017-11-14 | 2018-04-10 |  | 2011-07-01 | 2012-03-01 |  | 2011-11-01 | 2012-10-22 |  | 2018-12-18 |  | 2018-12-18 |  |  |  | The Terminal constructions work have been completed on Oct. 27, 2014. This TYNPD submission aims at purchasing FSRU and extending commercial availability of the company. Therefore FID relates to The LNG Terminal act coming into force (Dec 18, 2018) and related commercial decisions. | 2024 | 2024 |  | On time
Pipeline including CS | TRA-F-895 | Balticconnector | Estonia | Elering AS | FID | 2000-01-01 | 2005-12-31 |  | 2006-01-01 | 2006-12-31 |  | 2016-01-01 | 2016-02-29 |  | 2012-12-02 | 2019-01-01 |  | 2018-05-01 |  | 2016-10-26 |  | 2017-11-30 | 2019-12-27 |  | 2019 | 2020 | 2016-10-21 | On time
Pipeline including CS | TRA-F-902 | Capacity increase at IP Lanžhot entry | Slovakia | eustream,a.s. (a joint-stock company) | FID | 2015-06-01 | 2015-06-30 |  | 2015-06-30 | 2015-10-31 |  | 2015-09-01 | 2017-07-31 |  | 2017-08-01 | 2018-02-28 |  | 2017-01-01 |  | 2017-12-12 |  | 2018-02-01 | 2019-11-30 |  | 2019 | 2019 |  | On time
Pipeline including CS | TRA-F-915 | Enhancement of Estonia-Latvia interconnection | Estonia | Elering AS | FID | 2000-01-01 | 2015-01-01 |  | 2015-01-01 | 2016-01-01 |  | 2015-05-01 | 2016-05-31 |  | 2015-09-01 | 2019-06-30 |  | 2018-02-07 |  | 2016-10-26 |  | 2018-06-17 | 2019-12-31 |  | 2019 | 2019 |  | On time
Pipeline including CS | TRA-F-918 | Capacity4Gas – CZ/SK | Czechia | NET4GAS, s.r.o. | FID | 2016-04-01 | 2017-04-10 |  |  |  | n/a | 2017-04-20 | 2018-06-30 |  | 2018-03-15 | 2018-08-15 |  | 2019-02-28 |  | 2017-03-07 |  | 2019-05-01 | 2019-12-31 |  | 2020 | 2020 |  | On time
Pipeline including CS | TRA-F-928 | Balticconnector Finnish part | Finland | Baltic Connector Oy | FID |  |  | Start date unknown, end date 31/12/2005. | 2006-01-01 | 2006-12-31 |  | 2016-01-01 | 2017-05-01 |  | 2012-12-02 | 2018-05-01 |  | 2017-10-16 |  | 2016-10-26 |  | 2017-12-01 | 2019-12-27 |  | 2019 | 2020 | 2016-10-21 | On time
Pipeline including CS | TRA-F-937 | Nord Stream 2 | Germany | Nord Stream 2 AG | FID |  |  | see No 150 | 2012-01-30 | 2012-10-08 |  |  |  | see No 150 and 152 |  |  | All construction permits except for Denmark received. Two additional route options provided for Denmark. Permit expected anytime soon. | 2016-12-31 |  | 2015-09-04 |  | 2018-02-01 | 2019-12-31 |  | 2019 | 2019 |  | On time
Pipeline including CS | TRA-F-941 | Metering and Regulating station at Nea Messimvria | Greece | DESFA S.A. | FID |  |  | DESFA decided that a pre-feasibility was not necessary. | 2016-01-30 | 2016-04-30 |  | 2016-05-04 | 2018-03-31 |  | 2018-02-28 | 2019-02-28 |  | 2019-09-20 |  | 2017-09-18 |  | 2019-09-20 | 2020-10-30 |  | 2020 | 2020 |  | On time
Pipeline including CS | TRA-F-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Germany | Gastransport Nord GmbH | FID | 2015-01-01 | 2016-01-01 |  | 2016-01-01 | 2017-01-01 |  | 2017-01-01 | 2018-01-01 |  | 2018-01-01 | 2019-01-01 |  | 2019-06-21 |  | 2018-04-09 |  | 2019-07-01 | 2019-12-15 |  | 2020 | 2027
Pipeline including CS | TRA-F-954 | TAG Reverse Flow | Austria | Trans Austria Gasleitung GmbH | FID |  |  | Pre-feasibility took place in 2018 |  |  | Feasibility phase took place in 2018 |  |  | FEED took place from end of 2018 and is about to be completed |  |  | Permitting phase will take place from end 2019 till beginning 2020 |  | project not basically driven by supply contracts | 2016-09-23 |  |  |  | Construction is currently expected to take place in 2020 | 2020 | 2020 |  | Delayed | Internal re-planning due to external constraints
Pipeline including CS | TRA-F-964 | New NTS developments for taking over gas from the Black Sea shore | Romania | SNTGN Transgaz SA | FID | 2016-04-28 | 2016-09-16 |  | 2016-10-24 | 2017-05-31 |  | 2017-08-01 | 2018-01-31 |  | 2017-03-01 | 2017-12-30 |  | 2018-10-31 |  | 2019-02-12 |  | 2019-03-01 | 2020-12-31 |  | 2021 | 2021 |  | Delayed
Pipeline including CS | TRA-N-1169 | Trans-Balkan Bi-directional Flow | Ukraine | JSC "UKRTRANSGAZ" | FID | 2018-07-01 | 2019-08-04 |  | 2019-08-05 | 2019-08-06 |  | 2019-08-05 | 2019-08-06 |  | 2019-08-07 | 2019-09-23 |  | 2019-09-23 |  | 2019-09-23 |  | 2019-10-01 | 2019-11-01 |  | 2020 | 2020
Pipeline including CS | TRA-F-1193 | TAP interconnection | Italy | Snam Rete Gas S.p.A. | FID |  |  | The projecyt feasebility has been studied before 2015 |  |  | The projecyt feasebility has been studied before 2015 | 2015-04-01 | 2018-05-01 |  | 2015-11-01 | 2018-05-01 |  | 2019-02-01 |  | 2018-05-29 |  | 2019-02-01 | 2020-10-31 |  | 2020 | 2020
Pipeline including CS | TRA-F-1241 | Interconnection with production in Gela | Italy | Snam Rete Gas S.p.A. | FID |  |  | Not applicable | 2017-01-02 | 2017-05-31 |  | 2017-09-28 | 2018-09-25 |  |  |  | Started 25/09/2018, but the permitting phase is still ongoing and it is forcasted for september 2019 |  | Supply is ongoing, but it isn't possible to make reference to a single supply contracts because the purchased items are buyed by aggragating more project needs. | 2017-09-01 |  | 2019-09-28 | 2020-04-01 |  | 2020 | 2020
Pipeline including CS | TRA-F-1254 | CS Elten | Germany | Open Grid Europe GmbH and Thyssengas GmbH | FID |  |  | info not available | 2018-10-01 | 2019-06-01 |  | 2017-07-01 | 2019-01-31 |  | 2019-10-01 | 2020-12-01 |  |  | info not available | 2016-03-01 |  | 2022-06-01 | 2022-11-01 |  | 2022 | 2022 |  | On time
Pipeline including CS | TRA-F-1267 | Upgrade Sülstorf station | Germany | NGT GmbH / GUD GmbH & Co. KG / Fluxys D GmbH | FID |  |  | completed |  |  | completed |  |  | completed |  |  | not necessary |  | current status | 2019-03-01 |  | 2019-06-01 | 2019-10-01 |  | 2019 | 2019 |  | On time
Pipeline including CS | TRA-F-1271 | Compressor Station Krummhoern | Germany | Open Grid Europe GmbH | FID |  |  | N/A |  |  | N/A | 2016-07-01 | 2019-06-28 |  | 2016-11-11 | 2019-06-28 |  |  | N/A | 2017-01-01 |  | 2017-06-12 | 2021-04-08 |  | 2022 | 2022
Pipeline including CS | TRA-F-1276 | Compressor station at Nea Messimvria (3rd unit) | Greece | DESFA S.A. | FID |  |  | DESFA did not need a pre-feasibility. | 2019-10-31 | 2019-01-31 |  | 2019-02-28 | 2019-10-31 |  | 2019-10-31 | 2020-09-30 |  | 2020-02-29 |  | 2019-06-28 |  | 2020-12-30 | 2022-09-30 |  | 2022 | 2022 |  | On time
Pipeline including CS | TRA-F-1277 | Upgrading GMS Isaccea 1 and GMS Negru Voda 1 | Romania | SNTGN Transgaz SA | FID |  |  | not available | 2018-01-01 | 2018-08-31 |  | 2018-01-01 | 2019-12-31 |  | 2018-01-01 | 2019-12-31 |  |  | Not available | 2018-12-18 |  | 2018-12-31 | 2020-12-31 |  | 2021 | 2021 |  | Delayed | Obtaining the necessary permits, agreements and approvals, extension of the duration of the tender procedures
Pipeline including CS | TRA-A-10 | Poseidon Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced |  |  | IGI Poseidon started the pre-fesability studied in 2002 | 2004-03-01 | 2006-10-01 |  | 2017-08-01 | 2019-01-01 |  | 2017-08-01 | 2019-06-01 |  |  | Market test to be perfomed | 2019-06-01 |  | 2020-03-01 | 2022-09-01 |  | 2022 | 2025 |  | On time
Pipeline including CS | TRA-A-12 | GALSI Pipeline Project | Italy | Galsi S.p.A. | Advanced |  |  | Start date not available END: 31/12/2006 | 2006-01-01 | 2006-12-31 |  | 2007-01-01 | 2010-12-31 |  | 2008-07-31 | 2018-11-30 |  | 2020-11-30 |  | 2020-11-30 |  | 2020-12-01 | 2022-12-31 |  | 2022 | 2022 | 2010-08-13 | On time
Pipeline including CS | TRA-A-21 | Bidirectional Austrian-Czech Interconnector (BACI) | Austria | GAS CONNECT AUSTRIA GmbH | Advanced | 2013-07-01 | 2014-01-14 |  |  |  | not applicable |  |  | not applicable | 2021-04-01 | 2021-09-01 |  | 2021-11-01 |  | 2021-07-01 |  | 2022-01-01 | 2024-05-01 |  | 2024 | 2024 | 2015-04-30 | Rescheduled | According to the footnote of the 3rd PCI list the implementation of BACI as a PCI is conditional upon the outcome of the pilot project ‘Trading Regional Upgrade" (TRU). Currently the one-year long pilot phase of TRU service is ongoing. The commissioning year (and the entire time-schedule was changed to 2024.
LNG Terminal | LNG-A-30 | Shannon LNG Terminal and Connecting Pipeline | Ireland | Shannon LNG Ltd | Advanced | 2005-01-01 | 2006-05-01 |  | 2006-05-01 | 2007-09-01 |  | 2020-01-01 | 2020-06-30 |  | 2007-09-01 | 2020-01-31 |  | 2020-10-01 |  | 2020-03-31 |  | 2020-04-01 | 2022-06-30 |  | 2022 | 2029 |  | Rescheduled | Previously we indicated a construction complete date of 1/4/2022. We are currently revising this with engineers and our current estimate is 30/6/2022
Pipeline including CS | TRA-A-31 | Melita TransGas Pipeline | Malta | Melita TransGas Co. Ltd. | Advanced | 2013-04-09 | 2015-04-30 |  | 2013-04-09 | 2015-04-30 |  | 2018-11-01 | 2020-03-01 |  | 2017-11-20 | 2020-07-01 |  | 2021-10-01 |  | 2020-07-01 |  | 2023-03-01 | 2024-05-01 |  | 2024 | 2024 | 2018-01-25 | On time
LNG Terminal | LNG-A-32 | Project GO4LNG LNG terminal Gothenburg | Sweden | Swedegas AB | Advanced | 2011-10-01 | 2012-01-01 |  | 2012-01-01 | 2012-06-01 |  | 2020-01-01 | 2020-05-01 |  | 2013-10-01 | 2014-05-01 |  | 2020-05-01 |  | 2020-06-01 |  | 2020-06-01 | 2023-04-01 |  | 2022 | 2022 |  | Delayed | Delayed because of market development is slower than expected. Discussions on-going with key potential players.
LNG Terminal | LNG-A-50 | Gate terminal phase 3 | Netherlands | Gate | Advanced | 2010-06-01 | 2010-06-01 |  | 2018-06-01 | 2018-06-01 |  | 2020-06-01 | 2020-06-01 |  | 2009-06-01 | 2009-06-01 |  | 2020-06-01 |  | 2020-06-01 |  | 2020-06-01 | 2022-06-01 |  | 2022 | 2024 | 2007-12-31 | Delayed | more time for the market to develop and finalise commercial discussions.
LNG Terminal | LNG-A-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Greece | Gastrade S.A. | Advanced | 2010-09-01 | 2010-12-01 |  | 2014-01-01 | 2014-06-01 |  | 2017-03-10 | 2017-09-29 |  | 2010-12-01 | 2015-01-20 |  |  | Supply contracts will be concluded after completion of the tenders for the construction of the project (4Q 2019). | 2020-03-31 |  | 2020-04-01 | 2021-10-31 |  | 2022 | 2022 | 2015-04-16 | Delayed | Permitting phase completed 1Q2015 and FEED completed in Sept. 2017. Final negotiations with Bulgartransgaz and Public Gas Corporation (DEPA) for acquiring stakes in GASTRADE is estimated to be completed by 3Q2019. GASTRADE initiated a Market Test in October 2018 and critical mass terminal use agreements are anticipated by Oct.2019. The first phase of the Market Test (EoI) was successfully completed on 31.12.2018 where 20 participants from SEE Europe & beyond expressed their interest for booking up to 12.2 bcm/y regasification capacity. Completion of financing agreements and EPC contract awards (subject to FID) required for FID. GASTRADE initiated on 21.09.2018 the Tendering procedure for the supply of the FSRU and for the EPCI of the pipeline. The first phase of the Tenders (Pre-qualification and EoI) was completed in April 2019. Evaluation procedure has been concluded and second phase of the Tender (RfP) will launch in Q3 2019. FID is planned for 1Q 2020 & COD 1Q 2022.
Pipeline including CS | TRA-A-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Greece | Gastrade S.A. | Advanced | 2010-09-01 | 2010-12-01 |  | 2014-01-01 | 2014-06-01 |  | 2017-03-10 | 2017-09-29 |  | 2010-12-01 | 2015-01-20 |  |  | Supply contracts will be concluded after completion of the tenders for the construction of the project (4Q 2019). | 2020-03-31 |  | 2020-04-01 | 2021-10-31 |  | 2022 | 2022 | 2015-04-16 | Delayed | Permitting phase completed 1Q2015 and FEED completed in Sept. 2017. Final negotiations with Bulgartransgaz and Public Gas Corporation (DEPA) for acquiring stakes in GASTRADE is estimated to be completed by 3Q2019. GASTRADE initiated a Market Test in October 2018 and critical mass terminal use agreements are anticipated by Oct.2019. The first phase of the Market Test (EoI) was successfully completed on 31.12.2018 where 20 participants from SEE Europe beyond expressed their interest for booking up to 12.2 bcm/y regasification capacity. Completion of financing agreements and EPC contract awards (subject to FID) required for FID. GASTRADE initiated on 21.09.2018 the Tendering procedure for the supply of the FSRU and for the EPCI of the pipeline. The first phase of the Tenders (Pre-qualification and EoI) was completed in April 2019. Evaluation procedure has been concluded and second phase of the Tender (RfP) will launch in Q3 2019. FID is planned for 1Q 2020 and COD for 1Q 2022.
Energy Transition Related Project | ETR-A-64 | Biomethane reverse flow Denmark | Denmark | Energinet | Advanced |  |  | Integrated in the feasibility study | 2018-08-01 | 2019-09-30 |  | 2019-02-01 | 2019-09-30 |  | 2019-06-27 | 2021-04-01 |  | 2020-01-01 |  | 2019-09-11 |  | 2021-04-01 | 2021-04-01 |  | 2021 | 2021
Pipeline including CS | TRA-A-68 | Ionian Adriatic Pipeline | Croatia | Plinacro Ltd | Advanced | 2007-01-01 | 2008-01-01 |  | 2012-05-01 | 2014-02-01 |  | 2017-01-01 | 2023-01-01 |  | 2009-07-21 | 2023-01-01 |  | 2022-01-01 |  | 2022-01-01 |  | 2022-01-01 | 2025-01-01 |  | 2023 | 2025 |  | Rescheduled | Dynamics of project implementation depends on the dynamics of TAP project implementation.
Pipeline including CS | TRA-A-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Croatia | Plinacro Ltd | Advanced |  |  | It is not necessary | 2021-01-01 | 2021-01-01 |  | 2021-01-01 | 2025-01-01 |  | 2010-01-12 | 2025-01-01 |  | 2022-01-01 |  | 2022-01-01 |  | 2022-01-01 | 2027-01-01 |  | 2023 | 2027 |  | Rescheduled
LNG Terminal | LNG-A-79 | Paldiski LNG Terminal | Estonia | Balti Gaas plc | Advanced | 2008-01-01 | 2008-11-01 |  | 2012-01-01 | 2016-01-29 |  | 2013-04-01 | 2014-04-24 |  | 2008-01-14 | 2017-06-12 |  | 2024-01-01 |  | 2022-01-01 |  | 2022-11-01 | 2025-12-31 |  | 2025 | 2025 |  | Rescheduled | The project is technically ready for construction, but no FID can be taken before the competing projects and govermental aid issues are solved (political decision regarding regional LNG terminal and potential financial aid to it).
Pipeline including CS | TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla) | Croatia | Plinacro Ltd | Advanced |  |  | It is not necesarry | 2014-09-01 | 2014-12-01 |  | 2018-06-01 | 2019-12-01 |  | 2015-10-14 | 2019-12-01 |  | 2020-01-01 |  | 2020-01-01 |  | 2020-01-01 | 2023-01-01 |  | 2021 | 2023 | 2016-04-25 | Rescheduled
Pipeline including CS | TRA-A-123 | Városföld CS | Hungary | FGSZ Ltd. | Advanced | 2014-03-01 | 2014-06-30 |  | 2016-09-01 | 2017-07-31 |  | 2019-12-01 | 2020-01-31 |  | 2020-02-01 | 2020-08-30 |  | 2020-05-01 |  | 2019-10-31 |  | 2020-09-01 | 2022-12-31 |  | 2022 | 2022 | 2016-10-14 | On time
Pipeline including CS | TRA-A-133 | Bidirectional Austrian Czech Interconnection (BACI) | Czechia | NET4GAS, s.r.o. | Advanced | 2003-03-01 | 2009-05-01 |  | 2012-03-01 | 2014-02-01 |  | 2012-03-01 | 2020-10-22 |  | 2015-05-01 | 2021-10-01 |  | 2021-11-04 |  |  | n/a | 2023-01-01 | 2024-04-01 |  | 2024 | 2024 | 2015-04-30 | Rescheduled
Pipeline including CS | TRA-A-136 | Czech-Polish Gas Interconnector (CPI) | Czechia | NET4GAS, s.r.o. | Advanced | 2009-01-01 | 2011-08-01 |  | 2009-01-01 | 2012-12-31 |  | 2014-11-01 | 2017-10-31 |  | 2016-02-01 | 2021-09-30 |  | 2021-11-26 |  |  | n/a | 2021-07-30 | 2023-08-31 |  | 2023 | 2023 | 2018-05-02 | Delayed | The delay was caused by lengthy permitting processes.
Storage Facility | UGS-A-138 | Balkan Gas Hub - UGS Chiren Expansion | Bulgaria | Bulgartransgaz EAD | Advanced | 2009-05-19 | 2011-06-01 |  | 2015-03-02 | 2020-03-02 |  | 2022-02-28 | 2024-01-31 |  | 2021-06-30 | 2024-02-28 |  | 2022-02-28 |  | 2021-04-30 |  | 2022-07-31 | 2025-06-28 |  | 2025 | 2025 | 2015-10-23 | Delayed | Commissioning: 2025 The delay of the overall PCI implementation is due to delay in the in the implementation of 3D seismic studies. The reasons are that within the tender procedure, the Selection Decision was appealed by one of the bidders and that hindered its successful completion. In the mean time new standard templates for tender procedures were approved by the Bulgarian Ministry of Finance, which from our side let to delay in the preparation of new tender documentation for the 3D seismic studies tendering, which afterwards needed to be re-launch. Another reason is delay in the process of granting access to the lands / propertis within the survey area, due to difficulties in obtaining Right of Way Agreements from the users of agricultural properties to perform seismic activities.
Pipeline including CS | TRA-A-161 | South Transit East Pyrenees (STEP) - ENAGAS | Spain | Enagas Transporte S.A.U. | Advanced | 2007-01-01 | 2007-01-01 |  | 2007-01-01 | 2007-01-01 |  | 2016-01-01 | 2016-12-31 |  | 2016-06-01 | 2022-03-01 |  |  | Not applicable | 2020-09-01 |  | 2022-07-01 | 2023-11-30 |  | 2024 | 2024 | 2018-01-25 | Rescheduled | The Agency has not yet published its decision Depending on ACER´s decision, the project configuration could be modified
Storage Facility | UGS-A-233 | Depomures | Romania | Engie Romania SA | Advanced | 2004-01-05 | 2004-06-01 |  | 2008-06-01 | 2009-06-01 |  | 2011-06-01 | 2012-06-01 |  | 2012-06-01 | 2017-09-26 |  | 2016-08-09 |  | 2019-12-31 |  | 2020-01-01 | 2024-03-01 |  | 2021 | 2024 |  | Delayed | The main delay encountered is related to permit granting for part of the investment (i.e. the last sector of the main gathering pipeline). The construction of the main gathering pipeline was essential for the entire project and a pre-requisite for implementing the rest of the project (dehydration and compression station and subsequent expansion to 600 mcm of the capacity). The permit was eventually obtained in September 2017. In addition, the lack of visibility and certainty on tariff methodology represents an important drawback when it comes for taking the FID and obtaining the necessary financing sources.
Pipeline including CS | TRA-A-252 | South Transit East Pyrenees (STEP) - TEREGA | France | TEREGA | Advanced |  |  | Since then the Feasibility study is already completed. This information is not relevant anymore. | 2016-01-04 | 2017-01-31 |  | 2016-01-19 | 2020-12-31 |  | 2018-06-17 | 2022-12-31 |  |  | based on the CBCA decision | 2020-11-30 |  | 2022-10-03 | 2024-09-30 |  | 2024 | 2024 | 2016-01-19 | Rescheduled | Project deadline planed on the 31/12/2024 due to the recent (21/06/2019) ACER's decision regarding the CBCA.
Pipeline including CS | TRA-A-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | Poland | GAZ-SYSTEM S.A. | Advanced |  |  | N/A | 2016-03-15 | 2017-01-10 |  | 2017-08-03 | 2019-11-25 |  | 2017-08-03 | 2020-04-24 |  |  | N/A | 2018-11-30 |  | 2020-04-01 | 2022-09-30 |  | 2022 | 2022 | 2019-04-15 | On time
Pipeline including CS | TRA-A-273 | Poland - Czech Republic Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | Advanced |  |  | N/A |  |  | N/A | 2015-07-28 | 2017-12-22 |  | 2016-07-19 | 2017-12-29 |  |  | N/A |  | To be agreed |  |  | To be agreed | 2023 | 2023
Pipeline including CS | TRA-A-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | Portugal | REN-Gasodutos, S.A. | Advanced | 2015-01-01 | 2015-03-31 |  | 2019-07-01 | 2020-04-30 |  | 2020-08-01 | 2021-07-31 |  | 2021-05-01 | 2024-10-31 |  | 2023-10-01 |  | 2023-05-01 |  | 2024-10-01 | 2025-12-31 |  | 2025 | 2025 | 2015-07-14 | Rescheduled | In the last edition of the TYNDP, REN was in the permitting process phase, waiting for the Environmental Impact Declaration to be issued by the Competent Authorities. At this moment, REN already received the declaration with a unfavorable decision. As a consequence,it will be necessary to make an adjustment to the initial route, maintaining the same point of interconnection with Spain. Furthermore, the project of the 3rd Interconnection between Portugal and Spain was rescheduled due to the activities that are being developed in the High Level Group for the development of the interconnections between France, Spain and Portugal. It’s important to notice that the Portuguese project has its decision dependent on the STEP project’s decision.
Storage Facility | UGS-A-294 | Islandmagee Gas Storage Facility | United Kingdom | Islandmagee Storage Limited | Advanced |  |  | This work has successfully completed. |  |  | This work has successfully completed. | 2018-01-15 | 2018-12-20 |  |  |  | PCI 5.1.3 has a grant of planning permission for above ground elements & drilling has confirmed suitable geology for gas storage. Further final approvals/engagement will be required from/with the RA & Government Departments before construction can commence. | 2019-06-28 |  | 2019-09-30 |  | 2019-10-01 | 2022-05-03 |  | 2022 | 2026 | 2016-06-17 | Rescheduled | ​The project has been rescheduled due to the availability of finance and the difficult trading conditions within the UK gas market.
LNG Terminal | LNG-A-295 | Mugardos LNG Terminal: Send-out Increase | Spain | Reganosa | Advanced | 2017-04-10 | 2018-02-09 |  | 2017-04-10 | 2018-02-09 |  | 2018-11-19 | 2020-02-07 |  | 2020-06-01 | 2021-05-14 |  |  | This phase is not scheduled for this project | 2021-05-14 |  | 2021-09-06 | 2024-03-15 |  | 2024 | 2024 |  | Rescheduled
LNG Terminal | LNG-A-296 | Mugardos LNG Terminal: 2nd Jetty | Spain | Reganosa | Advanced | 2015-02-11 | 2015-12-15 |  | 2015-02-11 | 2015-12-15 |  | 2016-04-06 | 2017-06-27 |  | 2021-04-28 | 2022-03-29 |  |  | This phase is not scheduled for this project | 2022-03-29 |  | 2022-06-22 | 2024-07-02 |  | 2024 | 2024 |  | Rescheduled
Pipeline including CS | TRA-A-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Croatia | Plinacro Ltd | Advanced | 2013-04-09 | 2013-09-01 |  | 2017-07-03 | 2018-05-31 |  | 2021-06-01 | 2022-05-31 |  | 2014-08-25 | 2022-05-31 |  | 2022-09-01 |  | 2022-06-01 |  | 2022-10-03 | 2023-12-29 |  | 2023 | 2023 |  | Rescheduled
Energy Transition Related Project | ETR-A-312 | P2G Velke Kapusany | Slovakia | NAFTA a.s. (joint stock company) | Advanced | 2018-12-01 | 2019-08-01 |  | 2019-09-01 | 2020-01-01 |  | 2020-02-01 | 2021-04-01 |  | 2017-11-01 | 2021-04-01 |  | 2020-09-01 |  | 2020-01-01 |  | 2021-06-01 | 2023-06-01 |  | 2023 | 2023 |  | Not applicable
Pipeline including CS | TRA-A-320 | Carregado Compressor Station | Portugal | REN-Gasodutos, S.A. | Advanced | 2008-09-01 | 2010-01-01 |  | 2008-09-01 | 2010-01-01 |  | 2010-08-01 | 2010-11-01 |  | 2014-02-25 | 2016-07-06 |  | 2023-10-01 |  | 2023-05-01 |  | 2024-01-01 | 2025-12-31 |  | 2025 | 2025 |  | Rescheduled | The investment in this infrastructure should be decided in future NDP. The schedule of this project is aligned and is a enabler of the PCI project 5.4 - 3rd interconnection between Portugal and Spain (TRA-N-283), which in turn is dependent on STEP's decision.
Pipeline including CS | TRA-A-330 | EastMed Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | 2011-01-01 | 2014-01-01 |  | 2015-05-01 | 2018-03-31 |  | 2018-11-01 | 2021-12-31 |  | 2019-06-30 | 2021-12-01 |  |  | Currently the detailed design (FEED) and marine survey activities for EastMed are being prepared/carried out, including all the engineering details for project implementation, as well as permitting activities in Cyprus and Greece. | 2021-12-01 |  | 2021-12-01 | 2024-12-31 |  | 2025 | 2025 | 2018-01-25 | On time | The project's development activities are on time. Compared to the previous TYNDP application, the date of FID has been corrected from 06 2021, to 12 2021 and the formal start of the permitting phase, according to Article 10 of Regulation 347/2013 adjusted. The overall project schedule remains unaffected.
Pipeline including CS | TRA-A-339 | Trans-Caspian | Turkmenistan | W-Stream Caspian Pipeline Company OU | Advanced | 2010-01-01 | 2013-01-01 |  | 2018-05-01 | 2020-04-30 |  | 2020-04-01 | 2020-12-30 |  | 2019-08-01 | 2020-12-30 |  | 2021-06-01 |  | 2021-01-01 |  | 2021-04-01 | 2022-09-01 |  | 2022 | 2023 | 2018-01-25 | Rescheduled | The progress of the Trans Caspian Pipeline system was not that fast as previously expected because of lack of clarity regarding legal status of the Caspian Sea. Since the signature of the Caspian Sea convention - signed mid of 2018 - the perceived risks by potential investors has decreased, subsequently interest in the Trans Caspian Pipeline system has increased. Nevertheless, it takes some time to fully built up the necessary confidence of investors consequently it will be difficult to catch up regarding initial time schedule to the full extend, thus a rescheduling of the Trans Caspian Pipeline was advisable.
Pipeline including CS | TRA-A-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | Lithuania | AB Amber Grid | Advanced |  |  | Pre-Feasibility Study has not been carried out. | 2017-10-06 | 2018-09-30 |  | 2018-09-30 | 2019-04-30 |  | 2019-05-01 | 2020-01-01 |  | 2023-04-30 |  | 2020-10-31 |  | 2020-10-31 | 2023-04-30 |  | 2023 | 2023 |  | Rescheduled | Referring to the results of the Feasibility study for the project (carried out in 2018) the project's implementation time shedule has been adjusted accordingly.
Storage Facility | UGS-A-356 | Underground Gas Storage Velke Kapusany | Slovakia | NAFTA a.s. (joint stock company) | Advanced | 2017-09-01 | 2017-11-01 |  | 2019-04-01 | 2019-09-01 |  | 2020-02-01 | 2021-04-01 |  | 2017-11-01 | 2021-04-01 |  | 2020-09-01 |  | 2020-01-01 |  | 2021-06-01 | 2023-06-01 |  | 2023 | 2023 |  | On time
Pipeline including CS | TRA-A-362 | Development on the Romanian territory of the Southern Transmission Corridor | Romania | SNTGN Transgaz SA | Advanced | 2014-01-01 | 2014-06-30 |  | 2014-07-01 | 2016-01-30 |  | 2016-06-01 | 2018-02-28 |  | 2015-01-01 | 2018-05-30 |  |  | Info not available. | 2019-12-31 |  | 2019-12-31 | 2021-12-01 |  | 2021 | 2021 |  | Delayed | Because of the postponement of the final investment decision of the titleholders of the Black Sea blocks
Pipeline including CS | TRA-A-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | Hungary | FGSZ Ltd. | Advanced | 2014-03-01 | 2014-06-30 |  | 2016-09-01 | 2017-07-31 |  | 2019-12-01 | 2020-01-31 |  | 2020-02-01 | 2020-08-30 |  | 2020-05-01 |  | 2019-10-31 |  | 2020-09-01 | 2022-12-31 |  | 2022 | 2022 | 2016-04-27 | On time
Pipeline including CS | TRA-A-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | Latvia | JSC "Conexus Baltic Grid" | Advanced |  |  | There was no prefeasibility study, only feasibility study | 2017-10-06 | 2018-09-30 |  | 2018-06-30 | 2020-12-31 |  | 2018-06-30 | 2022-06-30 |  | 2022-08-31 |  | 2020-01-05 |  | 2020-01-05 | 2023-06-30 |  | 2023 | 2023 | 2018-03-30 | Rescheduled
Pipeline including CS | TRA-A-394 | Norwegian tie-in to Danish upstream system | Denmark | Energinet.dk | Advanced |  |  | Not available | 2015-09-01 | 2016-12-15 |  | 2018-05-01 | 2022-02-27 |  | 2018-01-01 | 2019-07-01 |  | 2017-10-31 |  | 2018-12-01 |  | 2020-01-01 | 2022-10-01 |  | 2022 | 2022 |  | On time
Pipeline including CS | TRA-A-408 | Wilhelmshaven LNG-Terminal Anbindungsleitung | Germany | Open Grid Europe GmbH | Advanced |  |  | No information available. | 2018-10-01 | 2019-03-27 |  | 2019-02-04 | 2019-11-29 |  | 2019-12-02 | 2020-12-21 |  |  | to be defined | 2020-12-21 |  | 2021-06-01 | 2022-10-31 |  | 2022 | 2022
Pipeline including CS | TRA-A-429 | Adaptation L- gas - H-gas | France | GRTgaz and Storengy | Advanced | 2014-06-01 | 2016-09-30 |  | 2014-06-01 | 2016-09-30 |  | 2015-09-01 | 2020-09-30 |  | 2016-11-01 | 2026-12-31 |  |  | na | 2016-06-01 |  | 2017-04-01 | 2026-12-31 |  | 2025 | 2025 |  | On time
Energy Transition Related Project | ETR-A-430 | Porthos | Netherlands | N.V. Nederlandse Gasunie | Advanced | 2018-02-01 | 2018-02-01 |  | 2018-04-01 | 2018-04-01 |  | 2019-04-01 | 2020-12-31 |  | 2020-01-01 | 2021-07-01 |  | 2020-01-01 |  | 2020-12-31 |  | 2021-10-01 | 2023-04-01 |  | 2023 | 2023
Energy Transition Related Project | ETR-A-437 | Supercritical water gasification facilities | Netherlands | N.V. Nederlandse Gasunie | Advanced | 2017-01-01 | 2018-12-31 |  | 2018-01-01 | 2019-06-23 |  | 2019-07-01 | 2020-12-31 |  | 2019-01-01 | 2020-12-31 |  | 2021-01-01 |  | 2020-07-01 |  | 2021-01-01 | 2023-12-31 |  | 2021 | 2021
Pipeline including CS | TRA-A-496 | Increase of Gas Transport to the Netherlands | Germany | Gasunie Deutschland Transport Service GmbH | Advanced |  |  | The pre feassibility studies were overteaken from similar projects from the past. There were plans to increase the capacity towards NL since 2015 | 2017-01-01 | 2017-01-01 |  | 2017-01-01 | 2018-01-01 |  | 2018-01-01 | 2019-01-01 |  |  | Not decided yet |  | Not decided yet |  |  | Not decided yet | 2022 | 2022
Energy Transition Related Project | ETR-A-504 | Sun2Hy | Spain | Enagas S.A. | Advanced | 2018-06-01 | 2018-12-30 |  | 2019-01-01 | 2020-12-31 |  | 2019-01-01 | 2019-12-30 |  | 2019-09-01 | 2020-01-30 |  |  | No applicable |  | No data | 2020-01-01 | 2023-12-31 |  | 2023 | 2023
Energy Transition Related Project | ETR-A-519 | Hub Baleares | Spain | Enagas S.A. | Advanced | 2019-02-13 | 2019-05-24 |  | 2019-10-22 | 2019-01-15 |  | 2019-01-15 | 2019-03-20 |  | 2019-10-10 | 2021-07-28 |  | 2023-01-01 |  | 2019-12-01 |  | 2021-01-01 | 2023-01-01 |  | 2023 | 2023
Pipeline including CS | TRA-A-561 | Poland-Ukraine Interconnector (Ukrainian section) | Ukraine | PJSC UKRTRANSGAZ | Advanced | 2015-12-01 | 2016-02-29 |  | 2015-01-01 | 2016-12-31 |  | 2016-12-01 | 2018-07-31 |  | 2016-12-01 | 2018-09-30 |  |  | tbd |  | tbd | 2018-08-01 | 2020-03-31 |  | 2022 | 2022
Pipeline including CS | TRA-A-621 | Poland - Ukraine Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | Advanced |  |  | N/A |  |  | N/A | 2016-09-01 | 2019-06-16 |  | 2016-10-11 | 2019-02-19 |  |  | N/A |  | To be agreed |  |  | To be agreed | 2022 | 2022 |  |  | The dialogue between the TSOs of both countries is ongoing in order to establish grounds for taking the positive FID for implementation of the PL-UA interconnection. Therefore, launching of the construction works is postponed until the FID is taken.
Pipeline including CS | TRA-A-628 | Eastring - Slovakia | Slovakia | eustream, a.s. (a joint stock company) | Advanced | 2015-01-01 | 2016-08-31 |  | 2017-09-01 | 2018-09-14 |  | 2019-01-01 | 2020-08-12 |  | 2021-11-18 | 2022-06-01 |  | 2021-01-24 |  | 2020-09-09 |  | 2023-02-09 | 2025-01-28 |  | 2025 | 2030 | 2017-05-12 | Delayed | Time schedule in the last TYNDP was estimated according to the data from the pre-feasibility study with lower level of details.
Pipeline including CS | TRA-A-654 | Eastring - Bulgaria | Bulgaria | Bulgartransgaz EAD | Advanced | 2015-01-01 | 2016-08-31 |  | 2017-09-01 | 2018-09-14 |  | 2019-01-01 | 2020-08-12 |  | 2020-03-01 | 2020-06-30 |  | 2020-01-31 |  | 2020-09-30 |  | 2023-02-01 | 2025-04-30 |  | 2025 | 2030 | 2017-05-12 | Delayed | Time schedule in the last TYNDP was estimated according to the data from the pre-feasibility study with lower level of details.
Pipeline including CS | TRA-A-655 | Eastring - Romania | Romania | SNTGN Transgaz SA | Advanced | 2015-01-01 | 2016-08-01 |  | 2017-09-01 | 2018-09-01 |  | 2019-01-01 | 2020-08-12 |  | 2021-11-18 | 2022-06-01 |  | 2021-01-24 |  | 2020-09-09 |  | 2023-02-09 | 2025-01-28 |  | 2025 | 2030 |  | Delayed | Time schedule in the last TYNDP was estimated according to the data from the pre-feasibility study with lower level of details.
Pipeline including CS | TRA-A-656 | Eastring - Hungary | Hungary | FGSZ Ltd. | Advanced | 2015-01-01 | 2016-08-31 |  | 2017-09-01 | 2018-06-30 |  | 2019-01-01 | 2020-08-12 |  | 2021-11-18 | 2022-06-01 |  | 2021-01-24 |  | 2020-09-09 |  | 2023-02-09 | 2025-01-28 |  | 2025 | 2030 | 2017-05-12 | Delayed | Time schedule in the last TYNDP was estimated according to the data from the pre-feasibility study with lower level of details.
Pipeline including CS | TRA-A-782 | TANAP X- Expansion of Trans Anatolian Natural Gas Pipeline Projec | Turkey | SOCAR (The State Oil Company of the Azerbaijan Republic) | Advanced | 2021-05-17 | 2021-08-17 |  | 2021-08-18 | 2021-12-29 |  | 2022-01-02 | 2022-05-10 |  | 2022-05-01 | 2022-07-26 |  | 2022-09-13 |  | 2022-12-13 |  | 2023-02-01 | 2025-12-15 |  | 2025 | 2025 | 2016-03-01 | On time
Pipeline including CS | TRA-A-808 | Additional transport of gas volumes to the Netherlands | Germany | Gasunie Deutschland Transport Services GmbH | Advanced |  |  | The pre feasibility studies were taken from similar projects from the past. There were plans to increase the capacity towards NL since 2015 | 2017-01-01 | 2017-01-01 |  | 2017-01-01 | 2018-01-01 |  | 2018-01-01 | 2019-07-01 |  |  | Not planned yet. For planning the projects have to be confirmed by the NRA which is decided after the anual auction in July 2019 |  | Not scheduled yet. For planning the projects have to be confirmed by the NRA which is decided after the anual auction in July 2019 |  |  | Not scheduled yet. For planning the projects have to be confirmed by the NRA which is decided after the anual auction in July 2019 | 2025 | 2025 |  | On time
Pipeline including CS | TRA-A-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | Ireland | Gas Networks Ireland | Advanced | 2017-06-22 | 2018-11-28 |  | 2017-06-22 | 2018-11-28 |  | 2020-06-01 | 2020-12-31 |  | 2021-01-01 | 2021-12-31 |  | 2021-06-30 |  | 2021-12-31 |  | 2022-01-01 | 2022-12-31 |  | 2022 | 2022 | 2017-03-14 | Rescheduled | Results and recommendations from the feasibility study were communicated to stakeholders and industry in Q1 2019.The project can now progress into FEED stage. The FEED commencement date has been adjusted by 12 months to allow sufficient time to progress an application to the next CEF call for proposals.
Pipeline including CS | TRA-A-950 | Guitiriz - Lugo - Zamora pipeline | Spain | Reganosa | Advanced | 2017-07-31 | 2017-12-01 |  | 2017-07-31 | 2017-12-01 |  | 2017-12-04 | 2019-01-25 |  | 2020-10-05 | 2021-10-15 |  |  | This phase is not scheduled for this project. | 2021-10-15 |  | 2021-10-18 | 2024-01-19 |  | 2024 | 2024 |  | Rescheduled
Pipeline including CS | TRA-A-951 | Embedding CS Folmhusen in H-Gas | Germany | Gasunie Deutschland Transport Services GmbH | Advanced | 2015-01-01 | 2015-01-01 |  | 2015-01-01 | 2015-01-01 |  | 2016-01-01 | 2016-12-01 |  |  |  | Not decided yet |  | Not decided yet |  | Not decided yet |  |  | Not decided yet | 2020 | 2020 |  | On time
LNG Terminal | LNG-A-962 | Tallinn LNG | Estonia | Liwathon E.O.S. AS / Port of Tallinn AS | Advanced | 2012-02-01 | 2012-09-12 |  | 2012-02-01 | 2012-09-12 |  | 2016-01-01 | 2020-01-31 |  | 2012-01-01 | 2017-03-27 |  | 2021-08-01 |  | 2020-02-06 |  | 2020-04-01 | 2022-12-31 |  | 2022 | 2022 | 2020-02-06 | Delayed | The project is delayed because of the uncertainty and delay in other former LNG Terminal projects in the region, as this affects the project scope, feasibility, FEED and FID.
Pipeline including CS | TRA-A-967 | Nea-Messimvria to Evzoni/Gevgelija pipeline (IGNM) | Greece | DESFA S.A. | Advanced |  |  | DESFA found that pre-feasibility is not necessary | 2017-03-30 | 2019-01-30 |  | 2019-03-30 | 2019-11-30 |  | 2018-12-30 | 2020-03-30 |  | 2020-10-30 |  | 2020-06-18 |  | 2020-12-30 | 2022-09-30 |  | 2022 | 2022 |  | Rescheduled | The condition imposed by the Regulator for the approval of the inclusion of the project iin the NDP (i.e. the execution of a successful Market Test) had as a consequence a delay for the drafting of the relevant Guidelines and Notice and for the alignement betwenn the two gas transmission companies.
Pipeline including CS | TRA-A-980 | Interconnection North Macedonia-Greece (North Macedonian part) | North Macedonia | MER JSC Skopje | Advanced |  |  | MER proceeded directly to the feasibility phase | 2017-03-30 | 2019-01-30 |  | 2019-03-29 | 2019-12-13 |  | 2018-12-30 | 2020-03-30 |  | 2020-10-30 |  | 2020-06-18 |  | 2020-12-30 | 2022-09-30 |  | 2022 | 2022 |  | Rescheduled
LNG Terminal | LNG-A-1146 | Cyprus Gas2EU | Cyprus | Ministry of Energy, Commerce and Industry (MECI) | Advanced | 2015-11-15 | 2017-02-15 |  | 2017-04-14 | 2017-10-16 |  | 2017-05-02 | 2018-09-01 |  | 2019-10-30 | 2022-01-31 |  | 2022-01-31 |  | 2019-11-01 |  | 2019-11-02 | 2022-03-31 |  | 2022 | 2022 | 2018-01-25 | On time
Pipeline including CS | TRA-A-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | Poland | GAZ-SYSTEM S.A. | Advanced |  |  | N/A | 2016-03-15 | 2017-01-10 |  | 2017-12-15 | 2020-02-19 |  | 2017-12-15 | 2020-01-07 |  |  | N/A | 2018-11-30 |  | 2020-08-11 | 2022-09-30 |  | 2022 | 2022 | 2019-04-15
LNG Terminal | LNG-A-1198 | LNG Terminal Brunsbuettel | Germany | GermanLNG Terminal GmbH | Advanced | 2016-01-01 | 2016-12-31 |  | 2017-01-01 | 2018-03-31 |  | 2018-04-01 | 2019-06-01 |  | 2019-08-31 | 2020-10-01 |  | 2019-12-31 |  | 2019-12-31 |  | 2020-10-01 | 2023-05-31 |  | 2023 | 2023 |  | On time
Pipeline including CS | TRA-A-1199 | LNG Terminal Brunsbuettel - Grid Integration | Germany | Gasunie Deutschland Transport Service GmbH | Advanced | 2018-01-01 | 2018-07-01 |  | 2018-07-01 | 2019-03-01 |  | 2019-04-01 | 2020-06-01 |  | 2020-07-01 | 2021-08-01 |  | 2020-01-01 |  | 2020-10-01 |  | 2021-08-01 | 2022-10-01 |  | 2023 | 2023
Pipeline including CS | TRA-A-1268 | Romania-Serbia Interconnection | Romania | SNTGN Tranzgaz SA | Advanced | 2017-07-01 | 2018-02-28 |  | 2018-02-28 | 2018-11-30 |  | 2018-03-31 | 2019-01-31 |  | 2018-03-31 | 2019-10-01 | [8 empty] | 2020 | 2020 |  | On time
Pipeline including CS | TRA-A-1303 | IAEF - Vlora ccgt | Albania | Albgaz Sha | Advanced | 2016-03-08 | 2017-02-08 |  | 2017-03-08 | 2018-02-01 |  | 2018-09-06 | 2018-09-06 |  | 2018-11-14 | 2019-03-12 |  | 2019-06-06 |  | 2019-09-12 |  | 2019-11-14 | 2020-11-28 |  | 2020 | 2020 | 2016-01-28 | On time
Pipeline including CS | TRA-A-1322 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase II | Romania | SNTGN Transgaz SA | Advanced | 2013-09-02 | 2013-12-31 |  | 2014-01-01 | 2015-09-30 |  | 2015-07-01 | 2018-11-01 |  | 2016-01-01 | [7 empty] | 2022-12-30 |  | 2022 | 2022 | 2015-05-18 | Delayed | Delayed, in order to respond to the market demand as a result of the Open Season Procedure at IP Csandodpalota
Pipeline including CS | TRA-N-7 | Development for new import from the South (Adriatica Line) | Italy | Snam Rete Gas S.p.A. | Less-Advanced |  |  | The pre-feasebility ended in 2004 |  |  | The feasebility ended in 2004 | 2009-01-01 | 2011-05-01 |  | 2009-01-01 | 2023-09-01 |  | 2023-09-01 |  | 2021-01-01 |  | 2023-09-01 | 2026-01-01 |  | 2026 | 2026
Pipeline including CS | TRA-N-8 | Import developments from North-East | Italy | Snam Rete Gas S.p.A. | Less-Advanced |  |  | See the comment below |  |  | See the comment below |  |  | See the comment below |  |  | See the comment below |  | See the comment below |  | See the comment below |  |  | See the comment below | 2034 | 2034
Pipeline including CS | TRA-N-9 | Additional Southern developments | Italy | Snam Rete Gas S.p.A. | Less-Advanced |  |  | See the comment below |  |  | See the comment below |  |  | See the comment below |  |  | See the comment below |  | See the comment below |  | See the comment below |  |  | See the comment below | 2034 | 2034 |  | Not applicable
Pipeline including CS | TRA-N-14 | Komotini-Thesprotia pipeline | Greece | DESFA S.A. | Less-Advanced | 2017-04-03 | 2018-10-10 |  | 2018-10-10 | 2020-03-02 |  | 2020-06-01 | 2020-12-30 |  | 2020-12-30 | 2021-12-30 |  | 2022-03-01 |  | 2022-01-10 |  | 2022-05-02 | 2025-07-25 |  | 2025 | 2025 |  | Delayed | Lack of interest from the market
Energy Transition Related Project | ETR-N-20 | GNI Renewable Gas Central Grid Injection Project | Ireland | Gas Networks Ireland | Less-Advanced | 2019-03-01 | 2019-09-30 |  | 2019-10-01 | 2020-06-30 |  | 2021-05-01 | 2024-06-30 |  | 2021-05-01 | 2024-06-30 |  |  | Dependent on procurement approach, this may involve more than one supplier etc or may be divided into lots. | 2022-07-31 |  | 2022-08-01 | 2025-10-31 |  | 2023 | 2028
Energy Transition Related Project | ETR-N-22 | Ervia Cork CCUS | Ireland | Ervia (parent company of Gas Networks Ireland) | Less-Advanced | 2019-02-04 | 2019-07-30 |  | 2019-07-31 | 2020-07-30 |  | 2020-07-31 | 2022-11-09 |  | 2022-02-03 | 2023-05-10 |  | 2023-05-10 |  | 2024-04-09 |  | 2024-04-10 | 2028-12-20 |  | 2028 | 2028 |  | Not applicable
Pipeline including CS | TRA-N-27 | Physical reverse flow from NI to GB and IE via SNIP pipeline | United Kingdom | Premier Transmission Limited | Less-Advanced | 2019-10-01 | 2019-10-01 |  | 2019-10-01 | 2019-10-01 |  | 2020-01-01 | 2020-01-01 |  | 2019-10-01 | 2020-09-30 |  | 2020-01-01 |  | 2020-12-31 |  | 2021-01-01 | 2022-09-30 |  | 2021 | 2021 |  | On time | ​This project is linked to the Islandmagee gas storage project and has been subsequently delayed, in line with the gas storage project being delayed – caused by the absence of competitive transmission tariffs for gas storage.
Pipeline including CS | TRA-N-53 | White Stream | Georgia | White Stream Ltd | Less-Advanced | 2008-01-01 | 2011-12-01 |  | 2019-09-01 | 2020-09-01 |  | 2020-10-01 | 2021-09-01 |  | 2021-01-01 | 2021-12-01 |  | 2021-12-01 |  | 2022-01-01 |  | 2022-06-01 | 2023-12-01 |  | 2023 | 2023 |  | Rescheduled | The progress of the Trans Caspian Pipeline system (2 strings) - so the enabler project of the White Stream Pipeline, was not that fast as previously expected because of the uncertainties regarding legal status of the Caspian Sea. Since the signature of the Caspian Sea convention - signed mid of 2018 - the perceived risks by potential investors has decreased, subsequently interest in the Trans Caspian Pipeline system has increased. Nevertheless, it takes some time to fully built up the necessary confidence of investors consequently it will be difficult to catch up regarding initial time schedule to the full extend, thus a rescheduling of the White Stream Pipeline was advisable.
Pipeline including CS | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Croatia | Plinacro Ltd | Less-Advanced |  |  | The Feasibility Study will be dran up. | 2020-01-01 | 2020-01-01 |  | 2020-01-01 | 2020-01-01 |  | 2020-01-01 | 2020-01-01 |  | 2021-01-01 |  | 2022-01-01 |  | 2022-01-01 | 2023-01-01 |  | 2025 | 2025 |  | Delayed | Environmental impact assessment has expired. Environmental impact assessment of the project of the northern interconnection pipeline between Croatia and B&H shall be conducted again. Also, location permit for has expired as well. New request for the issuing of the location permit should be submit to the ralevant body.
Pipeline including CS | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Croatia | Plinacro Ltd | Less-Advanced |  |  | It is not necessary to draw it up. | 2015-09-01 | 2016-10-01 |  | 2018-06-01 | 2019-04-01 |  | 2009-07-02 | 2025-01-01 |  | 2025-01-01 |  | 2025-01-01 |  | 2025-01-01 | 2027-01-01 |  | 2027 | 2027 | 2015-11-24 | Rescheduled | The preparatory work will be performed in phases, depending on the development of the LNG project,
Energy Transition Related Project | ETR-N-80 | Power to Gas Production with infrastructure building/enhacement in Latvia | Latvia | JSC "Conexus Baltic Grid" | Less-Advanced | 2019-09-01 | 2020-02-01 |  | 2019-09-15 | 2020-03-01 |  |  |  | Will be scheduled following findings of the feasibility study |  |  | Will be scheduled following findings of the feasibility study |  | Will be scheduled following findings of the feasibility study |  | Will be scheduled following findings of the feasibility study |  |  | Will be scheduled following findings of the feasibility study | 2025 | 2025 |  | Not applicable
Pipeline including CS | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | Slovenia | Plinovodi d.o.o. | Less-Advanced |  |  | n/a | 2014-11-01 | 2015-02-01 |  | 2021-09-01 | 2023-12-01 |  | 2022-10-01 | 2024-10-01 |  | 2025-10-01 |  | 2020-09-01 |  | 2024-10-01 | 2025-10-01 |  | 2025 | 2025
Pipeline including CS | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade | Slovenia | Plinovodi d.o.o. | Less-Advanced | 2014-07-01 | 2015-01-01 |  | 2015-04-01 | 2015-05-01 |  | 2020-07-01 | 2022-07-01 |  | 2021-07-01 | 2022-12-01 |  | 2023-12-01 |  | 2021-09-01 |  | 2022-07-01 | 2023-12-01 |  | 2023 | 2023 |  | Rescheduled
Pipeline including CS | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Slovenia | Plinovodi d.o.o. | Less-Advanced |  |  | n/a | 2014-11-01 | 2015-02-01 |  | 2021-09-01 | 2023-12-01 |  | 2022-10-01 | 2024-10-01 |  | 2025-10-01 |  | 2020-09-01 |  | 2024-10-01 | 2025-10-01 |  | 2025 | 2025
Pipeline including CS | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Slovenia | Plinovodi d.o.o. | Less-Advanced | 2009-10-01 | 2010-04-01 |  | 2014-11-01 | 2015-02-01 |  | 2020-09-01 | 2023-12-01 |  | 2020-09-01 | 2024-07-01 |  | 2025-10-01 |  | 2020-09-01 |  | 2022-04-01 | 2025-10-01 |  | 2023 | 2025 |  | Rescheduled
Energy Transition Related Project | ETR-N-125 | Biomethane production with infrastructure building/enhancement in Latvia | Latvia | JSC "Conexus Baltic Grid" | Less-Advanced | 2019-09-01 | 2019-12-01 |  | 2020-02-02 | 2020-09-01 |  |  |  | Will be scheduled following findings of feasibility study |  |  | Will be scheduled following findings of feasibility study |  | Will be scheduled following findings of feasibility study |  | Will be scheduled following findings of feasibility study | 2023-01-01 | 2025-12-31 |  | 2025 | 2025 |  | Not applicable
Pipeline including CS | TRA-N-128 | Compressor Station Kipi | Greece | DESFA S.A. | Less-Advanced |  |  | Not necessary acording to DESFA. | 2019-06-30 | 2019-09-30 |  | 2020-01-31 | 2020-06-30 |  | 2020-03-30 | 2021-01-29 |  | 2021-02-28 |  | 2021-01-29 |  | 2021-06-01 | 2023-06-30 |  | 2024 | 2024
Pipeline including CS | TRA-N-137 | Balkan Gas Hub - Interconnection Bulgaria - Serbia | Bulgaria | Bulgartransgaz EAD | Less-Advanced | 2010-01-01 | 2011-02-01 |  | 2011-12-01 | 2012-12-01 |  |  |  | Following the transferring of the project, Bulgartransgaz EAD will update the project documentation for the site in line with the current regulatory framework and taking into account the prescriptions for route section change as a result of rescue archeological research. |  |  | Procedures on assigning the update activities are planned to be carried out in 2019 – 2020. The process began during the previous project promoter; following the project transferring, Bulgartransgaz EAD will use as much as possible documents from the process that are not subject to update or change. | 2020-03-02 |  |  | The FID depends on finalising the transfer of the project to Bulgartransgaz and timeline for the implementation of the preparatory activities. | 2020-10-01 | 2022-04-30 |  | 2022 | 2022 |  | Delayed | Changed project promoter. Delay in transferring of the project from the Ministry of Energy to Bulgartransgaz.
Pipeline including CS | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Spain | Enagas Transporte S.A.U. | Less-Advanced |  |  | Already done | 2020-08-01 | 2021-07-31 |  | 2020-08-01 | 2021-07-31 |  | 2021-05-01 | 2021-12-31 |  |  | Not applicable | 2022-06-01 |  | 2024-01-01 | 2025-06-01 |  | 2025 | 2025 |  | Rescheduled | In the last edition of the TYNDP, REN was in the permitting process phase, waiting for the Environmental Impact Declaration to be issued by the Competent Authorities. At this moment, REN already received the declaration with an unfavorable decision. As a consequence, it will be necessary to make an adjustment to the initial route, maintaining the same point of interconnection with Spain.
Pipeline including CS | TRA-N-192 | Entry capacity expansion GATE terminal | Netherlands | Gasunie Transport Services B.V. | Less-Advanced |  |  | Unknown at this time |  |  | Unknown at this time |  |  | Unknown at this time |  |  | Unknown at this time |  | Unknown at this time |  | Unknown at this time |  |  | Unknown at this time | 2022 | 2022
Pipeline including CS | TRA-N-224 | Gaspipeline Brod - Zenica | Bosnia Herzegovina | BH-Gas d.o.o. | Less-Advanced | 2005-02-28 | 2006-02-28 |  | 2020-01-31 | 2021-01-31 |  | 2021-02-28 | 2022-02-28 |  | 2021-02-28 | 2023-01-31 |  | 2024-01-31 |  | 2022-01-31 |  | 2024-03-01 | 2025-09-30 |  | 2025 | 2025 |  | Rescheduled | Regarding the fact that the part of this project runs through Republic of Srpska Entity, the main obstacle is lack of political support of the RS official representatives, as well as lack of primary gas legislation at the state level in accordance with the Third Energy Package. Also,existing natural gas market is not able to cover assessed project cost related to preliminary activities.
LNG Terminal | LNG-N-225 | Montoir LNG Terminal Expansion | France | Elengy | Less-Advanced |  |  | not available |  |  | not available |  |  | not available |  |  | not available |  | not available | 2021-06-01 |  | 2021-06-01 | 2025-06-01 |  | 2023 | 2025 |  | Rescheduled | market was not there, but situation may change soon
Energy Transition Related Project | ETR-N-226 | Fos Tonkin LNG Terminal Evolution | France | Elengy | Less-Advanced |  |  | done |  |  | done, cf. fields [046], [195] |  |  | not available |  |  | not available |  | not available | 2020-07-01 |  | 2020-07-01 | 2022-07-01 |  | 2022 | 2022 |  | Not applicable
LNG Terminal | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | France | Fosmax LNG | Less-Advanced |  |  | not available |  |  | not available |  |  | not available |  |  | not available |  | not available | 2021-06-01 |  | 2021-06-01 | 2025-06-01 |  | 2023 | 2025 |  | Rescheduled | market was not there, but situation may change soon
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | Poland | GAZ-SYSTEM S.A. | Less-Advanced |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A |  | N/A |  | N/A |  |  | N/A | 2029 | 2029
Pipeline including CS | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | France | GRTgaz | Less-Advanced | 2011-01-01 | 2011-12-31 |  |  |  | na |  |  | na |  |  | na |  | na |  | na | 2024-01-01 | 2026-12-31 |  | 2023 | 2023 |  | Rescheduled | Waiting for terminal promoter decision
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | France | GRTgaz | Less-Advanced |  |  | na |  |  | na |  |  | na |  |  | na |  | na |  | na | 2024-01-01 | 2026-11-30 |  | 2026 | 2026 |  | Rescheduled | Waiting for LNG terminal decision
LNG Terminal | LNG-N-297 | Mugardos LNG Terminal: Storage Extension | Spain | Reganosa | Less-Advanced | 2015-02-11 | 2015-12-15 |  | 2015-02-11 | 2015-12-15 |  | 2016-08-24 | 2017-11-14 |  | 2023-02-06 | 2024-02-02 |  |  | This phase is not schedule for this project | 2024-02-02 |  | 2024-05-27 | 2028-01-01 |  | 2026 | 2026 |  | Rescheduled
Pipeline including CS | TRA-N-299 | M3/1 Šempeter - Vodice | Slovenia | Plinovodi d.o.o. | Less-Advanced |  |  | n/a | 2014-11-01 | 2015-02-01 |  | 2021-03-01 | 2024-03-01 |  | 2022-03-01 | 2024-03-01 |  | 2026-01-01 |  | 2020-09-01 |  | 2024-03-01 | 2026-12-01 |  | 2026 | 2026
Energy Transition Related Project | ETR-N-300 | HyOffWind Zeebrugge | Belgium | Fluxys, Eoly, Parkwind | Less-Advanced | [19 empty] | 2020 | 2020
Pipeline including CS | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Croatia | Plinacro Ltd | Less-Advanced |  |  | It is not necessary to drawn up. | 2026-02-01 | 2026-05-28 |  | 2026-05-31 | 2027-05-31 |  | 2025-05-29 | 2027-05-31 |  | 2027-11-30 |  | 2027-01-01 |  | 2027-11-30 | 2028-11-30 |  | 2026 | 2026 |  | Rescheduled
LNG Terminal | LNG-N-304 | Italy-Sardinia Virtual Pipeline | Italy | Snam S.p.A. | Less-Advanced | 2019-01-01 | 2019-12-31 |  | 2019-01-01 | 2019-12-31 |  | 2020-01-01 | 2020-01-01 |  | 2020-01-01 | 2020-12-31 |  | 2020-12-31 |  | 2020-01-01 |  | 2021-01-01 | 2021-12-31 |  | 2021 | 2021
Energy Transition Related Project | ETR-N-305 | PEGASUS | Italy | S.G.I. SpA | Less-Advanced | 2019-04-01 | 2019-05-31 |  | 2019-06-01 | 2019-07-31 |  | 2019-08-01 | 2020-09-30 |  | 2020-10-01 | 2021-12-31 |  | 2022-02-01 |  | 2022-02-01 |  | 2022-03-01 | 2023-12-31 |  | 2024 | 2024 | 2024-03-01 | Not applicable
Energy Transition Related Project | ETR-N-306 | Greening of Gas (GoG) | Czechia | NET4GAS, s.r.o. | Less-Advanced | 2018-06-01 | 2018-12-31 |  | 2019-01-01 | 2019-12-31 |  |  |  | n/a |  |  | n/a |  | n/a |  | n/a |  |  | n/a | 2023 | 2023
Energy Transition Related Project | ETR-N-315 | G2F - Gas to Future | Slovakia | NAFTA a.s. (joint stock company) | Less-Advanced | 2020-05-01 | 2020-12-31 |  | 2021-04-01 | 2022-04-30 |  | 2023-01-01 | 2023-12-31 |  | 2020-05-01 | 2024-03-31 |  | 2024-04-30 |  |  | yet unknown | 2024-05-01 | 2025-06-30 |  | 2025 | 2025 |  | Not applicable
Energy Transition Related Project | ETR-N-322 | North Sea Wind Power Hub | Netherlands | N.V. Nederlandse Gasunie | Less-Advanced |  | 2020-12-31 |  |  | 2021-12-31 |  |  | 2026-12-31 |  |  | 2025-12-31 | [6 empty] | 2030-12-31 |  | 2032 | 2032
Pipeline including CS | TRA-N-325 | Slovenian-Hungarian interconnector | Hungary | FGSZ Ltd. | Less-Advanced | 2014-11-01 | 2015-12-31 |  | 2016-05-01 | 2019-10-01 |  | 2021-03-01 | 2022-02-28 |  | 2021-01-01 | 2022-03-01 |  | 2022-04-01 |  | 2020-08-31 |  | 2022-03-01 | 2025-10-01 |  | 2023 | 2025 |  | Rescheduled
Pipeline including CS | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Croatia | Plinacro Ltd | Less-Advanced |  |  | It is not necessary as Feasibility Study will be drawn up. | 2027-01-01 | 2027-01-01 |  | 2028-01-01 | 2028-01-01 |  | 2026-01-01 | 2028-01-01 |  | 2028-01-01 |  | 2028-01-01 |  | 2028-01-01 | 2029-01-01 |  | 2029 | 2029
Storage Facility | UGS-N-347 | Gas storage facility Grubisno Polje | Croatia | Podzemno skladiste plina Ltd | Less-Advanced | 2018-01-01 | 2018-12-31 |  | 2019-01-01 | 2019-06-30 |  | 2019-07-01 | 2019-12-31 |  | 2020-01-01 | 2020-07-01 |  | 2020-12-31 |  | 2020-12-31 |  | 2021-01-01 | 2021-07-01 |  | 2025 | 2025 | 2017-03-31
Pipeline including CS | TRA-N-354 | Interconnection with Slovenia | Italy | Snam Rete Gas S.p.A. | Less-Advanced |  |  | Completed |  |  | completed | 2020-01-01 | 2020-01-01 |  | 2021-01-01 | 2022-01-01 |  | 2022-01-01 |  | 2020-01-01 |  | 2022-01-01 | 2022-01-01 |  | 2023 | 2023
Pipeline including CS | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | Austria | GAS CONNECT AUSTRIA GmbH | Less-Advanced |  |  | n.a. |  |  | n.a. |  |  | n.a. | 2020-07-01 | 2020-12-31 |  | 2021-03-01 |  | 2020-11-01 |  | 2021-05-01 | 2023-08-01 |  | 2023 | 2023 |  | Rescheduled
Energy Transition Related Project | ETR-N-370 | Hydrogen transmission backbone Netherlands | Netherlands | N.V. Nederlandse Gasunie | Less-Advanced | 2018-06-01 | 2018-09-30 |  | 2019-07-01 | 2019-10-31 |  | 2019-07-01 | 2021-07-01 |  | 2019-07-01 | 2023-07-01 |  | 2025-01-01 |  | 2025-01-01 |  | 2025-01-01 | 2029-12-31 |  | 2030 | 2030
Storage Facility | UGS-N-371 | Sarmasel undeground gas storage in Romania | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | 2016-01-01 | 2016-06-01 |  | 2019-03-01 | 2020-03-01 |  | 2020-06-01 | 2021-04-01 |  | 2021-04-01 | 2021-10-01 |  | 2021-12-01 |  | 2020-06-01 |  | 2022-01-01 | 2024-10-01 |  | 2024 | 2024 | 2021-12-01 | On time
Storage Facility | UGS-N-385 | South Kavala Underground Gas Storage facility | Greece | Hellenic Republic Asset Development Fund | Less-Advanced | 2018-08-01 | 2019-11-30 |  | 2019-11-30 | 2020-06-15 |  | 2020-06-30 | 2020-10-31 |  | 2021-02-01 | 2021-09-30 |  |  | to be decided | 2021-10-12 |  | 2021-11-01 | 2023-09-30 |  | 2023 | 2023 |  | Rescheduled | Current market conditions are considered favourable for the project's advancement and the project promoter strongly believes that the indicated timeline will be met.
Pipeline including CS | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Slovenia | Plinovodi d.o.o. | Less-Advanced | 2014-07-01 | 2015-01-01 |  | 2015-04-01 | 2015-05-01 |  | 2020-07-01 | 2022-07-01 |  | 2021-07-01 | 2022-12-01 |  | 2023-12-01 |  | 2021-09-01 |  | 2022-07-01 | 2023-12-01 |  | 2023 | 2023 |  | Rescheduled
Pipeline including CS | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Slovenia | Plinovodi d.o.o. | Less-Advanced | 2014-07-01 | 2015-01-01 |  | 2015-04-01 | 2015-05-01 |  | 2020-07-01 | 2022-07-01 |  | 2021-07-01 | 2022-12-01 |  | 2023-12-01 |  | 2021-09-01 |  | 2022-07-01 | 2023-12-01 |  | 2021 | 2023 |  | Rescheduled
Energy Transition Related Project | ETR-N-396 | Djewels | Netherlands | Nouryon | Less-Advanced | 2019-01-01 | 2019-12-31 |  | 2020-01-01 | 2020-12-31 |  | 2021-01-01 | 2021-12-31 |  |  |  | Unknown at this time |  | Unknown at this time |  | Unknown at this time |  |  | Unknown at this time | 2030 | 2030
Storage Facility | UGS-N-398 | Ghercesti underground gas storage in Romania | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced |  |  | Decision for feasibility study execution already taken based on company procedures in June 20th 2019 | 2020-02-07 | 2021-02-01 |  | 2021-06-02 | 2022-06-06 |  | 2022-07-11 | 2023-12-28 |  | 2023-03-09 |  | 2021-03-05 |  | 2024-01-08 | 2026-12-10 |  | 2026 | 2026 |  | Not applicable
Storage Facility | UGS-N-399 | Falticeni UGS | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced |  |  | Decision for feasibility study execution will be taken based on company procedures by the end of 2019 | 2020-03-03 | 2021-03-19 |  | 2024-02-05 | 2025-02-04 |  | 2025-03-09 | 2026-03-02 |  | 2027-10-12 |  | 2023-11-23 |  | 2026-09-04 | 2029-03-09 |  | 2029 | 2029
Energy Transition Related Project | ETR-N-401 | Antwerp@C | Belgium | Fluxys and Antwerp Port Authority | Less-Advanced | 2018-03-01 | 2019-03-01 | [17 empty] | 2026 | 2026 |  | Not applicable
Pipeline including CS | TRA-N-402 | TENP Security of Supply | Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | Less-Advanced | [19 empty] | 2024 | 2024
Energy Transition Related Project | ETR-N-406 | hybridge - gas grid infrastructure | Germany | Open Grid Europe GmbH | Less-Advanced | 2018-01-01 | 2019-03-28 |  | 2019-01-01 | 2020-03-31 |  | 2020-01-01 | 2020-12-31 |  | 2021-01-01 | 2021-12-31 |  |  | currently no contracts are concluded | 2020-01-01 |  | 2022-01-01 | 2023-06-30 |  | 2023 | 2023
Pipeline including CS | TRA-N-423 | GCA Mosonmagyaróvár | Austria | GAS CONNECT AUSTRIA GmbH | Less-Advanced |  |  | n.a. |  |  | n.a. |  |  | n.a. | 2021-05-01 | 2021-10-01 |  | 2022-02-01 |  | 2021-08-01 |  | 2022-02-01 | 2024-07-01 |  | 2024 | 2024 |  | Rescheduled | The project proposal for HUAT has been submitted to the involved NRA's for joint approval. Due to the lack of a joint approval by both NRAs, ACER got involved. According to ACER decision No 05/2019 of 09 April 2019 the Agency approved to carry out a binding phase (auction) for selling of incremental capacity.
Energy Transition Related Project | ETR-N-427 | P2G integrated in Reganosa NG Transmission Grid | Spain | Reganosa | Less-Advanced | 2019-10-01 | 2020-06-01 |  | 2019-10-01 | 2020-06-01 |  | 2020-08-01 | 2021-06-01 |  | 2021-06-01 | 2023-06-01 |  |  | This phase is not scheduled for this project | 2023-06-01 |  | 2023-06-01 | 2024-12-01 |  | 2024 | 2024 |  | Not applicable
Energy Transition Related Project | ETR-N-432 | Athos | Netherlands | N.V. Nederlandse Gasunie | Less-Advanced | 2018-12-01 | 2018-12-31 |  | 2019-01-01 | 2019-06-30 |  | 2021-01-01 | 2021-04-01 |  | 2020-01-01 | 2020-04-01 |  | 2021-01-31 |  | 2023-10-01 |  | 2023-10-30 | 2026-01-01 |  | 2026 | 2026
Pipeline including CS | TRA-N-439 | Stazione di Spinta "San Marco" | Italy | S.G.I. S.p.A. | Less-Advanced | 2015-03-01 | 2015-07-31 |  | 2018-06-01 | 2019-10-31 |  | 2019-11-01 | 2020-06-30 |  | 2019-11-01 | 2021-03-31 |  | 2021-05-31 |  | 2021-01-01 |  | 2021-06-01 | 2022-12-31 |  | 2022 | 2022 |  | On time
Energy Transition Related Project | ETR-N-449 | Hydrogen Region Lausitz | Germany | ONTRAS Gastransport GmbH | Less-Advanced | 2019-01-01 | 2019-12-31 |  | 2020-01-01 | 2020-03-01 |  | 2020-03-01 | 2020-08-01 |  |  |  | uncertain |  | uncertain |  | uncertain |  |  | uncertain | 2021 | 2021
Energy Transition Related Project | ETR-N-452 | Element Eins | Germany | Thyssengas GmbH, Gasunie Deutschland Transport Services GmbH, Tennet TSO Gm | Less-Advanced | 2019-06-01 | 2019-10-31 |  | 2019-10-31 | 2019-12-31 |  |  |  | Info not available yet |  |  | Info not available yet |  | Info not available yet |  | Info not available yet | 2022-01-01 | 2022-12-31 |  | 2022 | 2028
Energy Transition Related Project | ETR-N-483 | L2DG (LNG to Decarbonised Gas) | Spain | Reganosa | Less-Advanced | 2019-08-01 | 2020-07-01 |  | 2019-08-01 | 2020-07-01 |  | 2020-08-01 | 2021-06-01 |  | 2021-06-01 | 2023-06-01 |  |  | This phase is not scheduled for this project. | 2023-06-01 |  | 2023-06-01 | 2024-12-01 |  | 2024 | 2024 |  | Not applicable
Energy Transition Related Project | ETR-N-501 | Hub País Vasco | Spain | Enagas S.A. | Less-Advanced | 2019-02-01 | 2019-12-30 |  | 2020-01-01 | 2020-12-30 |  | 2021-01-01 | 2021-12-30 |  | 2021-06-01 | 2022-06-01 |  |  | Not applicable |  | Not define yet | 2022-01-01 | 2023-12-31 |  | 2023 | 2023 |  | On time
Pipeline including CS | TRA-N-502 | Interconnector Romania - Ukraine | Ukraine | Joint-Stock Company | Less-Advanced | 2019-01-01 | 2019-12-31 |  | 2020-01-01 | 2020-12-31 |  |  |  | tbd |  |  | tbd |  | tbd |  | tbd |  |  | tbd | 2025 | 2025
Energy Transition Related Project | ETR-N-521 | Hub Murcia | Spain | Enagas S.A. | Less-Advanced | 2020-01-01 | 2020-01-01 |  | 2020-01-01 | 2021-01-01 |  | 2021-01-01 | 2022-01-01 |  | 2021-01-01 | 2022-01-01 |  | 2022-01-01 |  | 2021-01-01 |  | 2022-01-01 | 2023-01-01 |  | 2023 | 2023
Pipeline including CS | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Hungary | FGSZ Ltd. | Less-Advanced | 2018-01-01 | 2018-12-31 |  | 2018-01-01 | 2018-12-31 |  | 2019-10-01 | 2020-10-01 |  | 2019-10-01 | 2020-10-01 |  |  | Based on previous steps's completeness, during 2020 | 2019-08-01 |  | 2020-08-01 | 2022-10-31 |  | 2022 | 2022
Energy Transition Related Project | ETR-N-528 | Microliquefaction plants | Italy | Snam4mobility | Less-Advanced | 2019-01-01 | 2019-12-31 |  | 2019-01-01 | 2019-12-31 |  | 2020-01-01 | 2021-12-31 |  | 2020-01-01 | 2021-12-31 |  | 2020-06-01 |  | 2020-01-01 |  | 2020-01-01 | 2022-01-01 |  | 2022 | 2022
Energy Transition Related Project | ETR-N-537 | Hub Aragon | Spain | Enagas S.A. | Less-Advanced | 2019-01-01 | 2019-01-01 |  | 2020-01-01 | 2020-01-01 |  | 2020-01-01 | 2022-01-01 |  | 2020-01-01 | 2020-01-01 |  |  | No data |  | No data | 2020-01-01 | 2022-01-01 |  | 2022 | 2022 |  | On time
Energy Transition Related Project | ETR-N-562 | Energy Park Bad Lauchstädt | Germany | ONTRAS Gastransport GmbH | Less-Advanced | 2018-01-01 | 2019-04-30 |  | 2019-05-01 | 2021-04-30 |  | 2019-06-01 | 2021-05-31 |  | 2020-01-01 | 2020-12-31 |  |  | unknown |  | unknown |  |  | unknown | 2023 | 2023
Energy Transition Related Project | ETR-N-591 | Power to gas plant in the south of Italy | Italy | Snam Rete Gas S.p.A. | Less-Advanced |  |  | See the comment below |  |  | See the comment below |  |  | See the comment below |  |  | See the comment below |  | See the comment below |  | See the comment below |  |  | See the comment below | 2025 | 2025
Energy Transition Related Project | ETR-N-595 | Transport of hydrogen into natural gas network | Italy | Snam Rete Gas S.p.A. | Less-Advanced |  |  | See the comment below |  |  | See the comment below |  |  | See the comment below |  |  | See the comment below |  | See the comment below |  | See the comment below |  |  | See the comment below | 2025 | 2025
Pipeline including CS | TRA-N-596 | Interconnection between the RO and the UA gas transmission systems | Romania | SNTGN Transgaz SA | Less-Advanced | 2018-01-14 | 2018-11-30 |  | 2019-01-13 | 2020-06-30 |  | 2020-07-01 | 2021-12-31 |  | 2020-07-01 | 2021-12-31 |  |  | not available | 2021-12-31 |  | 2022-01-16 | 2024-12-31 |  | 2025 | 2025 |  | Not applicable
Pipeline including CS | TRA-N-598 | NTS developments in North-Vest Romania | Romania | SNTGN Transgaz SA | Less-Advanced | 2016-01-15 | 2016-12-30 |  | 2019-07-01 | 2020-07-01 |  | 2020-07-31 | 2023-12-29 |  | 2020-07-31 | 2023-12-29 |  |  | not available | 2020-12-31 |  | 2021-01-15 | 2026-12-31 |  | 2026 | 2026
Energy Transition Related Project | ETR-N-616 | Renewable Methane according to NEP2020 | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | 2019-01-01 | 2020-01-01 |  | 2019-01-01 | 2023-01-01 |  | 2022-01-01 | 2024-01-01 |  | 2021-01-01 | 2025-01-01 |  | 2022-01-01 |  | 2023-01-01 |  | 2023-01-01 | 2025-01-01 |  | 2023 | 2025
Energy Transition Related Project | ETR-N-617 | Project to facilitate biomethane production plants inteconnection | Italy | Snam Rete Gas | Less-Advanced |  |  | The project is an aggregation of several intervention so it is impossible to give a schedule |  |  | The project is an aggregation of several intervention so it is impossible to give a schedule |  |  | The project is an aggregation of several intervention so it is impossible to give a schedule |  |  | The project is an aggregation of several intervention so it is impossible to give a schedule |  | The project is an aggregation of several intervention so it is impossible to give a schedule |  | The project is an aggregation of several intervention so it is impossible to give a schedule |  |  | The project is an aggregation of several intervention so it is impossible to give a schedule | 2022 | 2022
Energy Transition Related Project | ETR-N-622 | Renewable Hydrogen according to NEP2020 | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | 2019-01-01 | 2021-01-01 |  | 2019-01-01 | 2023-01-01 |  | 2022-01-01 | 2024-01-01 |  | 2021-01-01 | 2024-01-01 |  | 2022-01-01 |  | 2023-01-01 |  | 2023-01-01 | 2025-01-01 |  | 2020 | 2025
Energy Transition Related Project | ETR-N-624 | Biomethane: Reverse flow projects | France | GRTgaz | Less-Advanced |  |  | na |  |  | na |  |  | na |  |  | na |  | na |  | na |  |  | na | 2028 | 2028
Energy Transition Related Project | ETR-N-633 | GETH2-ETR 1 | Germany | Nowega GmbH | Less-Advanced |  |  | until End of 2019 |  |  | 2020 |  |  | not available |  |  | 2020 |  | not available |  | scheduled Mid of 2020 |  |  | not available | 2022 | 2022
Pipeline including CS | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Hungary | FGSZ Ltd. | Less-Advanced |  |  | was not made |  |  | was not made |  |  | Technical requirements and design guidelines finalized on 04.09.2018. internally – no conventional FEED was made. |  |  | no permitting needed – starting of construction was reported to mining authority on 21.06.2019. | 2019-07-08 |  | 2019-08-26 |  | 2019-08-26 | 2019-09-30 |  | 2022 | 2022
Energy Transition Related Project | ETR-N-728 | Biomethane: connecting production units and reverse flow projects | France | TEREGA | Less-Advanced |  |  | All backhaul facilities are still at the the stage of pre-feasibility study but one. |  |  | All grid extensions to connect biomethane production units have completed the pre-feasibility studies and are at the the stage of the feasibility study but three. one is still at the the pre-feasibility study phase and two are the FID stage |  |  | N/A |  |  | N/A |  | N/A |  | 2 grid extension projects have the FID taken |  |  | 2 grid extension projects will be completed by 2020 | 2029 | 2029 |  | Not applicable | N/A
Pipeline including CS | TRA-N-809 | Reallocation H-Gas towards NL: Bunde/Oude to Zone Oude Statenzijl H | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | 2016-01-01 | 2016-01-01 |  | 2016-06-01 | 2016-12-06 |  |  |  | Not decided yet |  |  | Not decided yet |  | Not decided yet |  | Not decided yet |  |  | Not decided yet | 2022 | 2022
Pipeline including CS | TRA-N-810 | TAP Expansion | Greece | Trans Adriatic Pipeline AG | Less-Advanced | 2009-01-01 | 2013-03-25 |  | 2009-01-01 | 2013-03-25 |  |  |  | Timeline of FEED depends on the timing and outcome of the Binding phase of the TAP 2019 Market Test. |  |  | Permitting activities are to be conducted based on the already existing permits for the Initial Capacity of TAP and are dependent on the pre-FEED studies as well as the outcome of the Binding phase of the 2019 Market Test of TAP. |  | The conclusion of supply contracts depends on the outcome of the Binding phase of the 2019 Market Test of TAP. |  | Timing of FID is not defined, and will i.a. depend on the outcome of the Binding phase of the 2019 Market Test of TAP, including a positive Economic Viability Test. |  |  | TAP Expansion preliminary construction date is estimated to 2022, depending on the progress of the Market Test process and on the outcome of the Binding phase of TAP 2019 Market Test process. | 2025 | 2025 |  | Not applicable
Pipeline including CS | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | Bosnia Herzegovina | BH-GAS d.o.o. | Less-Advanced | 2013-04-09 | 2013-10-31 |  | 2019-08-31 | 2020-08-31 |  | 2019-08-01 | 2021-01-31 |  | 2020-08-31 | 2022-01-31 |  | 2022-02-28 |  | 2021-01-31 |  | 2022-03-31 | 2023-09-30 |  | 2023 | 2023 |  | Rescheduled
Pipeline including CS | TRA-N-873 | Additional import at Oude StatenZijl area | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | 2017-07-01 | 2019-08-01 |  | 2019-08-01 | 2019-10-01 |  | 2020-01-01 | 2021-12-31 |  | 2021-01-01 | 2022-12-31 |  | 2024-12-31 |  | 2019-07-31 |  | 2025-02-01 | 2025-04-01 |  | 2022 | 2025
Pipeline including CS | TRA-N-882 | Transferring L-gas infrastructure to H-gas | Netherlands | Gasunie Transport Services B.V. | Less-Advanced |  |  | Unknown at this time |  |  | Unknown at this time |  |  | Unknown at this time |  |  | Unknown at this time |  | Unknown at this time |  | Unknown at this time |  |  | Unknown at this time | 2020 | 2030
Pipeline including CS | TRA-N-910 | West Interconnection BiH/CRO | Bosnia Herzegovina | BH-Gas d.o.o. | Less-Advanced | 2007-06-01 | 2008-06-30 |  | 2020-01-31 | 2021-01-31 |  | 2021-02-28 | 2023-02-28 |  | 2021-02-28 | 2024-03-31 |  | 2025-03-31 |  | 2023-03-31 |  | 2025-03-31 | 2026-09-30 |  | 2026 | 2026 |  | Rescheduled
LNG Terminal | LNG-N-912 | Skulte LNG | Latvia | AS Skulte LNG Terminal | Less-Advanced | 2014-10-01 | 2015-03-02 |  | 2015-03-03 | 2016-05-10 |  | 2019-09-01 | 2020-08-31 |  | 2020-04-01 | 2021-06-01 |  | 2023-02-01 |  | 2020-12-01 |  | 2021-07-01 | 2023-09-01 |  | 2023 | 2023 | 2020-03-30 | Delayed | The project was delayed due to lack of political support. Current government is very supportive and we have proceeded with EIA process. By political support we mean government instruction to Latvenergo (state own electricity company) to sign offtake agreement for 0.3bcm annual consumption on ToP basis. EIA process is the key issue now as the pipeline is crossing 156 land properties.
Storage Facility | UGS-N-914 | UGS Damasławek | Poland | GAZ-SYSTEM S.A. | Less-Advanced |  |  | N/A |  |  | N/A |  |  | To be agreed |  |  | To be agreed |  | N/A |  | To be agreed |  |  | To be agreed | 2026 | 2026
LNG Terminal | LNG-N-947 | FSRU Polish Baltic Sea Coast | Poland | GAZ-SYSTEM S.A. | Less-Advanced |  |  | N/A | 2017-03-01 | 2017-10-01 |  | 2020-01-06 | 2022-07-31 |  | 2019-09-01 | 2022-07-31 |  | 2020-08-29 |  | 2022-10-01 |  | 2023-03-01 | 2025-12-31 |  | 2025 | 2025 |  | On time
Pipeline including CS | TRA-N-955 | GUD: Complete conversion to H-gas | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced |  |  | The conversion from low calorific to high calorific started in 2017 and will be finished in 2030 for GUD. The conversion steps will be adjusted in coorperation withe the other German TSOs. |  |  | The conversion from low calorific to high calorific started in 2017 and will be finished in 2030 for GUD. The conversion steps will be adjusted in coorperation withe the other German TSOs. |  |  | The conversion from low calorific to high calorific started in 2017 and will be finished in 2030 for GUD. The conversion steps will be adjusted in coorperation withe the other German TSOs. |  |  | The conversion from low calorific to high calorific started in 2017 and will be finished in 2030 for GUD. The conversion steps will be adjusted in coorperation withe the other German TSOs. |  | The conversion from low calorific to high calorific started in 2017 and will be finished in 2030 for GUD. The conversion steps will be adjusted in coorperation withe the other German TSOs. |  | The conversion from low calorific to high calorific started in 2017 and will be finished in 2030 for GUD. The conversion steps will be adjusted in coorperation withe the other German TSOs. | 2019-01-01 | 2029-12-31 |  | 2021 | 2030
Pipeline including CS | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | Romania | SNTGN Transgaz SA | Less-Advanced | [5 empty] | SNTGN Transgaz SA will initiate the feasibility study when additional data and information will be available from the Black Sea blocks titleholders (capacity requests confirmations, approximate period of the availability of gas on the Black Sea shore, etc.). |  |  | NA |  |  | NA |  | NA |  | NA |  |  | NA | 2023 | 2023 |  | On time
Pipeline including CS | TRA-N-971 | Compressor station at Nea Messimvria | Greece | DESFA S.A. | Less-Advanced |  |  | There was no need for a pre-feasibility study | 2018-09-03 | 2019-06-03 |  | 2019-10-31 | 2020-06-30 |  | 2020-02-03 | 2020-09-01 |  | 2020-09-11 |  | 2020-09-01 |  | 2020-09-30 | 2023-03-31 |  | 2023 | 2023 |  | On time
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Croatia | Plinacro Ltd | Less-Advanced |  |  | It is not necessary to drawn it up. | 2025-06-01 | 2025-12-31 |  | 2026-01-01 | 2026-06-30 |  | 2025-06-01 | 2026-06-30 |  | 2026-06-30 |  | 2027-01-01 |  | 2027-01-01 | 2029-12-31 |  | 2029 | 2029 | 2016-04-25 | Rescheduled
Pipeline including CS | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Croatia | Plinacro Ltd | Less-Advanced |  |  | it is not necessary | 2015-09-01 | 2016-10-01 |  | 2023-01-01 | 2023-01-01 |  | 2014-09-01 | 2023-01-01 |  | 2024-01-01 |  | 2024-01-01 |  | 2024-01-01 | 2027-01-01 |  | 2027 | 2027 | 2015-11-24 |  | Project depend on LNG project
Pipeline including CS | TRA-N-1063 | Export to Malta | Italy | Snam Rete Gas S.p.A. | Less-Advanced | 2015-01-01 | 2015-12-31 |  | 2017-04-01 | 2017-12-31 |  | 2020-09-01 | 2022-12-31 |  | 2020-09-01 | 2022-12-31 |  | 2022-01-01 |  | 2020-09-01 |  | 2023-01-01 | 2024-01-01 |  | 2024 | 2024
Pipeline including CS | TRA-N-1064 | Moffat Physical Reverse Flow | United Kingdom | National Grid Gas plc | Less-Advanced |  |  | N/A | 2017-06-22 | 2018-11-28 |  | 2019-06-01 | 2019-12-31 |  | 2020-01-01 | 2020-12-31 |  |  | N/A | 2020-12-31 |  | 2021-01-01 | 2021-12-31 |  | 2020 | 2020 | 2017-03-14 | On time | Results and recommendations from the feasibility study will be communicated to stakeholders and industry in Q1 2019. Following this, the project will progress into FEED stage. The FEED commencement date has been adjusted by 5 months to allow for communication of Feasibility Study results to take place. This adjustment will be made feasible by building on the initial conceptual design work undertaken as part of the Feasibility Study.
Pipeline including CS | TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | Greece | DESFA S.A. | Less-Advanced |  |  | DESFA believes that pre feasibility is not necessary. | 2019-09-30 | 2020-02-28 |  | 2020-04-30 | 2020-12-30 |  | 2020-06-30 | 2021-06-30 |  | 2021-08-31 |  | 2021-07-31 |  |  | 2023-03-31 |  | 2022 | 2022 |  | On time
Pipeline including CS | TRA-N-1091 | Metering and Regulating station at Megalopoli | Greece | DESFA S.A. | Less-Advanced |  |  | DESFA does not require a pre-feasibility | 2022-04-30 | 2022-10-30 |  | 2022-12-30 | 2023-10-30 |  | 2022-02-28 | 2023-02-18 |  | 2023-09-29 |  | 2023-02-28 |  | 2023-09-29 | 2025-12-21 |  | 2025 | 2025 |  | Rescheduled | Lack of market demand
Pipeline including CS | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | Greece | DESFA S.A. | Less-Advanced |  |  | DESFA considered pre-feasibility not to be needed | 2020-04-30 | 2020-10-30 |  | 2020-11-30 | 2021-05-30 |  | 2020-12-30 | 2021-12-30 |  | 2022-03-30 |  | 2022-01-30 |  | 2022-03-30 | 2023-09-30 |  | 2023 | 2023 |  | Rescheduled | The project schedule depends on the implementation of the UGS of South Kavala, promoted by others (HRADF).
Pipeline including CS | TRA-N-1129 | Compressor Station Kipi Increment | Greece | DESFA S.A. | Less-Advanced | 2017-04-03 | 2017-07-27 |  | 2017-08-01 | 2020-07-01 |  | 2020-07-01 | 2021-03-30 |  | 2020-12-30 | 2021-12-30 |  | 2022-01-01 |  | 2022-01-01 |  | 2022-10-30 | 2024-12-30 |  | 2024 | 2024
Pipeline including CS | TRA-N-1138 | South Caucasus Pipeline Future Expansion (SCPFX) | Azerbaijan | SOCAR Midstream Operations LLC | Less-Advanced | 2019-07-01 | 2020-01-01 |  | 2020-01-01 | 2020-07-01 |  | 2020-07-01 | 2021-09-01 |  | 2020-07-01 | 2021-09-01 |  | 2021-09-01 |  | 2013-12-17 |  | 2022-03-01 | 2024-03-01 |  | 2024 | 2024 | 2022-01-01 | Rescheduled
Pipeline including CS | TRA-N-1181 | Connecting pipe to LNG terminal in Latvia | Latvia | JSC "Conexus Baltic Grid" | Less-Advanced | 2019-04-01 | 2019-05-30 |  | 2019-09-01 | 2019-12-30 |  |  |  | Will be schaduled following findings of the feasibility study |  |  | Will be schaduled following findings of the feasibility study |  | Will be schaduled following findings of the feasibility study |  | Will be schaduled following findings of the feasibility study |  |  | Will be schaduled following findings of the feasibility study | 2021 | 2021
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Italy | ENURA S.p.A. | Less-Advanced | 2016-01-01 | 2016-12-31 |  | 2016-01-01 | 2016-12-31 |  |  |  | The project is a multiphase one, the FEED started in 2017 and will with the last phase in 2022 |  |  | The project is a multiphase one, the FEED started in 2017 and will with the last phase in 2023 |  | The project is a multiphase one so the supply contract dates will be coherent with realization dates |  | The FID will be taken during 2019 |  |  | The project is a multiphase one so the construction works will start during 2020 and will finish in 2025 | 2020 | 2025
Pipeline including CS | TRA-N-1195 | Matagiola - Massafra pipeline | Italy | Snam Rete Gas S.p.A. | Less-Advanced | 2019-01-01 | 2019-12-31 |  | 2020-01-01 | 2020-12-31 |  | 2021-01-01 | 2022-01-01 |  | 2022-01-01 | 2024-06-01 |  | 2024-06-01 |  | 2021-01-01 |  | 2024-06-01 | 2026-01-01 |  | 2026 | 2026
Pipeline including CS | TRA-N-1202 | GCP GAZ-SYSTEM/ONTRAS - incremental capacity project | Poland | GAZ-SYSTEM S.A. | Less-Advanced |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A |  | N/A |  | N/A |  |  | N/A | 2023 | 2023 |  | Delayed | The lack of NRAs’ coordinated decisions regarding the project.
Pipeline including CS | TRA-N-1227 | Gorizia plant upgrade | Italy | Snam Rete Gas S.p.A. | Less-Advanced | 2021-01-01 | 2021-01-01 |  | 2021-01-01 | 2021-01-01 |  | 2022-01-01 | 2022-01-01 |  | 2023-01-01 | 2023-01-01 |  | 2024-01-01 |  | 2021-01-01 |  | 2024-01-01 | 2024-01-01 |  | 2026 | 2026
Pipeline including CS | TRA-N-1235 | Firm transmission capacity increase at the IP Veľké Zlievce | Slovakia | eustream,a.s. | Less-Advanced |  |  | Not worked out. | 2017-08-07 | 2018-05-04 |  | 2020-01-08 | 2020-06-30 |  | 2020-02-10 | 2020-09-30 |  | 2020-12-18 |  | 2020-05-27 |  | 2020-10-01 | 2022-06-30 |  | 2022 | 2022 |  | On time | N/A
Pipeline including CS | TRA-N-1246 | Greece - Italy interconnection | Italy | Snam Rete Gas S.p.A. | Less-Advanced | 2017-04-01 | 2017-07-27 |  | 2017-08-01 | 2020-07-01 |  | 2020-07-01 | 2023-02-01 |  | 2020-07-01 | 2024-04-01 |  | 2024-04-01 |  | 2019-07-01 |  | 2022-11-01 | 2025-07-01 |  | 2025 | 2025
Pipeline including CS | TRA-N-1265 | Biomethane productions interconnection | Italy | Snam Rete Gas S.p.A. | Less-Advanced |  |  | The project is an aggregation of several station construction so it is impossible to give a schedule |  |  | The project is an aggregation of several station construction so it is impossible to give a schedule |  |  | The project is an aggregation of several station construction so it is impossible to give a schedule |  |  | The project is an aggregation of several station construction so it is impossible to give a schedule |  | The project is an aggregation of several station construction so it is impossible to give a schedule |  | The project is an aggregation of several station construction so it is impossible to give a schedule |  |  | The project is an aggregation of several station construction so it is impossible to give a schedule | 2022 | 2022
Pipeline including CS | TRA-N-1278 | Compressor station at Ambelia | Greece | DESFA S.A. | Less-Advanced |  |  | There was no need for a pre-feasibility study. | 2018-12-31 | 2019-06-30 |  | 2019-10-30 | 2020-06-30 |  | 2019-11-30 | 2020-11-30 |  | 2020-07-31 |  | 2020-05-04 |  | 2020-12-31 | 2023-03-31 |  | 2023 | 2023

## Capacities
Capacity Created by the Projects
Point Category | Point | From System | To System | Code | Project Name | Promoter | Status | Operator | Commissioning Year | Capacity (GWh/d)
Cross-Border Transmission IP between EU and Non-EU | Slobodnica- Bosanski Brod-Zenica | Transmission Bosnia Herzegovina | Transmission Croatia | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd | Less-Advanced | Plinacro Ltd | 2025 | 162
Cross-Border Transmission IP between EU and Non-EU | Slobodnica- Bosanski Brod-Zenica | Transmission Croatia | Transmission Bosnia Herzegovina | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd | Less-Advanced | Plinacro Ltd | 2025 | 162
Cross-Border Transmission IP between EU and Non-EU | Slobodnica - Sotin (HR) / Bačko Novo Selo (RS) | Transmission Croatia | Transmission Serbia | TRA-A-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Plinacro Ltd | Advanced | Plinacro Ltd | 2023 | 42.11
Cross-Border Transmission IP between EU and Non-EU | Slobodnica - Sotin (HR) / Bačko Novo Selo (RS) | Transmission Serbia | Transmission Croatia | TRA-A-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Plinacro Ltd | Advanced | Plinacro Ltd | 2023 | 54.34
Cross-Border Transmission IP between EU and Non-EU | Slobodnica - Sotin (HR) / Bačko Novo Selo (RS) | Transmission Serbia | Transmission Croatia | TRA-A-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Plinacro Ltd | Less-Advanced | Plinacro Ltd | 2027 | 185.66
Cross-Border Transmission IP between EU and Non-EU | Slobodnica - Sotin (HR) / Bačko Novo Selo (RS) | Transmission Croatia | Transmission Serbia | TRA-A-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Plinacro Ltd | Less-Advanced | Plinacro Ltd | 2027 | 197.89
Cross-Border Transmission IP between EU and Non-EU | Interconnector BG RS | Transmission Serbia | Transmission Bulgaria (NGTS) | TRA-N-137 | Balkan Gas Hub - Interconnection Bulgaria - Serbia | Bulgartransgaz EAD | Less-Advanced | IBS Future Operator | 2022 | 58.5
Cross-Border Transmission IP between EU and Non-EU | Interconnector BG RS | Transmission Bulgaria (NGTS) | Transmission Serbia | TRA-N-137 | Balkan Gas Hub - Interconnection Bulgaria - Serbia | Bulgartransgaz EAD | Less-Advanced | IBS Future Operator | 2022 | 58.5
Cross-Border Transmission IP between EU and Non-EU | Wallbach | Transmission Switzerland | Transmission Germany (NCG) | TRA-F-208 | Reverse Flow TENP Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | FID | Fluxys TENP GmbH & Open Grid Europe GmbH | 2020 | 240
Cross-Border Transmission IP between EU and Non-EU | Slobodnica- Bosanski Brod-Zenica | Transmission Bosnia Herzegovina | Transmission Croatia | TRA-N-224 | Gaspipeline Brod - Zenica | BH-Gas d.o.o. | Less-Advanced | BH Gas d.o.o. | 2025 | 35
Cross-Border Transmission IP between EU and Non-EU | Slobodnica- Bosanski Brod-Zenica | Transmission Croatia | Transmission Bosnia Herzegovina | TRA-N-224 | Gaspipeline Brod - Zenica | BH-Gas d.o.o. | Less-Advanced | BH Gas d.o.o. | 2025 | 162
Cross-Border Transmission IP between EU and Non-EU | Strandzha (BG) / Malkoclar (TR) | Transmission Bulgarian Transit Bulgaria (GTNTT) | Transmission Turkey (Exports) | TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | Bulgartransgaz EAD | FID | Bulgartransgaz EAD | 2021 | 58.08
Cross-Border Transmission IP between EU and Non-EU | Interconnector BG RS | Transmission Bulgaria (NGTS) | Transmission Serbia | TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | Bulgartransgaz EAD | FID | IBS Future Operator | 2024 | 19.36
Cross-Border Transmission IP between EU and Non-EU | Interconnector BG RS | Transmission Serbia | Transmission Bulgaria (NGTS) | TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | Bulgartransgaz EAD | FID | IBS Future Operator | 2024 | 19.36
Cross-Border Transmission IP between EU and Non-EU | Posušje | Transmission Bosnia Herzegovina | Transmission Ionic-Adriatic Pipeline Croatia | TRA-A-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Plinacro Ltd | Advanced | Plinacro Ltd | 2023 | 81
Cross-Border Transmission IP between EU and Non-EU | Posušje | Transmission Ionic-Adriatic Pipeline Croatia | Transmission Bosnia Herzegovina | TRA-A-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Plinacro Ltd | Advanced | Plinacro Ltd | 2023 | 81
Cross-Border Transmission IP between EU and Non-EU | Rakovica (HR) / Trzac (BA) | Transmission Croatia | Transmission Bosnia Herzegovina | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd | Less-Advanced | Plinacro Ltd | 2026 | 81
Cross-Border Transmission IP between EU and Non-EU | Rakovica (HR) / Trzac (BA) | Transmission Bosnia Herzegovina | Transmission Croatia | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd | Less-Advanced | Plinacro Ltd | 2026 | 81
Cross-Border Transmission IP between EU and Non-EU | Ungheni | Transmission Romania | Transmission Moldavia | TRA-F-357 | NTS developments in North-East Romania | SNTGN Transgaz SA | FID | SNTGN Transgaz S.A. | 2021 | 42.11
Cross-Border Transmission IP between EU and Non-EU | PL>UA Interconnector | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Ukraine (Exports) | TRA-A-561 | Poland-Ukraine Interconnector (Ukrainian section) | PJSC UKRTRANSGAZ | Advanced | Ukrtransgaz | 2022 | 153.2
Cross-Border Transmission IP between EU and Non-EU | Kirevo (BG) / Serbia (RS) | Transmission Bulgaria (NGTS) | Transmission Serbia | TRA-F-592 | Balkan Gas Hub-Necessary expansion of the Bulgarian gas transmission system | Bulgartransgaz EAD | FID | Bulgartransgaz EAD | 2022 | 395.2
Cross-Border Transmission IP between EU and Non-EU | PL>UA Interconnector | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Ukraine (Exports) | TRA-A-621 | Poland - Ukraine Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | GAZ-SYSTEM S.A. | 2022 | 153.2
Cross-Border Transmission IP between EU and Non-EU | Eastring Cross-Border BG/EAR>TR | Transmission Eastring Bulgaria | Transmission Turkey (Exports) | TRA-A-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Less-Advanced | Bulgartransgaz EAD | 2030 | 617
Cross-Border Transmission IP between EU and Non-EU | Eastring Cross-Border BG/EAR>TR | Transmission Eastring Bulgaria | Transmission Turkey (Exports) | TRA-A-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Advanced | Bulgartransgaz EAD | 2025 | 617
Cross-Border Transmission IP between EU and Non-EU | Posušje | Transmission Bosnia Herzegovina | Transmission Ionic-Adriatic Pipeline Croatia | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | BH-GAS d.o.o. | Less-Advanced | BH Gas d.o.o. | 2023 | 38
Cross-Border Transmission IP between EU and Non-EU | Posušje | Transmission Ionic-Adriatic Pipeline Croatia | Transmission Bosnia Herzegovina | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | BH-GAS d.o.o. | Less-Advanced | BH Gas d.o.o. | 2023 | 73
Cross-Border Transmission IP between EU and Non-EU | Rakovica (HR) / Trzac (BA) | Transmission Croatia | Transmission Bosnia Herzegovina | TRA-N-910 | West Interconnection BiH/CRO | BH-Gas d.o.o. | Less-Advanced | BH Gas d.o.o. | 2026 | 73
Cross-Border Transmission IP between EU and Non-EU | Rakovica (HR) / Trzac (BA) | Transmission Bosnia Herzegovina | Transmission Croatia | TRA-N-910 | West Interconnection BiH/CRO | BH-Gas d.o.o. | Less-Advanced | BH Gas d.o.o. | 2026 | 73
Cross-Border Transmission IP between EU and Non-EU | Stojakovo village (MK) / Pontoiraklia (GR) | Transmission Greece | Transmission former Yugoslav Republic of Macedonia | TRA-A-967 | Nea-Messimvria to Evzoni/Gevgelija pipeline (IGNM) | DESFA S.A. | Advanced | DESFA S.A. | 2022 | 76.5
Cross-Border Transmission IP between EU and Non-EU | Stojakovo village (MK) / Pontoiraklia (GR) | Transmission Greece | Transmission former Yugoslav Republic of Macedonia | TRA-A-980 | Interconnection North Macedonia-Greece (North Macedonian part) | MER JSC Skopje | Advanced | MER JSC Skopje | 2022 | 76.5
Cross-Border Transmission IP between EU and Non-EU | Fier (AL) / (GR) | Transmission Trans-Adriatic Pipeline Albania | Transmission Albania | TRA-A-1303 | IAEF - Vlora ccgt | Albgaz Sha | Advanced | Albgaz Sha | 2020 | 0.012
Cross-Border Transmission IP between EU and Non-EU (import) | Kipi (TR) / Kipi (GR) | Transmission Turkey (Imports) | Transmission Greece (Komotini) | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | IGI Poseidon S.A. | 2025 | 150
Cross-Border Transmission IP between EU and Non-EU (import) | Kipi (TR) / Kipi (GR) | Transmission Turkey (Imports) | Transmission Greece (Komotini) | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | IGI Poseidon S.A. | 2022 | 480
Cross-Border Transmission IP between EU and Non-EU (import) | Koudiet Eddraouch (Galsi) (DZ) | Transmission Algeria | Transmission GALSI Algeria (International) | TRA-A-12 | GALSI Pipeline Project | Galsi S.p.A. | Advanced | Galsi S.p.A. | 2022 | 258
Cross-Border Transmission IP between EU and Non-EU (import) | Kipi (TR) / Kipi (TAP) | Transmission Trans-Anatolian Pipeline Turkey | Transmission Trans-Adriatic Pipeline Greece | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Trans-Adriatic Pipeline AG | 2020 | 350
Cross-Border Transmission IP between EU and Non-EU (import) | Kipi (TR) / Kipi (TAP) | Transmission Trans-Adriatic Pipeline Greece | Transmission Trans-Anatolian Pipeline Turkey | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Trans-Adriatic Pipeline AG | 2020 | 331
Cross-Border Transmission IP between EU and Non-EU (import) | Constanta (White Stream) | Transmission Georgia (White Stream) | Transmission Romania | TRA-N-53 | White Stream | White Stream Ltd | Less-Advanced | White Stream | 2023 | 505
Cross-Border Transmission IP between EU and Non-EU (import) | Kipi (TR) / Kipi (GR) | Transmission Turkey (Imports) | Transmission Greece (Komotini) | TRA-N-128 | Compressor Station Kipi | DESFA S.A. | Less-Advanced | DESFA S.A. | 2024 | 54.4
Cross-Border Transmission IP between EU and Non-EU (import) | Siret (RO) / Khotyn (UA) | Transmission Romania | Transmission Ukraine (Exports) | TRA-N-502 | Interconnector Romania - Ukraine | Joint-Stock Company | Less-Advanced | Ukrtransgaz | 2025 | 58.1
Cross-Border Transmission IP between EU and Non-EU (import) | Siret (RO) / Khotyn (UA) | Transmission Ukraine | Transmission Romania | TRA-N-502 | Interconnector Romania - Ukraine | Joint-Stock Company | Less-Advanced | Ukrtransgaz | 2025 | 87.1
Cross-Border Transmission IP between EU and Non-EU (import) | UA>PL Interconnector | Transmission Ukraine | Transmission Poland (VTP - GAZ-SYSTEM) | TRA-A-561 | Poland-Ukraine Interconnector (Ukrainian section) | PJSC UKRTRANSGAZ | Advanced | Ukrtransgaz | 2022 | 153.2
Cross-Border Transmission IP between EU and Non-EU (import) | Malkoclar (TR) > Strandzha (BG) | Transmission Turkey (Imports) | Transmission Bulgarian Transit Bulgaria (GTNTT) | TRA-F-592 | Balkan Gas Hub-Necessary expansion of the Bulgarian gas transmission system | Bulgartransgaz EAD | FID | Bulgartransgaz EAD | 2020 | 567.43
Cross-Border Transmission IP between EU and Non-EU (import) | Siret (RO) / Khotyn (UA) | Transmission Ukraine | Transmission Romania | TRA-N-596 | Interconnection between the RO and the UA gas transmission systems | SNTGN Transgaz SA | Less-Advanced | SNTGN Transgaz S.A. | 2025 | 87.1
Cross-Border Transmission IP between EU and Non-EU (import) | Siret (RO) / Khotyn (UA) | Transmission Romania | Transmission Ukraine (Exports) | TRA-N-596 | Interconnection between the RO and the UA gas transmission systems | SNTGN Transgaz SA | Less-Advanced | SNTGN Transgaz S.A. | 2025 | 58.1
Cross-Border Transmission IP between EU and Non-EU (import) | VIP Mediesu Aurit - Isaccea (RO-UA) | Transmission Romania | Transmission Ukraine (Exports) | TRA-N-598 | NTS developments in North-Vest Romania | SNTGN Transgaz SA | Less-Advanced | SNTGN Transgaz S.A. | 2026 | 77.18
Cross-Border Transmission IP between EU and Non-EU (import) | UA>PL Interconnector | Transmission Ukraine | Transmission Poland (VTP - GAZ-SYSTEM) | TRA-A-621 | Poland - Ukraine Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | GAZ-SYSTEM S.A. | 2022 | 153.2
Cross-Border Transmission IP between EU and Non-EU (import) | Eastring Cross-Border TR>BG/EAR | Transmission Turkey (Imports) | Transmission Eastring Bulgaria | TRA-A-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Less-Advanced | Bulgartransgaz EAD | 2030 | 617
Cross-Border Transmission IP between EU and Non-EU (import) | Eastring Cross-Border TR>BG/EAR | Transmission Turkey (Imports) | Transmission Eastring Bulgaria | TRA-A-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Advanced | Bulgartransgaz EAD | 2025 | 617
Cross-Border Transmission IP between EU and Non-EU (import) | Lubmin II | Transmission Nord Stream 2 Russia | Transmission Germany (GASPOOL) | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | FID | GASCADE Gastransport GmbH | 2019 | 962.42
Cross-Border Transmission IP between EU and Non-EU (import) | Lubmin II | Transmission Nord Stream 2 Russia | Transmission Germany (GASPOOL) | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | FID | GASCADE Gastransport GmbH | 2020 | 778.94
Cross-Border Transmission IP between EU and Non-EU (import) | Kipi (TR) / Kipi (TAP) | Transmission Trans-Anatolian Pipeline Turkey | Transmission Trans-Adriatic Pipeline Greece | TRA-A-782 | TANAP X- Expansion of Trans Anatolian Natural Gas Pipeline Projec | SOCAR (The State Oil Company of the Azerbaijan Republic) | Advanced | TANAP TSO | 2025 | 286
Cross-Border Transmission IP between EU and Non-EU (import) | Kipi (TR) / Kipi (TAP) | Transmission Trans-Anatolian Pipeline Turkey | Transmission Trans-Adriatic Pipeline Greece | TRA-N-810 | TAP Expansion | Trans Adriatic Pipeline AG | Less-Advanced | Trans-Adriatic Pipeline AG | 2025 | 233
Cross-Border Transmission IP between EU and Non-EU (import) | Lubmin II | Transmission Nord Stream 2 Russia | Transmission Germany (GASPOOL) | TRA-F-937 | Nord Stream 2 | Nord Stream 2 AG | FID | Nord Stream 2 AG | 2019 | 1750
Cross-Border Transmission IP between EU and Non-EU (import) | Kipi (TR) / Kipi (GR) | Transmission Turkey (Imports) | Transmission Greece (Komotini) | TRA-N-1129 | Compressor Station Kipi Increment | DESFA S.A. | Less-Advanced | DESFA S.A. | 2024 | 275.2
Cross-Border Transmission IP between EU and Non-EU (import) | RO/SB IP | Transmission Serbia | Transmission Romania | TRA-A-1268 | Romania-Serbia Interconnection | SNTGN Tranzgaz SA | Advanced | SNTGN Transgaz S.A. | 2020 | 46.27
Cross-Border Transmission IP between EU and Non-EU (import) | RO/SB IP | Transmission Romania | Transmission Serbia | TRA-A-1268 | Romania-Serbia Interconnection | SNTGN Tranzgaz SA | Advanced | SNTGN Transgaz S.A. | 2020 | 46.27
Cross-Border Transmission IP between EU and Non-EU (import) | Isaccea (RO) - Orlovka (UA) I | Transmission Trans-Balkan Pipeline Romania | Transmission Ukraine | TRA-F-1277 | Upgrading GMS Isaccea 1 and GMS Negru Voda 1 | SNTGN Transgaz SA | FID | SNTGN Transgaz S.A. | 2021 | 28.92
Cross-Border Transmission IP Non-EU | Ionic-Adriatic Pipeline - IAP / ME | Transmission Ionic-Adriatic Pipeline Croatia | Transmission Montenegro | TRA-A-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced | Plinacro Ltd | 2025 | 16.6
Cross-Border Transmission IP Non-EU | Ionic-Adriatic Pipeline - IAP / AB | Transmission Ionic-Adriatic Pipeline Croatia | Transmission Albania | TRA-A-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced | Plinacro Ltd | 2025 | 33.3
Cross-Border Transmission IP Non-EU | TCP/SCP | Transmission Turkmenistan | Transmission South Caucasus Pipeline Azerbaijan | TRA-A-339 | Trans-Caspian | W-Stream Caspian Pipeline Company OU | Advanced | W-Stream Caspian Pipeline Company OU | 2023 | 505
Cross-Border Transmission IP Non-EU | TCP/SCP | Transmission Turkmenistan | Transmission South Caucasus Pipeline Azerbaijan | TRA-A-339 | Trans-Caspian | W-Stream Caspian Pipeline Company OU | Advanced | W-Stream Caspian Pipeline Company OU | 2022 | 505
Cross-Border Transmission IP Non-EU | Türkgözü | Transmission South Caucasus Pipeline Georgia | Transmission Trans-Anatolian Pipeline Turkey | TRA-A-782 | TANAP X- Expansion of Trans Anatolian Natural Gas Pipeline Projec | SOCAR (The State Oil Company of the Azerbaijan Republic) | Advanced | TANAP TSO | 2025 | 286
Cross-Border Transmission IP Non-EU | Türkgözü | Transmission South Caucasus Pipeline Georgia | Transmission Trans-Anatolian Pipeline Turkey | TRA-N-1138 | South Caucasus Pipeline Future Expansion (SCPFX) | SOCAR Midstream Operations LLC | Less-Advanced | SOCAR Midstream Operations | 2024 | 150.7
Cross-Border Transmission IP Non-EU | Grebenyky | Transmission Ukraine | Transmission Moldavia | TRA-N-1169 | Trans-Balkan Bi-directional Flow | JSC "UKRTRANSGAZ" | FID | Ukrtransgaz | 2020 | 43.1
Cross-Border Transmission IP within EU | Komotini (DESFA) - GR / IGB | Transmission Greece (Komotini) | Transmission Interconnector Greece-Bulgaria Bulgaria | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | IGI Poseidon S.A. | 2022 | 90
Cross-Border Transmission IP within EU | Otranto - IT / IGI Poseidon | Transmission Italy (PSV) (Southern Projects) | Transmission ITGI Poseidon Greece | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | IGI Poseidon S.A. | 2022 | 160
Cross-Border Transmission IP within EU | Otranto - IT / IGI Poseidon | Transmission ITGI Poseidon Greece | Transmission Italy (PSV) (Southern Projects) | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | IGI Poseidon S.A. | 2025 | 250
Cross-Border Transmission IP within EU | Otranto - IT / IGI Poseidon | Transmission ITGI Poseidon Greece | Transmission Italy (PSV) (Southern Projects) | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | IGI Poseidon S.A. | 2022 | 380
Cross-Border Transmission IP within EU | East Med / Thesprotia (Poseidon) | Transmission East Med Greece | Transmission ITGI Poseidon Greece | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | IGI Poseidon S.A. | 2025 | 320
Cross-Border Transmission IP within EU | Komotini (DESFA) - GR / IGB | Transmission Greece (Komotini) | Transmission Interconnector Greece-Bulgaria Bulgaria | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | IGI Poseidon S.A. | 2025 | 65
Cross-Border Transmission IP within EU | Porto Botte (Galsi) | Transmission GALSI Algeria (International) | Transmission Italy (Sardinia) | TRA-A-12 | GALSI Pipeline Project | Galsi S.p.A. | Advanced | Galsi S.p.A. | 2022 | 258
Cross-Border Transmission IP within EU | Olbia (Galsi) | Transmission Italy (Sardinia) | Transmission GALSI Italia (National) | TRA-A-12 | GALSI Pipeline Project | Galsi S.p.A. | Advanced | Galsi S.p.A. | 2022 | 258
Cross-Border Transmission IP within EU | Olbia (Galsi) | Transmission GALSI Italia (National) | Transmission Italy (Sardinia) | TRA-A-12 | GALSI Pipeline Project | Galsi S.p.A. | Advanced | Galsi S.p.A. | 2022 | 32
Cross-Border Transmission IP within EU | Piombino (Galsi) | Transmission GALSI Italia (National) | Transmission Italy (PSV) (Southern Projects) | TRA-A-12 | GALSI Pipeline Project | Galsi S.p.A. | Advanced | Galsi S.p.A. | 2022 | 226
Cross-Border Transmission IP within EU | IP Greece - Italy | Transmission Greece | Transmission Italy (PSV) (Southern Projects) | TRA-N-14 | Komotini-Thesprotia pipeline | DESFA S.A. | Less-Advanced | DESFA S.A. | 2025 | 357.7
Cross-Border Transmission IP within EU | Poštorná / Reintal | Transmission Austria (CEGH) | Transmission Czech Republic (VOB) | TRA-A-21 | Bidirectional Austrian-Czech Interconnector (BACI) | GAS CONNECT AUSTRIA GmbH | Advanced | Gas Connect Austria GmbH | 2024 | 201.42
Cross-Border Transmission IP within EU | Poštorná / Reintal | Transmission Czech Republic (VOB) | Transmission Austria (CEGH) | TRA-A-21 | Bidirectional Austrian-Czech Interconnector (BACI) | GAS CONNECT AUSTRIA GmbH | Advanced | Gas Connect Austria GmbH | 2024 | 201.42
Cross-Border Transmission IP within EU | Moffat (NI) | Transmission United Kingdom (North Ireland) | Transmission United Kingdom (NBP) (Moffat) | TRA-N-27 | Physical reverse flow from NI to GB and IE via SNIP pipeline | Premier Transmission Limited | Less-Advanced | Premier Transmission Ltd | 2021 | 131
Cross-Border Transmission IP within EU | Gela (Italy) SRG-MTGP (Malta) Interconnection Point | Transmission Italy (PSV) (Italy Southern Import Fork) | Transmission Malta | TRA-A-31 | Melita TransGas Pipeline | Melita TransGas Co. Ltd. | Advanced | Melita TransGas Co. Ltd. | 2024 | 56
Cross-Border Transmission IP within EU | Gela (Italy) SRG-MTGP (Malta) Interconnection Point | Transmission Malta | Transmission Italy (PSV) (Italy Southern Import Fork) | TRA-A-31 | Melita TransGas Pipeline | Melita TransGas Co. Ltd. | Advanced | Melita TransGas Co. Ltd. | 2024 | 56
Cross-Border Transmission IP within EU | Melendugno - IT / TAP | Transmission Trans-Adriatic Pipeline Albania | Transmission Italy (PSV) (Southern Projects) | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Trans-Adriatic Pipeline AG | 2020 | 291
Cross-Border Transmission IP within EU | Nea Mesimvria | Transmission Trans-Adriatic Pipeline Greece | Transmission Greece | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Trans-Adriatic Pipeline AG | 2020 | 142
Cross-Border Transmission IP within EU | Melendugno - IT / TAP | Transmission Italy (PSV) (Southern Projects) | Transmission Trans-Adriatic Pipeline Albania | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Trans-Adriatic Pipeline AG | 2020 | 272
Cross-Border Transmission IP within EU | Nea Mesimvria | Transmission Greece | Transmission Trans-Adriatic Pipeline Greece | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Trans-Adriatic Pipeline AG | 2020 | 142
Cross-Border Transmission IP within EU | Komotini - TAP / IGB | Transmission Trans-Adriatic Pipeline Greece | Transmission Interconnector Greece-Bulgaria Bulgaria | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Trans-Adriatic Pipeline AG | 2020 | 142
Cross-Border Transmission IP within EU | Trans-Adriatic Pipeline (TAP) / Ionic-Adriatic Pipeline (IAP) | Transmission Trans-Adriatic Pipeline Albania | Transmission Ionic-Adriatic Pipeline Croatia (TAP-IAP Interconnection) | TRA-A-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced | Plinacro Ltd | 2025 | 166.5
Cross-Border Transmission IP within EU | Ionic-Adriatic Pipeline - IAP / Split - HR | Transmission Ionic-Adriatic Pipeline Croatia | Transmission Croatia | TRA-A-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced | Plinacro Ltd | 2023 | 83.2
Cross-Border Transmission IP within EU | Ionic-Adriatic Pipeline - IAP Entry | Transmission Ionic-Adriatic Pipeline Croatia (TAP-IAP Interconnection) | Transmission Ionic-Adriatic Pipeline Croatia | TRA-A-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced | Plinacro Ltd | 2025 | 166.5
Cross-Border Transmission IP within EU | Ionic-Adriatic Pipeline - IAP / Split - HR | Transmission Croatia | Transmission Ionic-Adriatic Pipeline Croatia | TRA-A-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced | Plinacro Ltd | 2025 | 116.6
Cross-Border Transmission IP within EU | Dravaszerdahely | Transmission Croatia | Transmission Hungary (MGP) | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd | Less-Advanced | Plinacro Ltd | 2027 | 54.34
Cross-Border Transmission IP within EU | Rogatec | Transmission Croatia | Transmission Slovenia | TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla) | Plinacro Ltd | Advanced | Plinacro Ltd | 2021 | 40.76
Cross-Border Transmission IP within EU | Rogatec | Transmission Slovenia | Transmission Croatia | TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla) | Plinacro Ltd | Advanced | Plinacro Ltd | 2023 | 162
Cross-Border Transmission IP within EU | Rogatec | Transmission Croatia | Transmission Slovenia | TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla) | Plinacro Ltd | Advanced | Plinacro Ltd | 2023 | 121.24
Cross-Border Transmission IP within EU | Dravaszerdahely | Transmission Croatia | Transmission Hungary (MGP) | TRA-F-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Plinacro Ltd | FID | Plinacro Ltd | 2020 | 40.76
Cross-Border Transmission IP within EU | Gorizia (IT) /Šempeter (SI) | Transmission Slovenia | Transmission Italia (PSV) | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Plinovodi d.o.o. | Less-Advanced | Plinovodi d.o.o. | 2025 | 0
Cross-Border Transmission IP within EU | Gorizia (IT) /Šempeter (SI) | Transmission Italia (PSV) | Transmission Slovenia | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Plinovodi d.o.o. | Less-Advanced | Plinovodi d.o.o. | 2025 | 0
Cross-Border Transmission IP within EU | Pince (SI) / Tornyszentmiklos (HU) | Transmission Slovenia | Transmission Hungary (MGP) | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. | Less-Advanced | Plinovodi d.o.o. | 2023 | 12.9
Cross-Border Transmission IP within EU | Pince (SI) / Tornyszentmiklos (HU) | Transmission Hungary (MGP) | Transmission Slovenia | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. | Less-Advanced | Plinovodi d.o.o. | 2023 | 12.9
Cross-Border Transmission IP within EU | Pince (SI) / Tornyszentmiklos (HU) | Transmission Slovenia | Transmission Hungary (MGP) | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. | Less-Advanced | Plinovodi d.o.o. | 2025 | 36.1
Cross-Border Transmission IP within EU | Pince (SI) / Tornyszentmiklos (HU) | Transmission Hungary (MGP) | Transmission Slovenia | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. | Less-Advanced | Plinovodi d.o.o. | 2025 | 36.1
Cross-Border Transmission IP within EU | Poštorná / Reintal | Transmission Austria (CEGH) | Transmission Czech Republic (VOB) | TRA-A-133 | Bidirectional Austrian Czech Interconnection (BACI) | NET4GAS, s.r.o. | Advanced | NET4GAS, s.r.o. | 2024 | 201.42
Cross-Border Transmission IP within EU | Poštorná / Reintal | Transmission Czech Republic (VOB) | Transmission Austria (CEGH) | TRA-A-133 | Bidirectional Austrian Czech Interconnection (BACI) | NET4GAS, s.r.o. | Advanced | NET4GAS, s.r.o. | 2024 | 201.42
Cross-Border Transmission IP within EU | Hať | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Czech Republic (VOB) | TRA-A-136 | Czech-Polish Gas Interconnector (CPI) | NET4GAS, s.r.o. | Advanced | NET4GAS, s.r.o. | 2023 | 153.2
Cross-Border Transmission IP within EU | Hať | Transmission Czech Republic (VOB) | Transmission Poland (VTP - GAZ-SYSTEM) | TRA-A-136 | Czech-Polish Gas Interconnector (CPI) | NET4GAS, s.r.o. | Advanced | NET4GAS, s.r.o. | 2023 | 219.1
Cross-Border Transmission IP within EU | VIP PIRINEOS | Transmission France (NS4) | Transmission Spain (MS-ATR) | TRA-A-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagas Transporte S.A.U. | Advanced | Enagas Transporte S.A.U. | 2024 | 110
Cross-Border Transmission IP within EU | VIP PIRINEOS | Transmission Spain (MS-ATR) | Transmission France (NS4) | TRA-A-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagas Transporte S.A.U. | Advanced | Enagas Transporte S.A.U. | 2024 | 120
Cross-Border Transmission IP within EU | VIP IBERICO | Transmission Portugal | Transmission Spain (MS-ATR) | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagas Transporte S.A.U. | Less-Advanced | Enagas Transporte S.A.U. | 2025 | 70
Cross-Border Transmission IP within EU | VIP IBERICO | Transmission Spain (MS-ATR) | Transmission Portugal | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagas Transporte S.A.U. | Less-Advanced | Enagas Transporte S.A.U. | 2025 | 70
Cross-Border Transmission IP within EU | Interconnector PL - SK | Transmission Slovakia | Transmission Poland (VTP - GAZ-SYSTEM) | TRA-F-190 | Poland - Slovakia interconnection | eustream,a.s. (a joint-stock company) | FID | eustream, a.s. | 2021 | 174.59
Cross-Border Transmission IP within EU | Interconnector PL - SK | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Slovakia | TRA-F-190 | Poland - Slovakia interconnection | eustream,a.s. (a joint-stock company) | FID | eustream, a.s. | 2021 | 143.96
Cross-Border Transmission IP within EU | Interconnector PL-LT | Transmission Lithuania | Transmission Poland (VTP - GAZ-SYSTEM) | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. | FID | GAZ-SYSTEM S.A. | 2021 | 58.3
Cross-Border Transmission IP within EU | Interconnector PL-LT | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Lithuania | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. | FID | GAZ-SYSTEM S.A. | 2021 | 73.9
Cross-Border Transmission IP within EU | VIP PIRINEOS | Transmission France (NS4) | Transmission Spain (MS-ATR) | TRA-A-252 | South Transit East Pyrenees (STEP) - TEREGA | TEREGA | Advanced | TERÉGA | 2024 | 0
Cross-Border Transmission IP within EU | VIP PIRINEOS | Transmission Spain (MS-ATR) | Transmission France (NS4) | TRA-A-252 | South Transit East Pyrenees (STEP) - TEREGA | TEREGA | Advanced | TERÉGA | 2024 | 0
Cross-Border Transmission IP within EU | Interconnector PL-DK | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Denmark | TRA-A-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | GAZ-SYSTEM S.A. | Advanced | GAZ-SYSTEM S.A. | 2022 | 91.1
Cross-Border Transmission IP within EU | Interconnector PL-DK | Transmission Denmark | Transmission Poland (VTP - GAZ-SYSTEM) | TRA-A-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | GAZ-SYSTEM S.A. | Advanced | GAZ-SYSTEM S.A. | 2022 | 306.8
Cross-Border Transmission IP within EU | Hať | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Czech Republic (VOB) | TRA-A-273 | Poland - Czech Republic Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | GAZ-SYSTEM S.A. | 2023 | 153.2
Cross-Border Transmission IP within EU | Hať | Transmission Czech Republic (VOB) | Transmission Poland (VTP - GAZ-SYSTEM) | TRA-A-273 | Poland - Czech Republic Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | GAZ-SYSTEM S.A. | 2023 | 219.1
Cross-Border Transmission IP within EU | Interconnector PL - SK | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Slovakia | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | FID | GAZ-SYSTEM S.A. | 2021 | 143.9
Cross-Border Transmission IP within EU | Interconnector PL - SK | Transmission Slovakia | Transmission Poland (VTP - GAZ-SYSTEM) | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | FID | GAZ-SYSTEM S.A. | 2021 | 174.5
Cross-Border Transmission IP within EU | VIP IBERICO | Transmission Portugal | Transmission Spain (MS-ATR) | TRA-A-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. | Advanced | REN - Gasodutos, S.A. | 2025 | 70
Cross-Border Transmission IP within EU | VIP IBERICO | Transmission Spain (MS-ATR) | Transmission Portugal | TRA-A-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. | Advanced | REN - Gasodutos, S.A. | 2025 | 85
Cross-Border Transmission IP within EU | Csanadpalota | Transmission Romania | Transmission Hungary (MGP) | TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | FGSZ Ltd. | FID | FGSZ Ltd. | 2019 | 48.9
Cross-Border Transmission IP within EU | Kulata (BG) / Sidirokastron (GR) | Transmission Bulgarian Transit Bulgaria (GTNTT) | Transmission Greece | TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | Bulgartransgaz EAD | FID | Bulgartransgaz EAD | 2021 | 13.78
Cross-Border Transmission IP within EU | Gorizia (IT) /Šempeter (SI) | Transmission Italia (PSV) | Transmission Slovenia | TRA-N-299 | M3/1 Šempeter - Vodice | Plinovodi d.o.o. | Less-Advanced | Plinovodi d.o.o. | 2026 | 49
Cross-Border Transmission IP within EU | Gorizia (IT) /Šempeter (SI) | Transmission Slovenia | Transmission Italia (PSV) | TRA-N-299 | M3/1 Šempeter - Vodice | Plinovodi d.o.o. | Less-Advanced | Plinovodi d.o.o. | 2026 | 51.6
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) | TRA-F-307 | H-gas exit OSZ GTG Nord | Gasunie Transport Services B.V. | FID | Gasunie Transport Services B.V. | 2027 | 76.2
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) | TRA-F-307 | H-gas exit OSZ GTG Nord | Gasunie Transport Services B.V. | FID | Gasunie Transport Services B.V. | 2020 | 25.4
Cross-Border Transmission IP within EU | Pince (SI) / Tornyszentmiklos (HU) | Transmission Slovenia | Transmission Hungary (MGP) | TRA-N-325 | Slovenian-Hungarian interconnector | FGSZ Ltd. | Less-Advanced | FGSZ Ltd. | 2023 | 12.8
Cross-Border Transmission IP within EU | Pince (SI) / Tornyszentmiklos (HU) | Transmission Hungary (MGP) | Transmission Slovenia | TRA-N-325 | Slovenian-Hungarian interconnector | FGSZ Ltd. | Less-Advanced | FGSZ Ltd. | 2023 | 12.8
Cross-Border Transmission IP within EU | Pince (SI) / Tornyszentmiklos (HU) | Transmission Hungary (MGP) | Transmission Slovenia | TRA-N-325 | Slovenian-Hungarian interconnector | FGSZ Ltd. | Less-Advanced | FGSZ Ltd. | 2025 | 46.5
Cross-Border Transmission IP within EU | Pince (SI) / Tornyszentmiklos (HU) | Transmission Slovenia | Transmission Hungary (MGP) | TRA-N-325 | Slovenian-Hungarian interconnector | FGSZ Ltd. | Less-Advanced | FGSZ Ltd. | 2025 | 46.5
Cross-Border Transmission IP within EU | East Med / Cyprus (CY) | Transmission East Med Greece | Transmission Cyprus | TRA-A-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | IGI Poseidon S.A. | 2025 | 30
Cross-Border Transmission IP within EU | East Med / Peloponnesus (GR) | Transmission East Med Greece | Transmission Greece | TRA-A-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | IGI Poseidon S.A. | 2025 | 90
Cross-Border Transmission IP within EU | East Med / Crete (GR) | Transmission East Med Greece | Transmission Greece (Crete) | TRA-A-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | IGI Poseidon S.A. | 2025 | 20
Cross-Border Transmission IP within EU | East Med / Thesprotia (Poseidon) | Transmission ITGI Poseidon Greece | Transmission East Med Greece | TRA-A-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | IGI Poseidon S.A. | 2025 | 350
Cross-Border Transmission IP within EU | East Med / Crete (GR) | Transmission Greece (Crete) | Transmission East Med Greece | TRA-A-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | IGI Poseidon S.A. | 2025 | 190
Cross-Border Transmission IP within EU | Dravaszerdahely | Transmission Croatia | Transmission Hungary (MGP) | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | Plinacro Ltd | FID | Plinacro Ltd | 2019 | 13.6
Cross-Border Transmission IP within EU | Sečovlje (SI) / Plovanija (HR) | Transmission Croatia | Transmission Slovenia | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Plinacro Ltd | Less-Advanced | Plinacro Ltd | 2029 | 16.2
Cross-Border Transmission IP within EU | Sečovlje (SI) / Plovanija (HR) | Transmission Slovenia | Transmission Croatia | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Plinacro Ltd | Less-Advanced | Plinacro Ltd | 2029 | 16.2
Cross-Border Transmission IP within EU | Interconnector PL-LT | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Lithuania | TRA-F-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | AB Amber Grid | FID | AB Amber Grid | 2021 | 73.9
Cross-Border Transmission IP within EU | Interconnector PL-LT | Transmission Lithuania | Transmission Poland (VTP - GAZ-SYSTEM) | TRA-F-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | AB Amber Grid | FID | AB Amber Grid | 2021 | 58.3
Cross-Border Transmission IP within EU | Kiemenai | Transmission Latvia | Transmission Lithuania | TRA-A-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | AB Amber Grid | Advanced | AB Amber Grid | 2023 | 54.43
Cross-Border Transmission IP within EU | Kiemenai | Transmission Lithuania | Transmission Latvia | TRA-A-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | AB Amber Grid | Advanced | AB Amber Grid | 2023 | 62.87
Cross-Border Transmission IP within EU | San Dorligo della Valle (IT) /Osp (SI) | Transmission Italia (PSV) | Transmission Slovenia | TRA-N-354 | Interconnection with Slovenia | Snam Rete Gas S.p.A. | Less-Advanced | Snam Rete Gas S.p.A. | 2023 | 3.6
Cross-Border Transmission IP within EU | Csanadpalota | Transmission Romania | Transmission Hungary (MGP) | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase I | SNTGN Transgaz S.A. | FID | SNTGN Transgaz S.A. | 2020 | 47.75
Cross-Border Transmission IP within EU | Ruse (BG) / Giurgiu (RO) | Transmission Romania | Transmission Bulgaria (NGTS) | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase I | SNTGN Transgaz S.A. | FID | SNTGN Transgaz S.A. | 2020 | 43.15
Cross-Border Transmission IP within EU | Murfeld (AT) / Ceršak (SI) | Transmission Austria (CEGH) | Transmission Slovenia | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | GAS CONNECT AUSTRIA GmbH | Less-Advanced | Gas Connect Austria GmbH | 2023 | 105.2
Cross-Border Transmission IP within EU | Murfeld (AT) / Ceršak (SI) | Transmission Slovenia | Transmission Austria (CEGH) | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | GAS CONNECT AUSTRIA GmbH | Less-Advanced | Gas Connect Austria GmbH | 2023 | 166.5
Cross-Border Transmission IP within EU | Csanadpalota | Transmission Hungary (MGP) | Transmission Romania | TRA-A-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | FGSZ Ltd. | Advanced | FGSZ Ltd. | 2022 | 76.5
Cross-Border Transmission IP within EU | Csanadpalota | Transmission Romania | Transmission Hungary (MGP) | TRA-A-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | FGSZ Ltd. | Advanced | FGSZ Ltd. | 2022 | 76.5
Cross-Border Transmission IP within EU | Stara Zagora - IGB / BG | Transmission Interconnector Greece-Bulgaria Bulgaria | Transmission Bulgaria (NGTS) | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | FID | ICGB a.d. | 2020 | 90
Cross-Border Transmission IP within EU | Komotini (DESFA) - GR / IGB | Transmission Greece (Komotini) | Transmission Interconnector Greece-Bulgaria Bulgaria | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | FID | ICGB a.d. | 2025 | 60
Cross-Border Transmission IP within EU | Komotini (DESFA) - GR / IGB | Transmission Greece (Komotini) | Transmission Interconnector Greece-Bulgaria Bulgaria | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | FID | ICGB a.d. | 2020 | 90
Cross-Border Transmission IP within EU | Komotini - TAP / IGB | Transmission Trans-Adriatic Pipeline Greece | Transmission Interconnector Greece-Bulgaria Bulgaria | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | FID | ICGB a.d. | 2020 | 90
Cross-Border Transmission IP within EU | Stara Zagora - IGB / BG | Transmission Interconnector Greece-Bulgaria Bulgaria | Transmission Bulgaria (NGTS) | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | FID | ICGB a.d. | 2025 | 60
Cross-Border Transmission IP within EU | Komotini - TAP / IGB | Transmission Trans-Adriatic Pipeline Greece | Transmission Interconnector Greece-Bulgaria Bulgaria | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | FID | ICGB a.d. | 2025 | 60
Cross-Border Transmission IP within EU | Kiemenai | Transmission Lithuania | Transmission Latvia | TRA-A-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | JSC "Conexus Baltic Grid" | Advanced | Conexus Baltic Grid | 2023 | 62.87
Cross-Border Transmission IP within EU | Kiemenai | Transmission Latvia | Transmission Lithuania | TRA-A-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | JSC "Conexus Baltic Grid" | Advanced | Conexus Baltic Grid | 2023 | 54.43
Cross-Border Transmission IP within EU | Murfeld (AT) / Ceršak (SI) | Transmission Slovenia | Transmission Austria (CEGH) | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Plinovodi d.o.o. | Less-Advanced | Plinovodi d.o.o. | 2023 | 162
Cross-Border Transmission IP within EU | Murfeld (AT) / Ceršak (SI) | Transmission Austria (CEGH) | Transmission Slovenia | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Plinovodi d.o.o. | Less-Advanced | Plinovodi d.o.o. | 2023 | 78.5
Cross-Border Transmission IP within EU | Rogatec | Transmission Croatia | Transmission Slovenia | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Plinovodi d.o.o. | Less-Advanced | Plinovodi d.o.o. | 2023 | 121.24
Cross-Border Transmission IP within EU | Rogatec | Transmission Croatia | Transmission Slovenia | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Plinovodi d.o.o. | Less-Advanced | Plinovodi d.o.o. | 2021 | 40.76
Cross-Border Transmission IP within EU | Rogatec | Transmission Slovenia | Transmission Croatia | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Plinovodi d.o.o. | Less-Advanced | Plinovodi d.o.o. | 2023 | 162
Cross-Border Transmission IP within EU | Mosonmagyarovar | Transmission Hungary (MGP) | Transmission Austria (CEGH) | TRA-N-423 | GCA Mosonmagyaróvár | GAS CONNECT AUSTRIA GmbH | Less-Advanced | Gas Connect Austria GmbH | 2024 | 153.1
Cross-Border Transmission IP within EU | Blaregnies L (BE) / Taisnières B (FR) | Transmission Belgium (L-Zone) | Transmission France (FR PEG North L-Gas) | TRA-A-429 | Adaptation L- gas - H-gas | GRTgaz and Storengy | Advanced | GRTgaz | 2025 | -115
Cross-Border Transmission IP within EU | Zone Oude Statenzijl H | Transmission Germany (GASPOOL) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | TRA-A-496 | Increase of Gas Transport to the Netherlands | Gasunie Deutschland Transport Service GmbH | Advanced | Gasunie Deutschland Transport Services GmbH | 2022 | 175.2
Cross-Border Transmission IP within EU | Balassagyarmat (HU) / Velké Zlievce (SK) | Transmission Hungary (MGP) | Transmission Slovakia | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | FGSZ Ltd. | Less-Advanced | FGSZ Ltd. | 2022 | 102
Cross-Border Transmission IP within EU | Balassagyarmat (HU) / Velké Zlievce (SK) | Transmission Slovakia | Transmission Hungary (MGP) | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | FGSZ Ltd. | Less-Advanced | FGSZ Ltd. | 2022 | 26
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Slovakia | Transmission Eastring Hungary (MGP) | TRA-A-628 | Eastring - Slovakia | eustream, a.s. (a joint stock company) | Less-Advanced | Eastring B.V. | 2030 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Slovakia | Transmission Eastring Hungary (MGP) | TRA-A-628 | Eastring - Slovakia | eustream, a.s. (a joint stock company) | Advanced | Eastring B.V. | 2025 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Slovakia | TRA-A-628 | Eastring - Slovakia | eustream, a.s. (a joint stock company) | Less-Advanced | Eastring B.V. | 2030 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Slovakia | TRA-A-628 | Eastring - Slovakia | eustream, a.s. (a joint stock company) | Advanced | Eastring B.V. | 2025 | 617
Cross-Border Transmission IP within EU | Balassagyarmat (HU) / Velké Zlievce (SK) | Transmission Slovakia | Transmission Hungary (MGP) | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | FGSZ Ltd. | Less-Advanced | FGSZ Ltd. | 2022 | 26
Cross-Border Transmission IP within EU | Balassagyarmat (HU) / Velké Zlievce (SK) | Transmission Hungary (MGP) | Transmission Slovakia | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | FGSZ Ltd. | Less-Advanced | FGSZ Ltd. | 2022 | 102
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Romania | Transmission Eastring Bulgaria | TRA-A-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Less-Advanced | Bulgartransgaz EAD | 2030 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Bulgaria | Transmission Eastring Romania | TRA-A-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Less-Advanced | Bulgartransgaz EAD | 2030 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Romania | Transmission Eastring Bulgaria | TRA-A-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Advanced | Bulgartransgaz EAD | 2025 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Bulgaria | Transmission Eastring Romania | TRA-A-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Advanced | Bulgartransgaz EAD | 2025 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Bulgaria | Transmission Eastring Romania | TRA-A-655 | Eastring - Romania | SNTGN Transgaz SA | Less-Advanced | SNTGN Transgaz S.A. | 2030 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Romania | Transmission Eastring Hungary (MGP) | TRA-A-655 | Eastring - Romania | SNTGN Transgaz SA | Less-Advanced | SNTGN Transgaz S.A. | 2030 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Bulgaria | Transmission Eastring Romania | TRA-A-655 | Eastring - Romania | SNTGN Transgaz SA | Advanced | SNTGN Transgaz S.A. | 2025 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Romania | TRA-A-655 | Eastring - Romania | SNTGN Transgaz SA | Less-Advanced | SNTGN Transgaz S.A. | 2030 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Romania | TRA-A-655 | Eastring - Romania | SNTGN Transgaz SA | Advanced | SNTGN Transgaz S.A. | 2025 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Romania | Transmission Eastring Hungary (MGP) | TRA-A-655 | Eastring - Romania | SNTGN Transgaz SA | Advanced | SNTGN Transgaz S.A. | 2025 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Romania | Transmission Eastring Bulgaria | TRA-A-655 | Eastring - Romania | SNTGN Transgaz SA | Advanced | SNTGN Transgaz S.A. | 2025 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Romania | Transmission Eastring Bulgaria | TRA-A-655 | Eastring - Romania | SNTGN Transgaz SA | Less-Advanced | SNTGN Transgaz S.A. | 2030 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Slovakia | Transmission Eastring Hungary (MGP) | TRA-A-656 | Eastring - Hungary | FGSZ Ltd. | Less-Advanced | FGSZ Ltd. | 2030 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Romania | TRA-A-656 | Eastring - Hungary | FGSZ Ltd. | Advanced | FGSZ Ltd. | 2025 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Romania | Transmission Eastring Hungary (MGP) | TRA-A-656 | Eastring - Hungary | FGSZ Ltd. | Advanced | FGSZ Ltd. | 2025 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Slovakia | Transmission Eastring Hungary (MGP) | TRA-A-656 | Eastring - Hungary | FGSZ Ltd. | Advanced | FGSZ Ltd. | 2025 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Slovakia | TRA-A-656 | Eastring - Hungary | FGSZ Ltd. | Advanced | FGSZ Ltd. | 2025 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Romania | Transmission Eastring Hungary (MGP) | TRA-A-656 | Eastring - Hungary | FGSZ Ltd. | Less-Advanced | FGSZ Ltd. | 2030 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Romania | TRA-A-656 | Eastring - Hungary | FGSZ Ltd. | Less-Advanced | FGSZ Ltd. | 2030 | 617
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Slovakia | TRA-A-656 | Eastring - Hungary | FGSZ Ltd. | Less-Advanced | FGSZ Ltd. | 2030 | 617
Cross-Border Transmission IP within EU | VIP Brandov-GASPOOL (N4G) | Transmission Czech Republic (VOB) (Brandov) | Transmission Czech Republic (VOB) | TRA-F-752 | Capacity4Gas – DE/CZ | NET4GAS, s.r.o. | FID | NET4GAS, s.r.o. | 2019 | 665
Cross-Border Transmission IP within EU | VIP Brandov-GASPOOL (N4G) | Transmission Czech Republic (VOB) (Brandov) | Transmission Czech Republic (VOB) | TRA-F-752 | Capacity4Gas – DE/CZ | NET4GAS, s.r.o. | FID | NET4GAS, s.r.o. | 2021 | 454
Cross-Border Transmission IP within EU | VIP Brandov-GASPOOL | Transmission Germany (GASPOOL) | Transmission Czech Republic (VOB) (Brandov) | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | FID | GASCADE Gastransport GmbH | 2022 | 111.92
Cross-Border Transmission IP within EU | Deutschneudorf EUGAL Brandov | Transmission Germany (GASPOOL) | Transmission Czech Republic (VOB) (Brandov) | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | FID | GASCADE Gastransport GmbH | 2020 | 408.95
Cross-Border Transmission IP within EU | VIP Brandov-GASPOOL | Transmission Germany (GASPOOL) | Transmission Czech Republic (VOB) (Brandov) | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | FID | GASCADE Gastransport GmbH | 2019 | 66.48
Cross-Border Transmission IP within EU | Deutschneudorf EUGAL Brandov | Transmission Germany (GASPOOL) | Transmission Czech Republic (VOB) (Brandov) | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | FID | GASCADE Gastransport GmbH | 2019 | 598.36
Cross-Border Transmission IP within EU | Deutschneudorf EUGAL Brandov | Transmission Germany (GASPOOL) | Transmission Czech Republic (VOB) (Brandov) | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | FID | GASCADE Gastransport GmbH | 2022 | -111.92
Cross-Border Transmission IP within EU | Mallnow | Transmission Germany (GASPOOL) | Transmission Yamal Poland (VTP - GAZ-SYSTEM) | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | FID | GASCADE Gastransport GmbH | 2020 | 146.33
Cross-Border Transmission IP within EU | VIP Brandov-GASPOOL | Transmission Germany (GASPOOL) | Transmission Czech Republic (VOB) (Brandov) | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | FID | GASCADE Gastransport GmbH | 2020 | 45.44
Cross-Border Transmission IP within EU | Interconnector PL-DK | Transmission Denmark | Transmission Poland (VTP - GAZ-SYSTEM) | TRA-F-780 | Baltic Pipe project – onshore section in Denmark | Energinet | FID | Energinet | 2022 | 306.8
Cross-Border Transmission IP within EU | Interconnector PL-DK | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Denmark | TRA-F-780 | Baltic Pipe project – onshore section in Denmark | Energinet | FID | Energinet | 2022 | 91.1
Cross-Border Transmission IP within EU | Zone Oude Statenzijl H | Transmission Germany (GASPOOL) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | TRA-A-808 | Additional transport of gas volumes to the Netherlands | Gasunie Deutschland Transport Services GmbH | Advanced | Gasunie Deutschland Transport Services GmbH | 2025 | 175.2
Cross-Border Transmission IP within EU | Zone Oude Statenzijl H | Transmission Germany (GASPOOL) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | TRA-N-809 | Reallocation H-Gas towards NL: Bunde/Oude to Zone Oude Statenzijl H | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Gasunie Deutschland Transport Services GmbH | 2022 | 57.3
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GUD) | Transmission Germany (GASPOOL) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | TRA-N-809 | Reallocation H-Gas towards NL: Bunde/Oude to Zone Oude Statenzijl H | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Gasunie Deutschland Transport Services GmbH | 2022 | -57.3
Cross-Border Transmission IP within EU | Komotini - TAP / IGB | Transmission Trans-Adriatic Pipeline Greece | Transmission Interconnector Greece-Bulgaria Bulgaria | TRA-N-810 | TAP Expansion | Trans Adriatic Pipeline AG | Less-Advanced | Trans-Adriatic Pipeline AG | 2025 | 0
Cross-Border Transmission IP within EU | Nea Mesimvria | Transmission Trans-Adriatic Pipeline Greece | Transmission Greece | TRA-N-810 | TAP Expansion | Trans Adriatic Pipeline AG | Less-Advanced | Trans-Adriatic Pipeline AG | 2025 | 0
Cross-Border Transmission IP within EU | Melendugno - IT / TAP | Transmission Trans-Adriatic Pipeline Albania | Transmission Italy (PSV) (Southern Projects) | TRA-N-810 | TAP Expansion | Trans Adriatic Pipeline AG | Less-Advanced | Trans-Adriatic Pipeline AG | 2025 | 292
Cross-Border Transmission IP within EU | Moffat (IE) | Transmission Ireland (IBP) | Transmission United Kingdom (NBP) (Moffat) | TRA-A-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | Gas Networks Ireland | Advanced | Gas Networks Ireland | 2022 | 139
Cross-Border Transmission IP within EU | Zone Oude Statenzijl H | Transmission Germany (GASPOOL) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | TRA-N-873 | Additional import at Oude StatenZijl area | Gasunie Transport Services B.V. | Less-Advanced | Gasunie Transport Services B.V. | 2025 | 60
Cross-Border Transmission IP within EU | Zone Oude Statenzijl H | Transmission Germany (GASPOOL) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | TRA-N-873 | Additional import at Oude StatenZijl area | Gasunie Transport Services B.V. | Less-Advanced | Gasunie Transport Services B.V. | 2022 | 228
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GUD) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) | TRA-N-882 | Transferring L-gas infrastructure to H-gas | Gasunie Transport Services B.V. | Less-Advanced | Gasunie Transport Services B.V. | 2020 | 57.3
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GUD) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) | TRA-N-882 | Transferring L-gas infrastructure to H-gas | Gasunie Transport Services B.V. | Less-Advanced | Gasunie Transport Services B.V. | 2030 | 135
Cross-Border Transmission IP within EU | Balticonnector / Paldiski (EE) | Transmission Estonia | Transmission Balti Connector Finland | TRA-F-895 | Balticconnector | Elering AS | FID | Elering AS | 2020 | 48
Cross-Border Transmission IP within EU | Balticonnector / Paldiski (EE) | Transmission Balti Connector Finland | Transmission Estonia | TRA-F-895 | Balticconnector | Elering AS | FID | Elering AS | 2020 | 48
Cross-Border Transmission IP within EU | Balticonnector / Paldiski (EE) | Transmission Estonia | Transmission Balti Connector Finland | TRA-F-895 | Balticconnector | Elering AS | FID | Elering AS | 2019 | 32
Cross-Border Transmission IP within EU | Balticonnector / Paldiski (EE) | Transmission Balti Connector Finland | Transmission Estonia | TRA-F-895 | Balticconnector | Elering AS | FID | Elering AS | 2019 | 32
Cross-Border Transmission IP within EU | Lanžhot | Transmission Czech Republic (VOB) | Transmission Slovakia | TRA-F-902 | Capacity increase at IP Lanžhot entry | eustream,a.s. (a joint-stock company) | FID | eustream, a.s. | 2019 | 884
Cross-Border Transmission IP within EU | Karksi | Transmission Estonia | Transmission Latvia | TRA-F-915 | Enhancement of Estonia-Latvia interconnection | Elering AS | FID | Elering AS | 2019 | 105
Cross-Border Transmission IP within EU | Karksi | Transmission Latvia | Transmission Estonia | TRA-F-915 | Enhancement of Estonia-Latvia interconnection | Elering AS | FID | Elering AS | 2019 | 42
Cross-Border Transmission IP within EU | Lanžhot | Transmission Czech Republic (VOB) | Transmission Slovakia | TRA-F-918 | Capacity4Gas – CZ/SK | NET4GAS, s.r.o. | FID | NET4GAS, s.r.o. | 2020 | 333
Cross-Border Transmission IP within EU | Balticonnector / Paldiski (EE) | Transmission Estonia | Transmission Balti Connector Finland | TRA-F-928 | Balticconnector Finnish part | Baltic Connector Oy | FID | Baltic Connector Oy | 2019 | 32
Cross-Border Transmission IP within EU | Balticonnector / Paldiski (EE) | Transmission Balti Connector Finland | Transmission Estonia | TRA-F-928 | Balticconnector Finnish part | Baltic Connector Oy | FID | Baltic Connector Oy | 2019 | 32
Cross-Border Transmission IP within EU | Balticonnector / Paldiski (EE) | Transmission Balti Connector Finland | Transmission Estonia | TRA-F-928 | Balticconnector Finnish part | Baltic Connector Oy | FID | Baltic Connector Oy | 2020 | 48
Cross-Border Transmission IP within EU | Balticonnector / Paldiski (EE) | Transmission Estonia | Transmission Balti Connector Finland | TRA-F-928 | Balticconnector Finnish part | Baltic Connector Oy | FID | Baltic Connector Oy | 2020 | 48
Cross-Border Transmission IP within EU | Nea Mesimvria | Transmission Trans-Adriatic Pipeline Greece | Transmission Greece | TRA-F-941 | Metering and Regulating station at Nea Messimvria | DESFA S.A. | FID | DESFA S.A. | 2020 | 49.2
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) | TRA-F-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | FID | Gastransport Nord GmbH | 2024 | 25.4
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) | TRA-F-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | FID | Gastransport Nord GmbH | 2025 | 25.4
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) | TRA-F-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | FID | Gastransport Nord GmbH | 2027 | 76.2
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) | TRA-F-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | FID | Gastransport Nord GmbH | 2020 | 25.4
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) | TRA-F-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | FID | Gastransport Nord GmbH | 2022 | 25.4
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) | TRA-F-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | FID | Gastransport Nord GmbH | 2026 | 25.4
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) | TRA-F-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | FID | Gastransport Nord GmbH | 2021 | 25.4
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) | TRA-F-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | FID | Gastransport Nord GmbH | 2023 | 25.4
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GUD) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) | TRA-A-951 | Embedding CS Folmhusen in H-Gas | Gasunie Deutschland Transport Services GmbH | Advanced | Gasunie Deutschland Transport Services GmbH | 2020 | 57.3
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (L) (NL) (GUD) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (DE GASPOOL L-Gas) | TRA-A-951 | Embedding CS Folmhusen in H-Gas | Gasunie Deutschland Transport Services GmbH | Advanced | Gasunie Deutschland Transport Services GmbH | 2020 | -57.3
Cross-Border Transmission IP within EU | Tarvisio (IT) / Arnoldstein (AT) | Transmission Italy (PSV) (Italy Northern Export Fork) | Transmission Austria (CEGH) | TRA-F-954 | TAG Reverse Flow | Trans Austria Gasleitung GmbH | FID | TAG GmbH | 2020 | 0
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (L) (NL) (GUD) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (DE GASPOOL L-Gas) | TRA-N-955 | GUD: Complete conversion to H-gas | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Gasunie Deutschland Transport Services GmbH | 2030 | -135
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GUD) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) | TRA-N-955 | GUD: Complete conversion to H-gas | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Gasunie Deutschland Transport Services GmbH | 2030 | 135
Cross-Border Transmission IP within EU | Csanadpalota 2 | Transmission Hungary (MGP) | Transmission Romania | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | SNTGN Transgaz SA | Less-Advanced | SNTGN Transgaz S.A. | 2023 | 128.73
Cross-Border Transmission IP within EU | Csanadpalota 2 | Transmission Romania | Transmission Hungary (MGP) | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | SNTGN Transgaz SA | Less-Advanced | SNTGN Transgaz S.A. | 2023 | 128.73
Cross-Border Transmission IP within EU | Nea Mesimvria | Transmission Greece | Transmission Trans-Adriatic Pipeline Greece | TRA-N-971 | Compressor station at Nea Messimvria | DESFA S.A. | Less-Advanced | DESFA S.A. | 2023 | 49.2
Cross-Border Transmission IP within EU | Dravaszerdahely | Transmission Hungary (MGP) | Transmission Croatia | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Plinacro Ltd | Less-Advanced | Plinacro Ltd | 2027 | 135.85
Cross-Border Transmission IP within EU | Dravaszerdahely | Transmission Croatia | Transmission Hungary (MGP) | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Plinacro Ltd | Less-Advanced | Plinacro Ltd | 2027 | 82
Cross-Border Transmission IP within EU | Moffat | Transmission United Kingdom (NBP) (Moffat) | Transmission United Kingdom (NBP) | TRA-N-1064 | Moffat Physical Reverse Flow | National Grid Gas plc | Less-Advanced | National Grid Gas plc | 2020 | 139
Cross-Border Transmission IP within EU | East Med / Peloponnesus (GR) | Transmission East Med Greece | Transmission Greece | TRA-N-1091 | Metering and Regulating station at Megalopoli | DESFA S.A. | Less-Advanced | DESFA S.A. | 2025 | 90
Cross-Border Transmission IP within EU | Melendugno - IT / TAP | Transmission Trans-Adriatic Pipeline Albania | Transmission Italy (PSV) (Southern Projects) | TRA-F-1193 | TAP interconnection | Snam Rete Gas S.p.A. | FID | Snam Rete Gas S.p.A. | 2020 | 509
Cross-Border Transmission IP within EU | Melendugno - IT / TAP | Transmission Italy (PSV) (Southern Projects) | Transmission Trans-Adriatic Pipeline Albania | TRA-F-1193 | TAP interconnection | Snam Rete Gas S.p.A. | FID | Snam Rete Gas S.p.A. | 2020 | 158
Cross-Border Transmission IP within EU | Melendugno - IT / TAP | Transmission Trans-Adriatic Pipeline Albania | Transmission Italy (PSV) (Southern Projects) | TRA-N-1195 | Matagiola - Massafra pipeline | Snam Rete Gas S.p.A. | Less-Advanced | Snam Rete Gas S.p.A. | 2026 | 310
Cross-Border Transmission IP within EU | Otranto - IT / IGI Poseidon | Transmission ITGI Poseidon Greece | Transmission Italy (PSV) (Southern Projects) | TRA-N-1195 | Matagiola - Massafra pipeline | Snam Rete Gas S.p.A. | Less-Advanced | Snam Rete Gas S.p.A. | 2026 | 310
Cross-Border Transmission IP within EU | GCP GAZ-SYSTEM/ONTRAS | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Germany (GASPOOL) | TRA-N-1202 | GCP GAZ-SYSTEM/ONTRAS - incremental capacity project | GAZ-SYSTEM S.A. | Less-Advanced | GAZ-SYSTEM S.A. | 2023 | 48.6
Cross-Border Transmission IP within EU | Gorizia (IT) /Šempeter (SI) | Transmission Italia (PSV) | Transmission Slovenia | TRA-N-1227 | Gorizia plant upgrade | Snam Rete Gas S.p.A. | Less-Advanced | Snam Rete Gas S.p.A. | 2026 | 17.3
Cross-Border Transmission IP within EU | Gorizia (IT) /Šempeter (SI) | Transmission Slovenia | Transmission Italia (PSV) | TRA-N-1227 | Gorizia plant upgrade | Snam Rete Gas S.p.A. | Less-Advanced | Snam Rete Gas S.p.A. | 2026 | 44.3
Cross-Border Transmission IP within EU | Balassagyarmat (HU) / Velké Zlievce (SK) | Transmission Hungary (MGP) | Transmission Slovakia | TRA-N-1235 | Firm transmission capacity increase at the IP Veľké Zlievce | eustream,a.s. | Less-Advanced | eustream, a.s. | 2022 | 153
Cross-Border Transmission IP within EU | Balassagyarmat (HU) / Velké Zlievce (SK) | Transmission Slovakia | Transmission Hungary (MGP) | TRA-N-1235 | Firm transmission capacity increase at the IP Veľké Zlievce | eustream,a.s. | Less-Advanced | eustream, a.s. | 2022 | 25.4
Cross-Border Transmission IP within EU | IP Greece - Italy | Transmission Greece | Transmission Italy (PSV) (Southern Projects) | TRA-N-1246 | Greece - Italy interconnection | Snam Rete Gas S.p.A. | Less-Advanced | Snam Rete Gas S.p.A. | 2025 | 357.7
Cross-Border Transmission IP within EU | Nea Mesimvria | Transmission Trans-Adriatic Pipeline Greece | Transmission Greece | TRA-F-1276 | Compressor station at Nea Messimvria (3rd unit) | DESFA S.A. | FID | DESFA S.A. | 2022 | 32.4
Cross-Border Transmission IP within EU | Nea Mesimvria | Transmission Greece | Transmission Trans-Adriatic Pipeline Greece | TRA-F-1276 | Compressor station at Nea Messimvria (3rd unit) | DESFA S.A. | FID | DESFA S.A. | 2022 | 32.4
Cross-Border Transmission IP within EU | Nea Mesimvria | Transmission Greece | Transmission Trans-Adriatic Pipeline Greece | TRA-N-1278 | Compressor station at Ambelia | DESFA S.A. | Less-Advanced | DESFA S.A. | 2023 | 32.4
Cross-Border Transmission IP within EU | Nea Mesimvria | Transmission Trans-Adriatic Pipeline Greece | Transmission Greece | TRA-N-1278 | Compressor station at Ambelia | DESFA S.A. | Less-Advanced | DESFA S.A. | 2023 | 32.4
Cross-Border Transmission IP within EU | Csanadpalota | Transmission Hungary (MGP) | Transmission Romania | TRA-A-1322 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase II | SNTGN Transgaz SA | Advanced | SNTGN Transgaz S.A. | 2022 | 78.12
Cross-Border Transmission IP within EU | Csanadpalota | Transmission Romania | Transmission Hungary (MGP) | TRA-A-1322 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase II | SNTGN Transgaz SA | Advanced | SNTGN Transgaz S.A. | 2022 | 75.88
Distribution Point | Aggregated Distribution (PL) | Distribution Poland (VTP - GAZ-SYSTEM) | Transmission Poland (VTP - GAZ-SYSTEM) | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. | Less-Advanced | GAZ-SYSTEM S.A. | 2029 | 0
Distribution Point | Aggregated Distribution (PL) | Distribution Poland (VTP - GAZ-SYSTEM) | Transmission Poland (VTP - GAZ-SYSTEM) | TRA-F-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. | FID | GAZ-SYSTEM S.A. | 2021 | 0
Distribution Point | Aggregated Distribution (PL) | Distribution Poland (VTP - GAZ-SYSTEM) | Transmission Poland (VTP - GAZ-SYSTEM) | TRA-A-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | GAZ-SYSTEM S.A. | Advanced | GAZ-SYSTEM S.A. | 2022 | 0
Internal Point | Italy Mezzogiorno Import Fork | Transmission Italy (PSV) (Southern Projects) | Transmission Italia (PSV) | TRA-N-7 | Development for new import from the South (Adriatica Line) | Snam Rete Gas S.p.A. | Less-Advanced | Snam Rete Gas S.p.A. | 2026 | 264
Internal Point | New IP North-East Italy | Transmission Italy (PSV) (Northern Projects) | Transmission Italia (PSV) | TRA-N-8 | Import developments from North-East | Snam Rete Gas S.p.A. | Less-Advanced | Snam Rete Gas S.p.A. | 2034 | 340
Internal Point | Italy Mezzogiorno Import Fork | Transmission Italy (PSV) (Southern Projects) | Transmission Italia (PSV) | TRA-N-9 | Additional Southern developments | Snam Rete Gas S.p.A. | Less-Advanced | Snam Rete Gas S.p.A. | 2034 | 264
Internal Point | Italy Southern Import Fork | Transmission Italy (PSV) (Italy Southern Import Fork) | Transmission Italy (PSV) (Southern Projects) | TRA-N-9 | Additional Southern developments | Snam Rete Gas S.p.A. | Less-Advanced | Snam Rete Gas S.p.A. | 2034 | 264
Internal Point | Vale (GE) | Transmission South Caucasus Pipeline Georgia | Transmission Georgia (White Stream) | TRA-N-53 | White Stream | White Stream Ltd | Less-Advanced | White Stream | 2023 | 505
Internal Point | Komotini (DESFA) Bottleneck | Transmission Greece (Komotini) | Transmission Greece | TRA-N-128 | Compressor Station Kipi | DESFA S.A. | Less-Advanced | DESFA S.A. | 2024 | 54.4
Internal Point | Virtual Ips (GTS) NL-DE (Gaspool) | Transmission Netherlands (TTF) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | TRA-F-307 | H-gas exit OSZ GTG Nord | Gasunie Transport Services B.V. | FID | Gasunie Transport Services B.V. | 2020 | 25.4
Internal Point | Virtual Ips (GTS) NL-DE (Gaspool) | Transmission Netherlands (TTF) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | TRA-F-307 | H-gas exit OSZ GTG Nord | Gasunie Transport Services B.V. | FID | Gasunie Transport Services B.V. | 2027 | 76.2
Internal Point | Virtual Ips (GTS) NL-DE (Gaspool) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Netherlands (TTF) | TRA-N-873 | Additional import at Oude StatenZijl area | Gasunie Transport Services B.V. | Less-Advanced | Gasunie Transport Services B.V. | 2025 | 60
Internal Point | Virtual Ips (GTS) NL-DE (Gaspool) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Netherlands (TTF) | TRA-N-873 | Additional import at Oude StatenZijl area | Gasunie Transport Services B.V. | Less-Advanced | Gasunie Transport Services B.V. | 2022 | 228
Internal Point | Virtual Ips (GTS) NL-DE (Gaspool) | Transmission Netherlands (TTF) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | TRA-N-882 | Transferring L-gas infrastructure to H-gas | Gasunie Transport Services B.V. | Less-Advanced | Gasunie Transport Services B.V. | 2020 | 57.3
Internal Point | Virtual Ips (GTS) NL-DE (Gaspool) | Transmission Netherlands (TTF) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | TRA-N-882 | Transferring L-gas infrastructure to H-gas | Gasunie Transport Services B.V. | Less-Advanced | Gasunie Transport Services B.V. | 2030 | 135
Internal Point | Italy Mezzogiorno Import Fork | Transmission Italia (PSV) | Transmission Italy (PSV) (Southern Projects) | TRA-N-1063 | Export to Malta | Snam Rete Gas S.p.A. | Less-Advanced | Snam Rete Gas S.p.A. | 2024 | 56
LNG Entry IP | Shannon LNG | LNG Terminals Ireland (IBP) | Transmission Ireland (IBP) | LNG-A-30 | Shannon LNG Terminal and Connecting Pipeline | Shannon LNG Ltd | Advanced | Shannon LNG | 2022 | 86
LNG Entry IP | Shannon LNG | LNG Terminals Ireland (IBP) | Transmission Ireland (IBP) | LNG-A-30 | Shannon LNG Terminal and Connecting Pipeline | Shannon LNG Ltd | Advanced | Shannon LNG | 2025 | 64
LNG Entry IP | Shannon LNG | LNG Terminals Ireland (IBP) | Transmission Ireland (IBP) | LNG-A-30 | Shannon LNG Terminal and Connecting Pipeline | Shannon LNG Ltd | Less-Advanced | Shannon LNG | 2029 | 100
LNG Entry IP | Gothenburg LNG | LNG Terminals Sweden | Transmission Sweden | LNG-A-32 | Project GO4LNG LNG terminal Gothenburg | Swedegas AB | Advanced | Swedegas AB | 2022 | 26
LNG Entry IP | Gate Terminal (I) | LNG Terminals Netherlands (TTF) | Transmission Netherlands (TTF) | LNG-A-50 | Gate terminal phase 3 | Gate | Advanced | Gate Terminal B.V. | 2022 | 60
LNG Entry IP | Gate Terminal (I) | LNG Terminals Netherlands (TTF) | Transmission Netherlands (TTF) | LNG-A-50 | Gate terminal phase 3 | Gate | Advanced | Gate Terminal B.V. | 2024 | 61
LNG Entry IP | Alexandroupolis LNG | LNG Terminals Greece | Transmission Greece (Alexandropolis LNG) | LNG-A-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Gastrade S.A. | Advanced | Gastrade S.A. | 2022 | 253.1
LNG Entry IP | Alexandroupolis Amphitriti | Transmission Greece (Alexandropolis LNG) | Transmission Greece (Komotini) | TRA-A-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. | Advanced | Gastrade S.A. | 2022 | 253.1
LNG Entry IP | Croatia LNG | LNG Terminals Croatia | Transmission Croatia | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd | Less-Advanced | Plinacro Ltd | 2027 | 27.17
LNG Entry IP | Paldiski LNG | LNG Terminals Estonia | Transmission Estonia | LNG-A-79 | Paldiski LNG Terminal | Balti Gaas plc | Advanced | Balti Gaas plc | 2025 | 140
LNG Entry IP | Croatia LNG | LNG Terminals Croatia | Transmission Croatia | LNG-F-82 | LNG terminal Krk | LNG Hrvatska d.o.o. | FID | LNG Hrvatska d.o.o. | 2027 | 109.2
LNG Entry IP | Croatia LNG | LNG Terminals Croatia | Transmission Croatia | LNG-F-82 | LNG terminal Krk | LNG Hrvatska d.o.o. | FID | LNG Hrvatska d.o.o. | 2020 | 81.5
LNG Entry IP | Croatia LNG | LNG Terminals Croatia | Transmission Croatia | TRA-F-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Plinacro Ltd | FID | Plinacro Ltd | 2020 | 81.51
LNG Entry IP | Gran Canaria LNG | LNG Terminals Spain (Canaria) | Transmission Spain (Canaria) | LNG-F-163 | Gran Canaria LNG Terminal | Gascan | FID | Enagas Transporte S.A.U. | 2029 | 41.9
LNG Entry IP | Gran Canaria LNG | LNG Terminals Spain (Canaria) | Transmission Spain (Canaria) | LNG-F-163 | Gran Canaria LNG Terminal | Gascan | FID | Gascan | 2029 | 41.9
LNG Entry IP | Musel | LNG Terminals Spain (Atlantic) | Transmission Spain (MS-ATR) | LNG-F-178 | Musel LNG terminal | Enagas Transporte S.A.U. | FID | Enagas Transporte S.A.U. | 2021 | 0
LNG Entry IP | Tenerife LNG | LNG Terminals Spain (Canaria) | Transmission Spain (Canaria) | LNG-F-183 | Tenerife LNG Terminal | Gascan | FID | Gascan | 2022 | 41.9
LNG Entry IP | Tenerife LNG | LNG Terminals Spain (Canaria) | Transmission Spain (Canaria) | LNG-F-183 | Tenerife LNG Terminal | Gascan | FID | Enagas Transporte S.A.U. | 2022 | 41.9
LNG Entry IP | Gate Terminal (I) | LNG Terminals Netherlands (TTF) | Transmission Netherlands (TTF) | TRA-N-192 | Entry capacity expansion GATE terminal | Gasunie Transport Services B.V. | Less-Advanced | Gasunie Transport Services B.V. | 2022 | 121
LNG Entry IP | Montoir de Bretagne | LNG Terminals France (PEG North) | Transmission France (NS3) | LNG-N-225 | Montoir LNG Terminal Expansion | Elengy | Less-Advanced | Elengy | 2023 | 100
LNG Entry IP | Montoir de Bretagne | LNG Terminals France (PEG North) | Transmission France (NS3) | LNG-N-225 | Montoir LNG Terminal Expansion | Elengy | Less-Advanced | Elengy | 2025 | 260
LNG Entry IP | Fos Cavaou | LNG Terminals France (PEG South) | Transmission France (NS4) | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | Fosmax LNG | Less-Advanced | Fosmax LNG | 2023 | 110
LNG Entry IP | Fos Cavaou | LNG Terminals France (PEG South) | Transmission France (NS4) | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | Fosmax LNG | Less-Advanced | Fosmax LNG | 2025 | 330
LNG Entry IP | Montoir de Bretagne | LNG Terminals France (PEG North) | Transmission France (NS3) | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | GRTgaz | Less-Advanced | GRTgaz | 2023 | 100
LNG Entry IP | Fos (Tonkin/Cavaou) | LNG Terminals France (PEG South) | Transmission France (NS4) | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | Less-Advanced | GRTgaz | 2026 | 327
LNG Entry IP | Swinoujscie | LNG Terminals Poland (VTP - GAZ-SYSTEM) | Transmission Poland (VTP - GAZ-SYSTEM) | LNG-F-272 | Upgrade of LNG terminal in Świnoujście | GAZ-SYSTEM S.A. | FID | Polskie LNG S.A. | 2023 | 76.57
LNG Entry IP | Swinoujscie | LNG Terminals Poland (VTP - GAZ-SYSTEM) | Transmission Poland (VTP - GAZ-SYSTEM) | LNG-F-272 | Upgrade of LNG terminal in Świnoujście | GAZ-SYSTEM S.A. | FID | GAZ-SYSTEM S.A. | 2023 | 76.57
LNG Entry IP | Mugardos | LNG Terminals Spain (Atlantic) | Transmission Spain (MS-ATR) | LNG-A-295 | Mugardos LNG Terminal: Send-out Increase | Reganosa | Advanced | Reganosa (LSO) | 2024 | 115
LNG Entry IP | Mugardos | LNG Terminals Spain (Atlantic) | Transmission Spain (MS-ATR) | LNG-A-295 | Mugardos LNG Terminal: Send-out Increase | Reganosa | Advanced | Reganosa | 2024 | 115
LNG Entry IP | Sardinia LNG | LNG Terminals Italy (Sardinia) | Transmission Italy (Sardinia) | LNG-N-304 | Italy-Sardinia Virtual Pipeline | Snam S.p.A. | Less-Advanced | Snam Rete Gas S.p.A. | 2021 | 50
LNG Entry IP | Sines | LNG Terminals Portugal | Transmission Portugal | TRA-A-320 | Carregado Compressor Station | REN-Gasodutos, S.A. | Advanced | REN - Gasodutos, S.A. | 2025 | 92.8
LNG Entry IP | Klaipeda (LNG) | LNG Terminals Lithuania | Transmission Lithuania | LNG-F-824 | LNG Terminal in Klaipeda | AB Klaipėdos Nafta | FID | AB Klaipėdos Nafta | 2024 | 122.4
LNG Entry IP | Skulte (LV) | LNG Terminals Latvia | Transmission Latvia | LNG-N-912 | Skulte LNG | AS Skulte LNG Terminal | Less-Advanced | AS Skulte LNG Terminal | 2023 | 150
LNG Entry IP | FSRU Polish Baltic Sea Coast | LNG Terminals Poland (VTP - GAZ-SYSTEM) | Transmission Poland (VTP - GAZ-SYSTEM) | LNG-N-947 | FSRU Polish Baltic Sea Coast | GAZ-SYSTEM S.A. | Less-Advanced | GAZ-SYSTEM S.A. | 2025 | 138
LNG Entry IP | Tallinn LNG | LNG Terminals Estonia | Transmission Estonia | LNG-A-962 | Tallinn LNG | Liwathon E.O.S. AS / Port of Tallinn AS | Advanced | Liwathon E.O.S. | 2022 | 121
LNG Entry IP | Croatia LNG | LNG Terminals Croatia | Transmission Croatia | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Plinacro Ltd | Less-Advanced | Plinacro Ltd | 2027 | 82
LNG Entry IP | Alexandroupolis Amphitriti | Transmission Greece (Alexandropolis LNG) | Transmission Greece (Komotini) | TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | DESFA S.A. | Less-Advanced | DESFA S.A. | 2022 | 268
LNG Entry IP | Terminal 2 Vassiliko - Lemesos Port | LNG Terminals Cyprus | Transmission Cyprus | LNG-A-1146 | Cyprus Gas2EU | Ministry of Energy, Commerce and Industry (MECI) | Advanced | Natural Gas Public Company (DEFA LTD) | 2022 | 40
LNG Entry IP | Skulte (LV) | LNG Terminals Latvia | Transmission Latvia | TRA-N-1181 | Connecting pipe to LNG terminal in Latvia | JSC "Conexus Baltic Grid" | Less-Advanced | Conexus Baltic Grid | 2021 | 170
LNG Entry IP | Sardinia LNG | LNG Terminals Italy (Sardinia) | Transmission Italy (Sardinia) | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | ENURA S.p.A. | 2022 | 22
LNG Entry IP | Sardinia LNG | LNG Terminals Italy (Sardinia) | Transmission Italy (Sardinia) | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | ENURA S.p.A. | 2025 | 11
LNG Entry IP | Sardinia LNG | LNG Terminals Italy (Sardinia) | Transmission Italy (Sardinia) | TRA-N-1194 | Sardinia Methanization | ENURA S.p.A. | Less-Advanced | ENURA S.p.A. | 2020 | 17
LNG Entry IP | Brunsbuettel (DE) | LNG Terminals Germany (GASPOOL) | Transmission Germany (GASPOOL) | LNG-A-1198 | LNG Terminal Brunsbuettel | GermanLNG Terminal GmbH | Advanced | GermanLNG Terminal GmbH | 2023 | 256.2
LNG Entry IP | Brunsbuettel (DE) | LNG Terminals Germany (GASPOOL) | Transmission Germany (GASPOOL) | TRA-A-1199 | LNG Terminal Brunsbuettel - Grid Integration | Gasunie Deutschland Transport Service GmbH | Advanced | Gasunie Deutschland Transport Services GmbH | 2023 | 256.2
Production IP | Renewable Gas Ireland (IE) | NP Send-out Ireland (IBP) | Transmission Ireland (IBP) | ETR-N-20 | GNI Renewable Gas Central Grid Injection Project | Gas Networks Ireland | Less-Advanced | Gas Networks Ireland | 2027 | 1.3
Production IP | Renewable Gas Ireland (IE) | NP Send-out Ireland (IBP) | Transmission Ireland (IBP) | ETR-N-20 | GNI Renewable Gas Central Grid Injection Project | Gas Networks Ireland | Less-Advanced | Gas Networks Ireland | 2026 | 2.1
Production IP | Renewable Gas Ireland (IE) | NP Send-out Ireland (IBP) | Transmission Ireland (IBP) | ETR-N-20 | GNI Renewable Gas Central Grid Injection Project | Gas Networks Ireland | Less-Advanced | Gas Networks Ireland | 2024 | 1.3
Production IP | Renewable Gas Ireland (IE) | NP Send-out Ireland (IBP) | Transmission Ireland (IBP) | ETR-N-20 | GNI Renewable Gas Central Grid Injection Project | Gas Networks Ireland | Less-Advanced | Gas Networks Ireland | 2023 | 0.5
Production IP | Renewable Gas Ireland (IE) | NP Send-out Ireland (IBP) | Transmission Ireland (IBP) | ETR-N-20 | GNI Renewable Gas Central Grid Injection Project | Gas Networks Ireland | Less-Advanced | Gas Networks Ireland | 2028 | 0.5
Production IP | Renewable Gas Ireland (IE) | NP Send-out Ireland (IBP) | Transmission Ireland (IBP) | ETR-N-20 | GNI Renewable Gas Central Grid Injection Project | Gas Networks Ireland | Less-Advanced | Gas Networks Ireland | 2025 | 2
Production IP | GoG (CZ) | NP Send-out Czech Republic (VOB) | Transmission Czech Republic (VOB) | ETR-N-306 | Greening of Gas (GoG) | NET4GAS, s.r.o. | Less-Advanced | NET4GAS, s.r.o. | 2023 | 0.007
Production IP | East Med / Cyprus/Israeli Production Field | NP Send-out Cyprus | Transmission East Med Greece | TRA-A-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | IGI Poseidon S.A. | 2025 | 330
Production IP | Europipe (NO) / Baltic Pipe (DK) | Transmission Norway | NP Send-out Denmark (Offshore) | TRA-A-394 | Norwegian tie-in to Danish upstream system | Energinet.dk | Advanced | Energinet | 2022 | 306.8
Production IP | Production (OGE) (DE) | NP Send-out Germany (NCG) | Transmission Germany (NCG) | ETR-N-406 | hybridge - gas grid infrastructure | Open Grid Europe GmbH | Less-Advanced | Open Grid Europe GmbH | 2023 | 2
Production IP | Ostfriesland (Element Eins) | NP Send-out Germany (NCG) | Transmission Germany (NCG) | ETR-N-452 | Element Eins | Thyssengas GmbH, Gasunie Deutschland Transport Services GmbH, Tennet TSO Gm | Less-Advanced | Thyssengas GmbH | 2028 | 1.8
Production IP | Ostfriesland (Element Eins) | NP Send-out Germany (NCG) | Transmission Germany (NCG) | ETR-N-452 | Element Eins | Thyssengas GmbH, Gasunie Deutschland Transport Services GmbH, Tennet TSO Gm | Less-Advanced | Thyssengas GmbH | 2022 | 0.72
Production IP | Ostfriesland (Element Eins) | NP Send-out Germany (NCG) | Transmission Germany (NCG) | ETR-N-452 | Element Eins | Thyssengas GmbH, Gasunie Deutschland Transport Services GmbH, Tennet TSO Gm | Less-Advanced | Thyssengas GmbH | 2024 | 1.08
Production IP | Hydrogen (ES) | NP Send-out Spain (MS-ATR) | Transmission Spain (MS-ATR) | ETR-N-501 | Hub País Vasco | Enagas S.A. | Less-Advanced | Enagás S.A. | 2023 | 0.001
Production IP | Hydrogen (ES) | NP Send-out Spain (MS-ATR) | Transmission Spain (MS-ATR) | ETR-N-501 | Hub País Vasco | Enagas S.A. | Less-Advanced | Enagas Transporte S.A.U. | 2023 | 0.001
Production IP | Hydrogen (ES) | NP Send-out Spain (MS-ATR) | Transmission Spain (MS-ATR) | ETR-A-504 | Sun2Hy | Enagas S.A. | Advanced | Enagas Transporte S.A.U. | 2023 | 0
Production IP | Hydrogen (ES) | NP Send-out Spain (MS-ATR) | Transmission Spain (MS-ATR) | ETR-A-504 | Sun2Hy | Enagas S.A. | Advanced | Enagás S.A. | 2023 | 0
Production IP | Hydrogen (ES) | NP Send-out Spain (MS-ATR) | Transmission Spain (MS-ATR) | ETR-A-519 | Hub Baleares | Enagas S.A. | Advanced | Enagas Transporte S.A.U. | 2023 | 0
Production IP | Hydrogen (ES) | NP Send-out Spain (MS-ATR) | Transmission Spain (MS-ATR) | ETR-A-519 | Hub Baleares | Enagas S.A. | Advanced | Enagás S.A. | 2023 | 0
Production IP | Hydrogen (ES) | NP Send-out Spain (MS-ATR) | Transmission Spain (MS-ATR) | ETR-N-521 | Hub Murcia | Enagas S.A. | Less-Advanced | Enagás S.A. | 2023 | 0.003
Production IP | Hydrogen (ES) | NP Send-out Spain (MS-ATR) | Transmission Spain (MS-ATR) | ETR-N-521 | Hub Murcia | Enagas S.A. | Less-Advanced | Enagas Transporte S.A.U. | 2023 | 0.003
Production IP | IT - Indigenous Production | NP Send-out Italia (PSV) | Transmission Italia (PSV) | ETR-F-523 | Biomethane plants development | Snam4mobility | FID | Snam4Mobility S.p.A. | 2023 | 0.7
Production IP | Hydrogen (ES) | NP Send-out Spain (MS-ATR) | Transmission Spain (MS-ATR) | ETR-N-537 | Hub Aragon | Enagas S.A. | Less-Advanced | Enagas Transporte S.A.U. | 2022 | 0
Production IP | Hydrogen (ES) | NP Send-out Spain (MS-ATR) | Transmission Spain (MS-ATR) | ETR-N-537 | Hub Aragon | Enagas S.A. | Less-Advanced | Enagás S.A. | 2022 | 0
Production IP | IT - Indigenous Production | NP Send-out Italia (PSV) | Transmission Italia (PSV) | ETR-N-595 | Transport of hydrogen into natural gas network | Snam Rete Gas S.p.A. | Less-Advanced | Snam Rete Gas S.p.A. | 2025 | 0.192
Production IP | Production (DE) (GUD) H-Gas-Summe Produktion | NP Send-out Germany (GASPOOL) | Transmission Germany (GASPOOL) | ETR-N-616 | Renewable Methane according to NEP2020 | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Gasunie Deutschland Transport Services GmbH | 2025 | 0.6
Production IP | Production (DE) (GUD) H-Gas-Summe Produktion | NP Send-out Germany (GASPOOL) | Transmission Germany (GASPOOL) | ETR-N-616 | Renewable Methane according to NEP2020 | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Gasunie Deutschland Transport Services GmbH | 2023 | 0.26
Production IP | Production (DE) (GUD) H-Gas-Summe Produktion | NP Send-out Germany (GASPOOL) | Transmission Germany (GASPOOL) | ETR-N-622 | Renewable Hydrogen according to NEP2020 | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Gasunie Deutschland Transport Services GmbH | 2022 | 3.22
Production IP | Production (DE) (GUD) H-Gas-Summe Produktion | NP Send-out Germany (GASPOOL) | Transmission Germany (GASPOOL) | ETR-N-622 | Renewable Hydrogen according to NEP2020 | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Gasunie Deutschland Transport Services GmbH | 2024 | 1.42
Production IP | Production (DE) (GUD) H-Gas-Summe Produktion | NP Send-out Germany (GASPOOL) | Transmission Germany (GASPOOL) | ETR-N-622 | Renewable Hydrogen according to NEP2020 | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Gasunie Deutschland Transport Services GmbH | 2023 | 4.25
Production IP | Production (DE) (GUD) H-Gas-Summe Produktion | NP Send-out Germany (GASPOOL) | Transmission Germany (GASPOOL) | ETR-N-622 | Renewable Hydrogen according to NEP2020 | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Gasunie Deutschland Transport Services GmbH | 2025 | 6.03
Production IP | Production (DE) (GUD) H-Gas-Summe Produktion | NP Send-out Germany (GASPOOL) | Transmission Germany (GASPOOL) | ETR-N-622 | Renewable Hydrogen according to NEP2020 | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Gasunie Deutschland Transport Services GmbH | 2020 | 1.2
Production IP | IT - Indigenous Production | NP Send-out Italia (PSV) | Transmission Italia (PSV) | TRA-F-1241 | Interconnection with production in Gela | Snam Rete Gas S.p.A. | FID | Snam Rete Gas S.p.A. | 2020 | 45
Production IP (Aggregate) | Production France PEG TIGF | NP Send-out France (PEG TIGF) | Transmission France | ETR-N-728 | Biomethane: connecting production units and reverse flow projects | TEREGA | Less-Advanced | TERÉGA | 2029 | 3
Production IP (Aggregate) | Production France PEG TIGF | NP Send-out France (PEG TIGF) | Transmission France | ETR-F-743 | Impulse 2025 | Teréga | FID | TERÉGA | 2025 | 0
Production IP (Forecast) | Forecast Production Latvia | NP Send-out Latvia | Transmission Latvia | ETR-N-80 | Power to Gas Production with infrastructure building/enhacement in Latvia | JSC "Conexus Baltic Grid" | Less-Advanced | Conexus Baltic Grid | 2025 | 2
Production IP (Forecast) | Forecast Production Latvia | NP Send-out Latvia | Transmission Latvia | ETR-N-125 | Biomethane production with infrastructure building/enhancement in Latvia | JSC "Conexus Baltic Grid" | Less-Advanced | Conexus Baltic Grid | 2025 | 0.73
Production IP (Forecast) | Forecast Production France GRTgaz | NP Send-out France (PEG GRTgaz) | Transmission France | ETR-F-546 | Jupiter 1000: first industrial demonstrator of Power to Gas in France | GRTgaz, Terega | FID | GRTgaz | 2020 | 0.01
Production IP (Forecast) | Forecast Production France GRTgaz | NP Send-out France (PEG GRTgaz) | Transmission France | ETR-F-587 | West Grid Synergy | GRTgaz | FID | GRTgaz | 2019 | 0.4
Production IP (Forecast) | Forecast Production France GRTgaz | NP Send-out France (PEG GRTgaz) | Transmission France | ETR-N-624 | Biomethane: Reverse flow projects | GRTgaz | Less-Advanced | GRTgaz | 2028 | 70
Production IP (Forecast) | Forecast Production Italia | NP Send-out Italia (PSV) | Transmission Italia (PSV) | TRA-N-1265 | Biomethane productions interconnection | Snam Rete Gas S.p.A. | Less-Advanced | Snam Rete Gas S.p.A. | 2022 | 39.6
Storage IP | GMS Chiren | Transmission Bulgaria (NGTS) | Storage Bulgaria (NGTS) | UGS-A-138 | Balkan Gas Hub - UGS Chiren Expansion | Bulgartransgaz EAD | Advanced | Bulgartransgaz EAD (SSO) | 2025 | 51.07
Storage IP | GMS Chiren | Storage Bulgaria (NGTS) | Transmission Bulgaria (NGTS) | UGS-A-138 | Balkan Gas Hub - UGS Chiren Expansion | Bulgartransgaz EAD | Advanced | Bulgartransgaz EAD | 2025 | 48.9
Storage IP | GMS Chiren | Transmission Bulgaria (NGTS) | Storage Bulgaria (NGTS) | UGS-A-138 | Balkan Gas Hub - UGS Chiren Expansion | Bulgartransgaz EAD | Advanced | Bulgartransgaz EAD | 2025 | 51.07
Storage IP | GMS Chiren | Storage Bulgaria (NGTS) | Transmission Bulgaria (NGTS) | UGS-A-138 | Balkan Gas Hub - UGS Chiren Expansion | Bulgartransgaz EAD | Advanced | Bulgartransgaz EAD (SSO) | 2025 | 48.9
Storage IP | UGS Targu Mures | Transmission Romania | Storage Romania | UGS-A-233 | Depomures | Engie Romania SA | Advanced | Depomures | 2021 | 18.92
Storage IP | UGS Targu Mures | Transmission Romania | Storage Romania | UGS-A-233 | Depomures | Engie Romania SA | Advanced | Depomures | 2024 | 15.78
Storage IP | UGS Targu Mures | Storage Romania | Transmission Romania | UGS-A-233 | Depomures | Engie Romania SA | Advanced | Depomures | 2021 | 18.92
Storage IP | UGS Targu Mures | Storage Romania | Transmission Romania | UGS-A-233 | Depomures | Engie Romania SA | Advanced | Depomures | 2024 | 15.78
Storage IP | UGS - IT - Snam Rete Gas/STOGIT | Storage Italia (PSV) | Transmission Italia (PSV) | UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | STOGIT | FID | STOGIT | 2028 | 104.3
Storage IP | UGS - IT - Snam Rete Gas/STOGIT | Transmission Italia (PSV) | Storage Italia (PSV) | UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | STOGIT | FID | STOGIT | 2028 | 20.9
Storage IP | Islandmagee | Transmission United Kingdom (North Ireland) | Storage United Kingdom (NBP) | UGS-A-294 | Islandmagee Gas Storage Facility | Islandmagee Storage Limited | Advanced | Islandmagee Storage Ltd | 2022 | 132
Storage IP | Islandmagee | Transmission United Kingdom (North Ireland) | Storage United Kingdom (NBP) | UGS-A-294 | Islandmagee Gas Storage Facility | Islandmagee Storage Limited | Less-Advanced | Islandmagee Storage Ltd | 2026 | 65
Storage IP | Islandmagee | Storage United Kingdom (NBP) | Transmission United Kingdom (North Ireland) | UGS-A-294 | Islandmagee Gas Storage Facility | Islandmagee Storage Limited | Less-Advanced | Islandmagee Storage Ltd | 2026 | 175
Storage IP | Islandmagee | Storage United Kingdom (NBP) | Transmission United Kingdom (North Ireland) | UGS-A-294 | Islandmagee Gas Storage Facility | Islandmagee Storage Limited | Advanced | Islandmagee Storage Ltd | 2022 | 90
Storage IP | VIP Romgaz UGS (RO) | Storage Romania | Transmission Romania | UGS-F-311 | Bilciuresti daily withdrawal capacity increase | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | FID | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | 2025 | 42
Storage IP | UGS Velke Kapusany | Storage Slovakia | Transmission Slovakia | ETR-A-312 | P2G Velke Kapusany | NAFTA a.s. (joint stock company) | Advanced | NAFTA a.s. | 2023 | 1.23
Storage IP | UGS Lab (SK) (Nafta) | Storage Slovakia (SK Multi-country storages) (SK Multi-country storages) | Storage Slovakia (SK Multi-country storages) | ETR-N-315 | G2F - Gas to Future | NAFTA a.s. (joint stock company) | Less-Advanced | NAFTA a.s. | 2025 | 1.32
Storage IP | UGS Lab (SK) (Nafta) | Storage Slovakia (SK Multi-country storages) | Storage Slovakia (SK Multi-country storages) (SK Multi-country storages) | ETR-N-315 | G2F - Gas to Future | NAFTA a.s. (joint stock company) | Less-Advanced | NAFTA a.s. | 2025 | 1.32
Storage IP | UGS Croatia | Storage Croatia | Transmission Croatia | UGS-N-347 | Gas storage facility Grubisno Polje | Podzemno skladiste plina Ltd | Less-Advanced | Podzemno skladiste plina d.o.o. | 2025 | 16
Storage IP | UGS Croatia | Transmission Croatia | Storage Croatia | UGS-N-347 | Gas storage facility Grubisno Polje | Podzemno skladiste plina Ltd | Less-Advanced | Podzemno skladiste plina d.o.o. | 2025 | 23
Storage IP | UGS Velke Kapusany | Storage Slovakia | Transmission Slovakia | UGS-A-356 | Underground Gas Storage Velke Kapusany | NAFTA a.s. (joint stock company) | Advanced | NAFTA a.s. | 2023 | 37.05
Storage IP | UGS Velke Kapusany | Transmission Slovakia | Storage Slovakia | UGS-A-356 | Underground Gas Storage Velke Kapusany | NAFTA a.s. (joint stock company) | Advanced | NAFTA a.s. | 2023 | 37.05
Storage IP | VIP Romgaz UGS (RO) | Transmission Romania | Storage Romania | UGS-N-371 | Sarmasel undeground gas storage in Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | 2024 | 34
Storage IP | VIP Romgaz UGS (RO) | Storage Romania | Transmission Romania | UGS-N-371 | Sarmasel undeground gas storage in Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | 2024 | 45
Storage IP | Incukalns (LV) | Storage Latvia | Transmission Latvia | UGS-F-374 | Enhancement of Incukalns UGS | JSC "Conexus Baltic Grid" | FID | Conexus Baltic Grid | 2019 | 84
Storage IP | Incukalns (LV) | Transmission Latvia | Storage Latvia | UGS-F-374 | Enhancement of Incukalns UGS | JSC "Conexus Baltic Grid" | FID | Conexus Baltic Grid | 2025 | 8.5
Storage IP | UGS South Kavala (GR) | Transmission Greece (Komotini) | Storage Greece | UGS-N-385 | South Kavala Underground Gas Storage facility | Hellenic Republic Asset Development Fund | Less-Advanced | Hellenic Republic Asset Management Fund | 2023 | 55
Storage IP | UGS South Kavala (GR) | Storage Greece | Transmission Greece (Komotini) | UGS-N-385 | South Kavala Underground Gas Storage facility | Hellenic Republic Asset Development Fund | Less-Advanced | Hellenic Republic Asset Management Fund | 2023 | 44
Storage IP | VIP Romgaz UGS (RO) | Storage Romania | Transmission Romania | UGS-N-398 | Ghercesti underground gas storage in Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | 2026 | 28
Storage IP | VIP Romgaz UGS (RO) | Transmission Romania | Storage Romania | UGS-N-398 | Ghercesti underground gas storage in Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | 2026 | 18
Storage IP | VIP Romgaz UGS (RO) | Transmission Romania | Storage Romania | UGS-N-399 | Falticeni UGS | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | 2029 | 14
Storage IP | VIP Romgaz UGS (RO) | Storage Romania | Transmission Romania | UGS-N-399 | Falticeni UGS | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | 2029 | 18
Storage IP | Damasławek (PL) | Storage Poland (VTP - GAZ-SYSTEM) | Transmission Poland (VTP - GAZ-SYSTEM) | UGS-N-914 | UGS Damasławek | GAZ-SYSTEM S.A. | Less-Advanced | GAZ-SYSTEM S.A. | 2026 | 200
Storage IP | Damasławek (PL) | Transmission Poland (VTP - GAZ-SYSTEM) | Storage Poland (VTP - GAZ-SYSTEM) | UGS-N-914 | UGS Damasławek | GAZ-SYSTEM S.A. | Less-Advanced | GAZ-SYSTEM S.A. | 2026 | 100
Storage IP | UGS Lesum | Transmission Germany (DE GASPOOL L-Gas) | Storage Germany (DE GASPOOL L-Gas) | TRA-N-955 | GUD: Complete conversion to H-gas | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Gasunie Deutschland Transport Services GmbH | 2021 | -10.7
Storage IP | UGS Lesum | Storage Germany (DE GASPOOL L-Gas) | Transmission Germany (DE GASPOOL L-Gas) | TRA-N-955 | GUD: Complete conversion to H-gas | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Gasunie Deutschland Transport Services GmbH | 2021 | -48.9
Storage IP | UGS South Kavala (GR) | Transmission Greece (Komotini) | Storage Greece | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | DESFA S.A. | Less-Advanced | DESFA S.A. | 2023 | 55
Storage IP | UGS South Kavala (GR) | Storage Greece | Transmission Greece (Komotini) | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | DESFA S.A. | Less-Advanced | DESFA S.A. | 2023 | 44
Trading Point | ETR virtual aggregation (DK) | Distribution Denmark | Transmission Denmark | ETR-A-64 | Biomethane reverse flow Denmark | Energinet | Advanced | Energinet | 2021 | 1
Transmission Point | Drohne NOWAL | Transmission Germany (GASPOOL) | Transmission Germany (NCG) | TRA-F-291 | NOWAL - Nord West Anbindungsleitung | GASCADE Gastransport GmbH | FID | GASCADE Gastransport GmbH | 2020 | 200
Transmission Point | Nybro | NP Send-out Denmark (Offshore) | Transmission Denmark | TRA-A-394 | Norwegian tie-in to Danish upstream system | Energinet.dk | Advanced | Energinet | 2022 | 306.8
Transmission Point | Larino (IT) | Transmission Italia (SGI) | Transmission Italia (PSV) | TRA-F-409 | Larino - Chieti | SGI S.p.A: | FID | Società Gasdotti Italia | 2022 | 53
Transmission Point | Recanati (IT) | Transmission Italia (PSV) | Transmission Italia (SGI) | TRA-F-424 | SAN MARCO - RECANATI | SGI S.p.A. | FID | Società Gasdotti Italia | 2022 | 53
Transmission Point | Larino (IT) | Transmission Italia (PSV) | Transmission Italia (SGI) | TRA-N-439 | Stazione di Spinta "San Marco" | S.G.I. S.p.A. | Less-Advanced | Società Gasdotti Italia | 2022 | 53
Transmission Point | Eastring BG Domestic Point | Transmission Bulgaria (NGTS) | Transmission Eastring Bulgaria | TRA-A-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Advanced | Bulgartransgaz EAD | 2025 | 200
Transmission Point | Eastring BG Domestic Point | Transmission Eastring Bulgaria | Transmission Bulgaria (NGTS) | TRA-A-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Advanced | Bulgartransgaz EAD | 2025 | 200
Transmission Point | Eastring RO Domestic Point | Transmission Eastring Romania | Transmission Romania | TRA-A-655 | Eastring - Romania | SNTGN Transgaz SA | Advanced | SNTGN Transgaz S.A. | 2025 | 150
Transmission Point | Eastring RO Domestic Point | Transmission Romania | Transmission Eastring Romania | TRA-A-655 | Eastring - Romania | SNTGN Transgaz SA | Advanced | SNTGN Transgaz S.A. | 2025 | 150
Transmission Point | Eastring HU Domestic Point | Transmission Hungary (MGP) | Transmission Eastring Hungary (MGP) | TRA-A-656 | Eastring - Hungary | FGSZ Ltd. | Advanced | FGSZ Ltd. | 2025 | 310
Transmission Point | Eastring HU Domestic Point | Transmission Eastring Hungary (MGP) | Transmission Hungary (MGP) | TRA-A-656 | Eastring - Hungary | FGSZ Ltd. | Advanced | FGSZ Ltd. | 2025 | 310
Transmission Point | Nybro | NP Send-out Denmark (Offshore) | Transmission Denmark | TRA-F-780 | Baltic Pipe project – onshore section in Denmark | Energinet | FID | Energinet | 2022 | 306.8
Transmission Point | Balticconnector / Siuntio (FI) | Transmission Balti Connector Finland | Transmission Finland | TRA-F-928 | Balticconnector Finnish part | Baltic Connector Oy | FID | Baltic Connector Oy | 2019 | 32
Transmission Point | Balticconnector / Siuntio (FI) | Transmission Finland | Transmission Balti Connector Finland | TRA-F-928 | Balticconnector Finnish part | Baltic Connector Oy | FID | Baltic Connector Oy | 2019 | 32
Transmission Point | Balticconnector / Siuntio (FI) | Transmission Balti Connector Finland | Transmission Finland | TRA-F-928 | Balticconnector Finnish part | Baltic Connector Oy | FID | Baltic Connector Oy | 2020 | 48
Transmission Point | Balticconnector / Siuntio (FI) | Transmission Finland | Transmission Balti Connector Finland | TRA-F-928 | Balticconnector Finnish part | Baltic Connector Oy | FID | Baltic Connector Oy | 2020 | 48
Transmission Point | Zone L-Gas GUD/OGE | Transmission Germany (DE GASPOOL L-Gas) | Transmission Germany (DE NCG L-Gas) | TRA-N-955 | GUD: Complete conversion to H-gas | Gasunie Deutschland Transport Services GmbH | Less-Advanced | Gasunie Deutschland Transport Services GmbH | 2027 | -42
|  |  |  | ETR-N-300 | HyOffWind Zeebrugge | Fluxys, Eoly, Parkwind | Less-Advanced | Eoly & Parkwind | 2020 | 0.4
|  |  |  | ETR-A-437 | Supercritical water gasification facilities | Gasunie Transport Services B.V. | Advanced | Gasunie Transport Services B.V. | 2020 | 2.4
|  |  |  | ETR-A-437 | Supercritical water gasification facilities | Gasunie Transport Services B.V. | Advanced | Gasunie Transport Services B.V. | 2021 | 2.4
|  |  |  | ETR-A-437 | Supercritical water gasification facilities | Gasunie Transport Services B.V. | Advanced | Gasunie Transport Services B.V. | 2022 | 2.4
|  |  |  | ETR-A-437 | Supercritical water gasification facilities | Gasunie Transport Services B.V. | Advanced | Gasunie Transport Services B.V. | 2023 | 7
|  |  |  | ETR-A-437 | Supercritical water gasification facilities | Gasunie Transport Services B.V. | Advanced | Gasunie Transport Services B.V. | 2024 | 7
|  |  |  | ETR-A-437 | Supercritical water gasification facilities | Gasunie Transport Services B.V. | Less-Advanced | Gasunie Transport Services B.V. | 2025 | 13.7
|  |  |  | ETR-N-449 | Hydrogen Region Lausitz | ONTRAS Gastransport GmbH | Less-Advanced | ONTRAS Gastransport GmbH | 2021 | 0.91
|  |  |  | ETR-N-449 | Hydrogen Region Lausitz | ONTRAS Gastransport GmbH | Less-Advanced | ONTRAS Gastransport GmbH | 2030 | 0.9
|  |  |  | ETR-N-562 | Energy Park Bad Lauchstädt | ONTRAS Gastransport GmbH | Less-Advanced | ONTRAS Gastransport GmbH | 2023 | 0.6
|  |  |  | ETR-N-427 | P2G integrated in Reganosa NG Transmission Grid | Reganosa | Less-Advanced | Reganosa | 2024 | 1.9
|  |  |  | ETR-N-483 | L2DG (LNG to Decarbonised Gas) | Reganosa | Less-Advanced | Reganosa | 2024 | 3.8
|  |  |  | ETR-N-305 | PEGASUS | SGI SPA | Less-Advanced | SGI SPA | 2024 | 0.12
|  |  |  | ETR-F-516 | CNG and L-CNG stations | Snam Rete Gas | FID | Snam4Mobility S.p.A. | 2022 | 1.83

## Enablers
Enabler Projects
Enabler Project Type | Enabler Code | Enabler Project Name | Enabled Code | Enabled Project Name
Pipeline including CS | TRA-A-10 | Poseidon Pipeline | TRA-A-330 | EastMed Pipeline
Pipeline including CS | TRA-N-53 | White Stream | TRA-A-339 | Trans-Caspian
LNG Terminal | LNG-A-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | TRA-A-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section
Pipeline including CS | TRA-A-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | LNG-A-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section
Pipeline including CS | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | TRA-F-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia)
Pipeline including CS | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica
Pipeline including CS | TRA-F-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac
Pipeline including CS | TRA-F-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica
Pipeline including CS | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | TRA-N-299 | M3/1 Šempeter - Vodice
Pipeline including CS | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia
Pipeline including CS | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec)
Pipeline including CS | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak)
Pipeline including CS | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade
Pipeline including CS | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade
Pipeline including CS | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia
Pipeline including CS | TRA-A-123 | Városföld CS | TRA-A-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage
Pipeline including CS | TRA-F-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | TRA-A-621 | Poland - Ukraine Gas Interconnection (PL section)
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section)
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | TRA-A-273 | Poland - Czech Republic Gas Interconnection (PL section)
Pipeline including CS | TRA-A-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | TRA-A-320 | Carregado Compressor Station
Pipeline including CS | TRA-F-291 | NOWAL - Nord West Anbindungsleitung | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink)
Pipeline including CS | TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | TRA-F-592 | Balkan Gas Hub-Necessary expansion of the Bulgarian gas transmission system
Pipeline including CS | TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | TRA-N-137 | Balkan Gas Hub - Interconnection Bulgaria - Serbia
Pipeline including CS | TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | TRA-A-654 | Eastring - Bulgaria
Pipeline including CS | TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | UGS-A-138 | Balkan Gas Hub - UGS Chiren Expansion
Pipeline including CS | TRA-N-299 | M3/1 Šempeter - Vodice | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade
Pipeline including CS | TRA-A-320 | Carregado Compressor Station | TRA-A-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border)
Pipeline including CS | TRA-A-330 | EastMed Pipeline | TRA-A-10 | Poseidon Pipeline
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla)
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-A-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo)
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod)
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-F-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia)
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac
Pipeline including CS | TRA-A-339 | Trans-Caspian | TRA-N-53 | White Stream
Pipeline including CS | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase I | TRA-A-1268 | Romania-Serbia Interconnection
Pipeline including CS | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase I | TRA-A-362 | Development on the Romanian territory of the Southern Transmission Corridor
Pipeline including CS | TRA-A-362 | Development on the Romanian territory of the Southern Transmission Corridor | TRA-A-1322 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase II
Storage Facility | UGS-F-374 | Enhancement of Incukalns UGS | TRA-N-1181 | Connecting pipe to LNG terminal in Latvia
Storage Facility | UGS-F-374 | Enhancement of Incukalns UGS | TRA-A-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part)
Pipeline including CS | TRA-A-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | TRA-A-123 | Városföld CS
Pipeline including CS | TRA-A-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage
Pipeline including CS | TRA-A-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | TRA-N-1181 | Connecting pipe to LNG terminal in Latvia
Pipeline including CS | TRA-A-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | UGS-F-374 | Enhancement of Incukalns UGS
Pipeline including CS | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade
Pipeline including CS | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec)
Pipeline including CS | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade
Pipeline including CS | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak)
Pipeline including CS | TRA-A-394 | Norwegian tie-in to Danish upstream system | TRA-F-780 | Baltic Pipe project – onshore section in Denmark
Pipeline including CS | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector
Pipeline including CS | TRA-F-780 | Baltic Pipe project – onshore section in Denmark | TRA-A-394 | Norwegian tie-in to Danish upstream system
Pipeline including CS | TRA-N-809 | Reallocation H-Gas towards NL: Bunde/Oude to Zone Oude Statenzijl H | TRA-A-808 | Additional transport of gas volumes to the Netherlands
Pipeline including CS | TRA-N-809 | Reallocation H-Gas towards NL: Bunde/Oude to Zone Oude Statenzijl H | TRA-A-496 | Increase of Gas Transport to the Netherlands
Pipeline including CS | TRA-F-895 | Balticconnector | TRA-F-915 | Enhancement of Estonia-Latvia interconnection
Pipeline including CS | TRA-F-915 | Enhancement of Estonia-Latvia interconnection | TRA-F-895 | Balticconnector
Pipeline including CS | TRA-F-964 | New NTS developments for taking over gas from the Black Sea shore | TRA-F-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea
Pipeline including CS | TRA-F-964 | New NTS developments for taking over gas from the Black Sea shore | TRA-F-357 | NTS developments in North-East Romania
Pipeline including CS | TRA-F-964 | New NTS developments for taking over gas from the Black Sea shore | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla)
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod)
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | TRA-A-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo)
Pipeline including CS | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac
Pipeline including CS | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system
Pipeline including CS | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | TRA-F-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia)
Pipeline including CS | TRA-N-1129 | Compressor Station Kipi Increment | TRA-N-14 | Komotini-Thesprotia pipeline
Pipeline including CS | TRA-A-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | TRA-A-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section
Pipeline including CS | TRA-F-1267 | Upgrade Sülstorf station | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink)
Pipeline including CS | TRA-N-1278 | Compressor station at Ambelia | TRA-F-941 | Metering and Regulating station at Nea Messimvria
Pipeline including CS | TRA-A-1322 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase II | TRA-A-362 | Development on the Romanian territory of the Southern Transmission Corridor
Pipeline including CS | TRA-A-1322 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase II | TRA-A-1268 | Romania-Serbia Interconnection

## National Development Plan Info
NDP Information
Code | Project Name | Country | Promoter | Maturity Status | PCI 3rd List | PCI 3rd List Code | Is Part of a NDP | NDP Number | NDP Name Or Reason for non-NDP inclusion | NDP Website | NDP Release Date
TRA-N-7 | Development for new import from the South (Adriatica Line) | Italy | Snam Rete Gas S.p.A. | Less-Advanced | Yes | 7.3.4 | Yes | RN_04 | Ten-year development plan of the natural gas transmission network 2018-2027 | URL | 2018-11-30
TRA-N-8 | Import developments from North-East | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | Yes | RN_06 | Ten-year development plan of the natural gas transmission network 2018-2027 | URL | 2018-11-30
TRA-N-9 | Additional Southern developments | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | Yes | RN_07 | Snam Rete Gas TYNDP 2017-2026 | URL | 2018-11-30
TRA-A-10 | Poseidon Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | Yes | 7.3.3 | Yes | n.a. | Piano decennale di sviluppo delle reti di trasporto di gas naturale 2017-2026 (pag. 55, 56, 98) | URL | 2017-11-30
TRA-A-12 | GALSI Pipeline Project | Italy | Galsi S.p.A. | Advanced | No |  | Yes | n.a. | SNAM NDP 2018-2027 | URL | 2018-12-31
TRA-N-14 | Komotini-Thesprotia pipeline | Greece | DESFA S.A. | Less-Advanced | No |  | Yes | 2.2.1.5 | Development Plan NNGS 2017-2026 | URL | 2019-02-22
TRA-A-21 | Bidirectional Austrian-Czech Interconnector (BACI) | Austria | GAS CONNECT AUSTRIA GmbH | Advanced | Yes | 6.4 | Yes | GCA 2015/01a | NDP 2019 - 2028 | URL | 2019-02-11
TRA-N-27 | Physical reverse flow from NI to GB and IE via SNIP pipeline | United Kingdom | Premier Transmission Limited | Less-Advanced | Yes | 5.1.2 | Yes | 5.1.2 | Northern Ireland Gas Capacity Statement - section 3.21 | URL | 2018-12-04
LNG-A-30 | Shannon LNG Terminal and Connecting Pipeline | Ireland | Shannon LNG Ltd | Advanced | Yes | 5.3 | Yes | 5.4 | Gas Networks Ireland 2018 Network Development Plan | URL | 2018-12-21
TRA-A-31 | Melita TransGas Pipeline | Malta | Melita TransGas Co. Ltd. | Advanced | Yes | 5.19 | Yes | Section 4.3.2 | Malta National Reform Programme April 2019 | URL | 2019-04-30
LNG-A-50 | Gate terminal phase 3 | Netherlands | Gate | Advanced | No |  | Yes | unknown see GTS | GTS | URL | 2018-03-01
TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Croatia | Plinacro Ltd | Less-Advanced | No |  | Yes | 1.15 | 2018-2027 | URL | 2017-12-15
TRA-A-68 | Ionian Adriatic Pipeline | Croatia | Plinacro Ltd | Advanced | No |  | Yes | 1.12, 1.25-1.27, 5.5 | 2018-2027 | URL | 2017-12-15
TRA-A-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Croatia | Plinacro Ltd | Advanced | No |  | Yes | 1.30, 1.31, 1.22 | 2018-2027 | URL | 2017-12-15
TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Croatia | Plinacro Ltd | Less-Advanced | Yes | 6.5.6 | Yes | 1.19, 1.20, 1.21 | 2018-2027 | URL | 2017-12-15
LNG-A-79 | Paldiski LNG Terminal | Estonia | Balti Gaas plc | Advanced | No |  | Yes | - | Estonian transmission system development plan for 2018-2027 | URL | 2018-03-03
LNG-F-82 | LNG terminal Krk | Croatia | LNG Hrvatska d.o.o. | FID | Yes | 6.5.1 | Yes | LNG terminal on the island of Krk | DESETOGODISNJI PLAN RAZVOJA PLINSKOG TRANSPORTNOG SUSTAVA REPUBLIKE HRVATSKE 2018. - 2027. | URL | 2017-11-01
TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla) | Croatia | Plinacro Ltd | Advanced | Yes | 6.26.1.1 | Yes | 1.9, 1.10, 1.11 | 2018-2027 | URL | 2017-12-15
TRA-F-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Croatia | Plinacro Ltd | FID | Yes | 6.5.1 | Yes | 1.18 | 2018-2027 | URL | 2017-12-15
TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | Slovenia | Plinovodi d.o.o. | Less-Advanced | No |  | Yes | C1 | TYNDP for the period 2019-2028 | URL | 2018-11-26
TRA-N-94 | CS Kidričevo, 2nd phase of upgrade | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.26.1.2 | Yes | C5 | TYNDP for the period 2019-2028 | URL | 2018-11-26
TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Slovenia | Plinovodi d.o.o. | Less-Advanced | No |  | Yes | C2 | TYNDP for the period 2019-2028 | URL | 2018-11-26
TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.23 | Yes | C3 | TYNDP for the period 2019-2028 | URL | 2018-11-26
TRA-A-123 | Városföld CS | Hungary | FGSZ Ltd. | Advanced | Yes | 6.24.4.3 | Yes | 12.10. | Hungarian TYNDP 2018 | URL | 2019-01-31
TRA-N-128 | Compressor Station Kipi | Greece | DESFA S.A. | Less-Advanced | Yes | 6.8.1 | Yes | 2.2.1.2 | National Development Plan NNGS 2017-2026 | URL | 2019-02-21
TRA-A-133 | Bidirectional Austrian Czech Interconnection (BACI) | Czechia | NET4GAS, s.r.o. | Advanced | Yes | 6.4 | Yes | TRA-N-133 | CZ NDP 2019-2028 (approved) | URL | 2018-10-31
TRA-A-136 | Czech-Polish Gas Interconnector (CPI) | Czechia | NET4GAS, s.r.o. | Advanced | Yes | 6.2.10; 6.2.12 | Yes | TRA-N-136 | CZ NDP 2019-2028 (approved) | URL | 2018-10-31
TRA-N-137 | Balkan Gas Hub - Interconnection Bulgaria - Serbia | Bulgaria | Bulgartransgaz EAD | Less-Advanced | Yes | 6.10 | Yes | Sectin 5.2 (5.2.3) | 2019-2028 Ten-year network development plan of BTG | URL | 2019-04-23
UGS-A-138 | Balkan Gas Hub - UGS Chiren Expansion | Bulgaria | Bulgartransgaz EAD | Advanced | Yes | 6.20.2 | Yes | Section 5.3 (5.3.1) | 2019-2028 Ten-year network development plan of BTG | URL | 2019-04-23
TRA-F-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | Romania | SNTGN Transgaz SA | FID | Yes | 6.24.10.1 | Yes | 7.3 | The National Gas Transmission System Development Plan 2018-2027 | URL | 2018-12-14
TRA-A-161 | South Transit East Pyrenees (STEP) - ENAGAS | Spain | Enagas Transporte S.A.U. | Advanced | Yes | 5.5.1 | Yes | No code in the NDP | Conexión internacional con Francia por Cataluña | URL | 2008-05-01
LNG-F-163 | Gran Canaria LNG Terminal | Spain | Gascan | FID | No |  | Yes | No code in the NDP | Planta de regasificación de Gran Canaria | URL | 2008-05-01
LNG-F-178 | Musel LNG terminal | Spain | Enagas Transporte S.A.U. | FID | No |  | Yes | No code in the NDP | planta de regasificación de El Musel | URL | 2008-05-01
LNG-F-183 | Tenerife LNG Terminal | Spain | Gascan | FID | No |  | Yes | No code in the NDP | Planta de regasificacion de Tenerife | URL | 2008-05-01
TRA-F-190 | Poland - Slovakia interconnection | Slovakia | eustream,a.s. (a joint-stock company) | FID | Yes | 6.2.1 | Yes | 4.1.1.1.-PL-SK gas interconnection | National Development Plan 2019-2028 | URL | 2018-11-30
TRA-N-192 | Entry capacity expansion GATE terminal | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | No |  | Yes | 6.5.2 | Netwerk Ontwikkelingsplan 2017 | URL
TRA-F-208 | Reverse Flow TENP Germany | Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | FID | Yes | 5.10 | Yes | 305-02 | Netzentwicklungsplan Gas 2018-2028 | URL | 2019-03-20
TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | Poland | GAZ-SYSTEM S.A. | FID | Yes | 8.5 | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-N-224 | Gaspipeline Brod - Zenica | Bosnia Herzegovina | BH-Gas d.o.o. | Less-Advanced | No |  | Yes | PTG1 | Framework Energy Strategy of BiH until 2035, 2018 and Strategic Plan and Program of FBiH, 2009 | URL | 2018-08-29
LNG-N-225 | Montoir LNG Terminal Expansion | France | Elengy | Less-Advanced | No |  | Yes | Montoir Extension | GRTgaz Ten Year Development plan 2018-2027 | URL | 2019-02-04
LNG-N-227 | Fos Cavaou LNG Terminal Expansion | France | Fosmax LNG | Less-Advanced | No |  | Yes | Fos Cavaou Extension | GRTgaz Ten Year Development plan 2018-2027 | URL | 2019-02-04
UGS-A-233 | Depomures | Romania | Engie Romania SA | Advanced | Yes | 6.20.4 | Yes | 8.5 | National Gas Transmission System Developpment Plan 2018-2027 | URL | 2018-12-14
TRA-N-245 | North - South Gas Corridor in Eastern Poland | Poland | GAZ-SYSTEM S.A. | Less-Advanced | Yes | 6.2.2 | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-F-247 | North - South Gas Corridor in Western Poland | Poland | GAZ-SYSTEM S.A. | FID | Yes | 6.2.11 | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-A-252 | South Transit East Pyrenees (STEP) - TEREGA | France | TEREGA | Advanced | Yes | 5.5.1 | Yes | No number | 2019 TEREGA NDP | URL
TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | France | GRTgaz | Less-Advanced | No |  | Yes | Augmentation des capacités d’entrée à partir du terminal de Montoir de 10 à 12,5 Gm³/an | Plan décennal de développement du réseau de transport de GRTgaz 2018-2027 | URL | 2019-02-04
UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | Italy | STOGIT | FID | No |  | Yes | not applicable | Ten-year development plan of the natural gas transmission network 2018-2027 | URL
TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | France | GRTgaz | Less-Advanced | No |  | Yes | Extension du terminal de Fos Cavaou à 16,5 Gm³/an | Plan décennal de développement du réseau de transport de GRTgaz 2018-2027 | URL | 2019-02-04
TRA-A-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | Poland | GAZ-SYSTEM S.A. | Advanced | Yes | 8.3.2 | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
LNG-F-272 | Upgrade of LNG terminal in Świnoujście | Poland | GAZ-SYSTEM S.A. | FID | Yes | 8.7 | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-A-273 | Poland - Czech Republic Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | Advanced | Yes | 6.2.10 | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | FID | Yes | 6.2.1 | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-A-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | Portugal | REN-Gasodutos, S.A. | Advanced | Yes | 5.4.1 | Yes | - | PDIRGN 2018 - 2027 | URL | 2018-12-19
TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | Hungary | FGSZ Ltd. | FID | Yes | 6.24.1.1 | Yes | 12.5. | Hungarian TYNDP 2018 | URL | 2019-01-31
TRA-F-291 | NOWAL - Nord West Anbindungsleitung | Germany | GASCADE Gastransport GmbH | FID | No |  | Yes | 410-01a and 410-01b | Netzentwicklungsplan Gas 2018-2028 | URL | 2019-03-20
UGS-A-294 | Islandmagee Gas Storage Facility | United Kingdom | Islandmagee Storage Limited | Advanced | Yes | 5.1.3 | Yes | n.a. | Northern Ireland Gas Capacity Statement | URL
LNG-A-295 | Mugardos LNG Terminal: Send-out Increase | Spain | Reganosa | Advanced | No |  | Yes | No Number- Name: Ampliación Planta de Reganosa. Ampliación de Emisión a 825,600 Nm3/h | PLANIFICACION ELECTRICIDAD Y GAS 2008-2016 | URL | 2008-05-01
TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | Bulgaria | Bulgartransgaz EAD | FID | Yes | 6.8.2 | Yes | Section 5.5. | 2019-2028 Ten-year network development plan of BTG | URL | 2019-04-23
TRA-N-299 | M3/1 Šempeter - Vodice | Slovenia | Plinovodi d.o.o. | Less-Advanced | No |  | Yes | C7, C8, C9 (3 sections) | TYNDP for the period 2019-2028 | URL | 2018-11-26
TRA-A-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Croatia | Plinacro Ltd | Advanced | No |  | Yes | 1.13 | 2018-2027 | URL | 2017-12-15
TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Croatia | Plinacro Ltd | Less-Advanced | No |  | Yes | 1.35 and 1.36 | 2018-2027 | URL | 2018-12-15
TRA-F-307 | H-gas exit OSZ GTG Nord | Netherlands | Gasunie Transport Services B.V. | FID | No |  | Yes | 6.5.1 | Netwerk Ontwikkelingsplan 2017 | URL
TRA-A-320 | Carregado Compressor Station | Portugal | REN-Gasodutos, S.A. | Advanced | No |  | Yes | - | PDIRGN 2018 - 2027 | URL | 2018-12-19
TRA-N-325 | Slovenian-Hungarian interconnector | Hungary | FGSZ Ltd. | Less-Advanced | Yes | 6.23 | Yes | 12.12. | Hungarian TYNDP 2017 | URL | 2018-12-19
TRA-F-329 | ZEELINK | Germany | Open Grid Europe GmbH and Thyssengas GmbH | FID | No |  | Yes | 203-02, 204-02a-d, 205-02a-b, 416-02, | Netzentwicklungsplan 2018 (German NDP 2018) | URL | 2019-03-20
TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | Croatia | Plinacro Ltd | FID | Yes | 6.5.5 | Yes | 5.1 | 2018-2027 | URL | 2017-12-15
TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Croatia | Plinacro Ltd | Less-Advanced | No |  | Yes | 1.37 | 2018-2027 | URL | 2017-12-15
TRA-F-340 | CS Wertingen | Germany | bayernets GmbH | FID | No |  | Yes | 036-04 | Netzentwicklungsplan Gas 2018-2028 | URL | 2018-04-01
TRA-F-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | Lithuania | AB Amber Grid | FID | Yes | 8.5 | Yes | n/a | Network Development Plan 2018-2027 | URL | 2018-08-23
TRA-A-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | Lithuania | AB Amber Grid | Advanced | Yes | 8.2.1 | Yes | n/a | Ten-Year Network Development Plan 2018-2027 | URL | 2018-08-23
TRA-N-354 | Interconnection with Slovenia | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | Yes | RN_03 | Ten-year development plan of the natural gas transmission network 2018-2027 | URL | 2018-11-30
UGS-A-356 | Underground Gas Storage Velke Kapusany | Slovakia | NAFTA a.s. (joint stock company) | Advanced | No |  | Yes | chapter 3.3 | Ten-Year Network Development Plan of the transmission system of the company Eustream | URL | 2017-11-30
TRA-F-357 | NTS developments in North-East Romania | Romania | SNTGN Transgaz SA | FID | No |  | Yes | 7.4 | The National Gas Transmission System Development Plan 2018 - 2027 | URL | 2018-12-14
TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase I | Romania | SNTGN Transgaz S.A. | FID | Yes | 6.24.1.2 | Yes | 7.1.1 | Development Plan for the National GTS 2018-2027 | URL | 2018-12-14
TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | Austria | GAS CONNECT AUSTRIA GmbH | Less-Advanced | Yes | 6.26.1.4 | Yes | GCA 2015/08 | NDP 2019-2028 | URL | 2019-02-11
TRA-A-362 | Development on the Romanian territory of the Southern Transmission Corridor | Romania | SNTGN Transgaz SA | Advanced | Yes | 6.24.4.5 | Yes | 7.2 | The National Gas Transmission System Development Plan 2018-2027 | URL | 2018-12-14
TRA-A-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | Hungary | FGSZ Ltd. | Advanced | Yes | 6.24.4.6 | Yes | 12.5 | Hungarian TYNDP 2018 | URL | 2019-01-31
TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | Bulgaria | ICGB a.d. | FID | Yes | 6.8.1 | Yes | not applicable | Included in both the TYNDPs of Greece and Bulgaria | URL
TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.26.1.5 | Yes | C4 | TYNDP for the period 2019-2028 | URL | 2018-11-26
TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.26.6 | Yes | C12 | TYNDP for the period 2019-2028 | URL | 2018-11-26
TRA-N-402 | TENP Security of Supply | Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | Less-Advanced | No |  | Yes | 552-01 / 554-01 / 555-01 | Netzentwicklungsplan Gas 2018-2028 | URL | 2019-03-20
TRA-F-409 | Larino - Chieti | Italy | SGI S.p.A: | FID | No |  | Yes | 5712 | LARINO-CHIETI | URL | 2018-09-30
TRA-N-423 | GCA Mosonmagyaróvár | Austria | GAS CONNECT AUSTRIA GmbH | Less-Advanced | Yes | 6.24.1.3 | Yes | GCA 2015/05 | NDP 2019 - 2028 | URL | 2019-02-11
TRA-F-424 | SAN MARCO - RECANATI | Italy | SGI S.p.A. | FID | No |  | Yes | 5681 | SAN MARCO - RECANATI | URL | 2018-11-30
TRA-A-429 | Adaptation L- gas - H-gas | France | GRTgaz and Storengy | Advanced | Yes | 5.21 | Yes | Plan de conversion du gaz B en gaz H | Plan décennal de développement du réseau de GRTgaz 2018-2027 | URL | 2019-02-04
TRA-N-439 | Stazione di Spinta "San Marco" | Italy | S.G.I. S.p.A. | Less-Advanced | No |  | Yes | 5515 | Stazione si Spinta San Marco | URL | 2018-11-30
TRA-F-500 | L/H Conversion Belgium | Belgium | Fluxys Belgium | FID | Yes | 5.21 | Yes | L/H Conversion | Ten-Year Indicative Investment Programme Fluxys Belgium & Fluxys LNG 2017-2026 | URL
TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Hungary | FGSZ Ltd. | Less-Advanced | Yes | 6.2.13 | Yes | TRA-N-524 (new nr will be received once project is approved) | National Development Plan- MGT 10 Year Development Plan | URL
TRA-F-592 | Balkan Gas Hub-Necessary expansion of the Bulgarian gas transmission system | Bulgaria | Bulgartransgaz EAD | FID | Yes | 6.25.4 | Yes | Section 5.1. (5.1.1) | 2019-2028 Ten-year network development plan of BTG | URL | 2019-04-23
TRA-N-596 | Interconnection between the RO and the UA gas transmission systems | Romania | SNTGN Transgaz SA | Less-Advanced | No |  | Yes | 7.9 | The Development Plan of the National Gas Transmission System 2018- 2027 | URL | 2018-12-14
TRA-A-621 | Poland - Ukraine Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | Advanced | No |  | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-A-628 | Eastring - Slovakia | Slovakia | eustream, a.s. (a joint stock company) | Advanced | Yes | 6.25.1 | Yes | None | Development plan of the transmission system of eustream, a.s. for the period 2019 - 2028 | URL | 2018-11-30
TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Hungary | FGSZ Ltd. | Less-Advanced | Yes | 6.2.13 | Yes | TRA-N-636 | National Development Plan - MGT 10 Year Development Plan | URL
TRA-A-654 | Eastring - Bulgaria | Bulgaria | Bulgartransgaz EAD | Advanced | Yes | 6.25.1 | Yes | Section 5.1 (5.1.2) | 2019-2028 Ten-year network development plan of BTG | URL | 2019-04-23
TRA-A-656 | Eastring - Hungary | Hungary | FGSZ Ltd. | Advanced | Yes | 6.25.1 | Yes | 12.13. | National Development Plan 2018 | URL | 2018-12-19
TRA-F-752 | Capacity4Gas – DE/CZ | Czechia | NET4GAS, s.r.o. | FID | No |  | Yes | TRA-F-752 | CZ NDP 2019-2028 (approved) | URL | 2018-10-31
TRA-F-755 | CS Rimpar | Germany | GRTgaz Deutschland GmbH | FID | No |  | Yes | 312-02 | Netzentwicklungsplan Gas 2018 | URL | 2019-03-20
TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | Germany | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | FID | No |  | Yes | 412-03, 507-01a,b,c,d,e,f | Netzentwicklungsplan Gas 2018-2028 | URL | 2019-03-20
TRA-N-809 | Reallocation H-Gas towards NL: Bunde/Oude to Zone Oude Statenzijl H | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | No |  | Yes | ID504-01a; ID504-01b; ID504-01c | Netzentwicklungsplan Gas 2018-2028 | URL | 2019-03-20
TRA-F-814 | Upgrade for IP Deutschneudorf et al. for More Capacity | Germany | ONTRAS Gastransport GmbH | FID | No |  | Yes | 507-01 g, 507-01 h, ID 507-02 i, 507-01 j, 507-01 m | Netzentwicklungsplan Gas 2018-2028 | URL | 2019-03-20
LNG-F-824 | LNG Terminal in Klaipeda | Lithuania | AB Klaipėdos Nafta | FID | No |  | Yes | Action Plan of National Energy Independence strategy, aprroved by the Goverment on 2018-12-05, task 8.1.1.1. | National Energy Independence strategy, appproved 2018-06-26 by Parlament, Order No. XI-2133 | URL | 2018-06-26
TRA-A-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | Ireland | Gas Networks Ireland | Advanced | Yes | 5.1.1 | Yes | PCI 5.1.1 | GNI, Network Development Plan 2017 | URL | 2017-12-15
TRA-N-851 | Southern Interconnection pipeline BiH/CRO | Bosnia Herzegovina | BH-GAS d.o.o. | Less-Advanced | No |  | Yes | No 10 in Framework Energy Strategy BiH until 2035 and PTG2 in SPP | Framework Energy Strategy BiH until 2035, 2018 and Strategic Plan and Programme of FBiH, 2009 | URL | 2018-08-29
TRA-N-873 | Additional import at Oude StatenZijl area | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | No |  | Yes | 6.5.4. | Netwerk Ontwikkelingsplan 2017 | URL | 2017-11-30
TRA-N-882 | Transferring L-gas infrastructure to H-gas | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | No |  | Yes | 6.5.1 | Netwerk Ontwikkelingsplan 2017 | URL
TRA-F-895 | Balticconnector | Estonia | Elering AS | FID | Yes | 8.1.1 | Yes | paragraph 3.2 | EESTI GAASIÜLEKANDEVÕRGU ARENGUKAVA 2019‐2028 | URL | 2019-03-03
TRA-F-902 | Capacity increase at IP Lanžhot entry | Slovakia | eustream,a.s. (a joint-stock company) | FID | No |  | Yes | 4.1.1.3. Lanžhot | National Development Plan 2018-2027 | URL | 2017-11-30
TRA-N-910 | West Interconnection BiH/CRO | Bosnia Herzegovina | BH-Gas d.o.o. | Less-Advanced | No |  | Yes | No 11 - Framework Energy Strategy of BiH until 2035 and PTG4 - Strategic Plan and Program of Development Energy Sector in FBiH 2009 | Framework Energy Strategy of BiH until 2035 and Strategic Plan and Programe of Development Energy Sector in FBiH 2009 | URL | 2018-08-29
UGS-N-914 | UGS Damasławek | Poland | GAZ-SYSTEM S.A. | Less-Advanced | No |  | Yes | N/A | National Ten-Year Transmission System Development Plan 2020-2029 | URL
TRA-F-915 | Enhancement of Estonia-Latvia interconnection | Estonia | Elering AS | FID | Yes | 8.2.2 | Yes | paragraph 3.2 | EESTI GAASIÜLEKANDEVÕRGU ARENGUKAVA 2019‐2028 | URL | 2019-03-03
TRA-F-918 | Capacity4Gas – CZ/SK | Czechia | NET4GAS, s.r.o. | FID | No |  | Yes | TRA-F-918 | CZ NDP 2019-2028 (approved) | URL | 2018-10-31
TRA-F-941 | Metering and Regulating station at Nea Messimvria | Greece | DESFA S.A. | FID | Yes | 7.1.3 | Yes | 2.2.1.4 | National Development Plan NNGS 2017-2026 | URL | 2019-02-21
LNG-N-947 | FSRU Polish Baltic Sea Coast | Poland | GAZ-SYSTEM S.A. | Less-Advanced | No |  | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-F-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Germany | Gastransport Nord GmbH | FID | No |  | Yes | 432-02b | Netzentwicklungsplan Entwurf 2018-2028 | URL | 2019-03-20
TRA-A-950 | Guitiriz - Lugo - Zamora pipeline | Spain | Reganosa | Advanced | No |  | Yes | N/A. | PLANIFICACION ELECTRICIDAD Y GAS 2008-2016 | URL | 2008-05-01
TRA-A-951 | Embedding CS Folmhusen in H-Gas | Germany | Gasunie Deutschland Transport Services GmbH | Advanced | No |  | Yes | ID 300-02 | NEP Gas 2015; NEP Gas 2016-2026; NEP Gas 2018-2028 | URL | 2019-03-20
TRA-F-954 | TAG Reverse Flow | Austria | Trans Austria Gasleitung GmbH | FID | No |  | Yes | TAG 2016-01 | Coordinated Network Development Plan 2018-2027 | URL | 2018-01-19
TRA-N-955 | GUD: Complete conversion to H-gas | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | No |  | Yes | ID 221-01 ID; ID 222-02; ID 223-01 | NEP Gas 2014; NEP Gas 2015; NEP Gas 2016-2026; NEP Gas 2018-2028 | URL | 2019-03-20
TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | Romania | SNTGN Transgaz SA | Less-Advanced | Yes | 6.24.10.2 | Yes | 7.5 | The National Gas Transmission System Development Plan 2018-2027 | URL | 2018-12-14
LNG-A-962 | Tallinn LNG | Estonia | Liwathon E.O.S. AS / Port of Tallinn AS | Advanced | No |  | Yes | Paragraph 3 point 7 | Eesti Gaasi Ülekandevõrgu arengukava 2018-2027. | URL | 2018-03-03
TRA-F-964 | New NTS developments for taking over gas from the Black Sea shore | Romania | SNTGN Transgaz SA | FID | Yes | 6.24.10.3 | Yes | 7.6 | The National Gas Transmission System Development Plan 2018-2027 | URL | 2018-12-14
TRA-A-967 | Nea-Messimvria to Evzoni/Gevgelija pipeline (IGNM) | Greece | DESFA S.A. | Advanced | No |  | Yes | 2.1.2.1 | NDP 2017-2026 | URL
TRA-N-971 | Compressor station at Nea Messimvria | Greece | DESFA S.A. | Less-Advanced | Yes | 7.1.3 | Yes | 2.2.1.4 | National Development Plan NNGS 2017-2026 | URL | 2019-02-21
TRA-A-980 | Interconnection North Macedonia-Greece (North Macedonian part) | North Macedonia | MER JSC Skopje | Advanced | No |  | Yes | Energy sector, no. 2 | Work Program of the Government of R.Macedonia | URL | 2018-11-27
TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Croatia | Plinacro Ltd | Less-Advanced | Yes | 6.26.1.3 | Yes | 5.3 and 5.4 | 2018-2027 | URL | 2017-12-15
TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Croatia | Plinacro Ltd | Less-Advanced | Yes | 6.5.6 | Yes | 1.32 | 2018-2027 | URL | 2017-12-15
TRA-N-1129 | Compressor Station Kipi Increment | Greece | DESFA S.A. | Less-Advanced | No |  | Yes | 2.2.1.2 | Development Plan NNGS 2017-2026 | URL | 2019-02-21
TRA-A-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | Poland | GAZ-SYSTEM S.A. | Advanced | Yes | 8.3.2 | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2020 | URL
TRA-F-1193 | TAP interconnection | Italy | Snam Rete Gas S.p.A. | FID | No |  | Yes | RN_02 | Ten-year development plan of the natural gas transmission network 2018-2027 | URL | 2017-11-30
TRA-N-1194 | Sardinia Methanization | Italy | ENURA S.p.A. | Less-Advanced | No |  | Yes | RN_09 | Ten-year development plan of the natural gas transmission network 2018-2027 | URL | 2018-11-30
TRA-N-1195 | Matagiola - Massafra pipeline | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | Yes | RN_05 | Ten-year development plan of the natural gas transmission network 2018-2027 | URL | 2017-11-30
TRA-A-1199 | LNG Terminal Brunsbuettel - Grid Integration | Germany | Gasunie Deutschland Transport Service GmbH | Advanced | No |  | Yes | ID300-01 | Netzentwicklungsplan Gas 2018-2028 | URL | 2019-03-20
TRA-N-1227 | Gorizia plant upgrade | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | Yes | RN_16 | Ten-year development plan of the natural gas transmission network 2018-2027 | URL | 2018-11-30
TRA-N-1235 | Firm transmission capacity increase at the IP Veľké Zlievce | Slovakia | eustream,a.s. | Less-Advanced | Yes | 6.2.13 | Yes | 4.1.1.3 a) Firm transmission capacity increase at the IP Veľké Zlievce | National Development Plan 2019 - 2028 | URL | 2018-11-30
TRA-F-1241 | Interconnection with production in Gela | Italy | Snam Rete Gas S.p.A. | FID | No |  | Yes | RN_17 | Ten-year development plan of the natural gas transmission network 2018-2027 | URL | 2018-11-30
TRA-N-1246 | Greece - Italy interconnection | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | Yes | not applicable | Ten-year development plan of the natural gas transmission network 2018-2027 | URL | 2018-11-30
TRA-F-1254 | CS Elten | Germany | Open Grid Europe GmbH and Thyssengas GmbH | FID | No |  | Yes | 422/01 | German NDP 2018 - 2028 (NEP 2018 -2028) | URL | 2019-03-20
TRA-N-1265 | Biomethane productions interconnection | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | Yes | NA | en-year development plan of the natural gas transmission network 2018-2027 | URL | 2018-11-30
TRA-F-1267 | Upgrade Sülstorf station | Germany | NGT GmbH / GUD GmbH & Co. KG / Fluxys D GmbH | FID | No |  | Yes | 507-01k | Netzentwicklungsplan Gas 2018-2028 | URL | 2019-03-20
TRA-A-1268 | Romania-Serbia Interconnection | Romania | SNTGN Tranzgaz SA | Advanced | No |  | Yes | 7.7 | THE NATIONAL GAS TRANSMISSION SYSTEM DEVELOPMENT PLAN 2018-2027 | URL | 2018-12-14
TRA-F-1271 | Compressor Station Krummhoern | Germany | Open Grid Europe GmbH | FID | No |  | Yes | 414-01 an 415-01 | Netzentwicklungsplan Gas 2018 (German NDP 2018) | URL | 2019-03-20
TRA-F-1276 | Compressor station at Nea Messimvria (3rd unit) | Greece | DESFA S.A. | FID | No |  | Yes | 2.1.2.8 | National Development Plan 2017-2026 | URL | 2019-02-21
TRA-F-1277 | Upgrading GMS Isaccea 1 and GMS Negru Voda 1 | Romania | SNTGN Transgaz SA | FID | No |  | Yes | 7.8 | The National Gas Transmission System development Plan 2018 - 2027 | URL | 2018-12-14
TRA-N-1278 | Compressor station at Ambelia | Greece | DESFA S.A. | Less-Advanced | No |  | Yes | 2.1.2.2 | National Development Plan 2017-2026 | URL | 2019-02-21
TRA-A-1303 | IAEF - Vlora ccgt | Albania | Albgaz Sha | Advanced | No |  | Yes | PiP1 | Plani 10 Vjecar i Zhvillimit (national TYNDP) | URL | 2018-02-15
TRA-A-1322 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase II | Romania | SNTGN Transgaz SA | Advanced | Yes | 6.24.4.4 | Yes | 7.1.2 | The Development Plan of the National Gas Transmission System 2018- 2027 | URL | 2018-12-14
ETR-N-20 | GNI Renewable Gas Central Grid Injection Project | Ireland | Gas Networks Ireland | Less-Advanced | No |  | No | N/A
ETR-N-22 | Ervia Cork CCUS | Ireland | Ervia (parent company of Gas Networks Ireland) | Less-Advanced | No |  | No | N/A
LNG-A-32 | Project GO4LNG LNG terminal Gothenburg | Sweden | Swedegas AB | Advanced | Yes | 8.6 | No | N/A | (2) no NDP exists in the country
TRA-F-51 | Trans Adriatic Pipeline | Greece | Trans Adriatic Pipeline AG | FID | Yes | 7.1.3 | No | N/A | TAP project is being developed on a stand-alone basis, independent from the national transmission systems of Greece, Albania and Italy.
TRA-N-53 | White Stream | Georgia | White Stream Ltd | Less-Advanced | No |  | No | N/A | (2) no NDP exists in the country
LNG-A-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Greece | Gastrade S.A. | Advanced | Yes | 6.9.1 | No | N/A | Gastrade has applied to DESFA for the interconnection of the Project with the NNGTS. DESFA conducted the Evaluation Study for the new interconnection. The Project is expected to be included in the very next updated NDP.
TRA-A-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Greece | Gastrade S.A. | Advanced | Yes | 6.9.1 | No | N/A | Gastrade has applied to DESFA for the interconnection of the Project with the NNGTS. DESFA conducted the Evaluation Study for the new interconnection. The Project is expected to be included in the very next updated NDP.
ETR-A-64 | Biomethane reverse flow Denmark | Denmark | Energinet | Advanced | No |  | No | N/A
ETR-N-80 | Power to Gas Production with infrastructure building/enhacement in Latvia | Latvia | JSC "Conexus Baltic Grid" | Less-Advanced | No |  | No | N/A
ETR-N-125 | Biomethane production with infrastructure building/enhancement in Latvia | Latvia | JSC "Conexus Baltic Grid" | Less-Advanced | No |  | No | N/A
TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Spain | Enagas Transporte S.A.U. | Less-Advanced | Yes | 5.4.1 | No | N/A | (1) the NDP was prepared at an earlier date and the project will be proposed for inclusion in the next NDP
ETR-N-226 | Fos Tonkin LNG Terminal Evolution | France | Elengy | Less-Advanced | No |  | No | N/A
LNG-A-296 | Mugardos LNG Terminal: 2nd Jetty | Spain | Reganosa | Advanced | No |  | No | N/A | The last aproved Spanish NDP ended in 2016. The Royal Decree-Law 13/2012 cancel any award procedures of new regasification plants in Spain. Currently, there isn´t any new NDP process or any NDP in force.
LNG-N-297 | Mugardos LNG Terminal: Storage Extension | Spain | Reganosa | Less-Advanced | No |  | No | N/A | The last aproved Spanish NDP ended in 2016. The Royal Decree-Law 13/2012 cancel any award procedures of new regasification plants in Spain. Currently, there isn´t any new NDP process or any NDP in force.
ETR-N-300 | HyOffWind Zeebrugge | Belgium | Fluxys, Eoly, Parkwind | Less-Advanced | No |  | No | N/A
LNG-N-304 | Italy-Sardinia Virtual Pipeline | Italy | Snam S.p.A. | Less-Advanced | No |  | No | N/A | (1) the NDP was prepared at an earlier date and the project will be proposed for inclusion in the next NDP
ETR-N-305 | PEGASUS | Italy | S.G.I. SpA | Less-Advanced | No |  | No | N/A
ETR-N-306 | Greening of Gas (GoG) | Czechia | NET4GAS, s.r.o. | Less-Advanced | No |  | No | N/A
UGS-F-311 | Bilciuresti daily withdrawal capacity increase | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | FID | No |  | No | N/A | (2) no NDP exists in the country
ETR-A-312 | P2G Velke Kapusany | Slovakia | NAFTA a.s. (joint stock company) | Advanced | No |  | No | N/A
ETR-N-315 | G2F - Gas to Future | Slovakia | NAFTA a.s. (joint stock company) | Less-Advanced | No |  | No | N/A
ETR-N-322 | North Sea Wind Power Hub | Netherlands | N.V. Nederlandse Gasunie | Less-Advanced | No |  | No | N/A
TRA-A-330 | EastMed Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | Yes | 7.3.1 | No | N/A | The EastMed project is considered an INGS so it is not included in the Greek NDP. It is referred in the NDP of Italy, as a project which concerns Italy.
TRA-A-339 | Trans-Caspian | Turkmenistan | W-Stream Caspian Pipeline Company OU | Advanced | Yes | 7.1.1 | No | N/A | (2) no NDP exists in the country
UGS-N-347 | Gas storage facility Grubisno Polje | Croatia | Podzemno skladiste plina Ltd | Less-Advanced | No |  | No | N/A | (1) the NDP was prepared at an earlier date and the project will be proposed for inclusion in the next NDP
ETR-N-370 | Hydrogen transmission backbone Netherlands | Netherlands | N.V. Nederlandse Gasunie | Less-Advanced | No |  | No | N/A
UGS-N-371 | Sarmasel undeground gas storage in Romania | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | Yes | 6.20.6 | No | N/A | (2) no NDP exists in the country
UGS-F-374 | Enhancement of Incukalns UGS | Latvia | JSC "Conexus Baltic Grid" | FID | Yes | 8.2.4 | No | N/A | (4) there is no obligation at national level for such a project to be part of the NDP
TRA-A-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | Latvia | JSC "Conexus Baltic Grid" | Advanced | Yes | 8.2.1 | No | N/A | (4) there is no obligation at national level for such a project to be part of the NDP
UGS-N-385 | South Kavala Underground Gas Storage facility | Greece | Hellenic Republic Asset Development Fund | Less-Advanced | Yes | 6.20.3 | No | N/A | (3) the operators are not required to prepare and publish a NDP
TRA-A-394 | Norwegian tie-in to Danish upstream system | Denmark | Energinet.dk | Advanced | No |  | No | N/A | (2) no NDP exists in the country
ETR-N-396 | Djewels | Netherlands | Nouryon | Less-Advanced | No |  | No | N/A
UGS-N-398 | Ghercesti underground gas storage in Romania | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | No |  | No | N/A | (2) no NDP exists in the country
UGS-N-399 | Falticeni UGS | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | Less-Advanced | No |  | No | N/A | (2) no NDP exists in the country
ETR-N-401 | Antwerp@C | Belgium | Fluxys and Antwerp Port Authority | Less-Advanced | No |  | No | N/A
ETR-N-406 | hybridge - gas grid infrastructure | Germany | Open Grid Europe GmbH | Less-Advanced | No |  | No | N/A
TRA-A-408 | Wilhelmshaven LNG-Terminal Anbindungsleitung | Germany | Open Grid Europe GmbH | Advanced | No |  | No | N/A | (1) the NDP was prepared at an earlier date and the project will be proposed for inclusion in the next NDP
ETR-N-427 | P2G integrated in Reganosa NG Transmission Grid | Spain | Reganosa | Less-Advanced | No |  | No | N/A
ETR-A-430 | Porthos | Netherlands | N.V. Nederlandse Gasunie | Advanced | No |  | No | N/A
ETR-N-432 | Athos | Netherlands | N.V. Nederlandse Gasunie | Less-Advanced | No |  | No | N/A
ETR-A-437 | Supercritical water gasification facilities | Netherlands | N.V. Nederlandse Gasunie | Advanced | No |  | No | N/A
ETR-N-449 | Hydrogen Region Lausitz | Germany | ONTRAS Gastransport GmbH | Less-Advanced | No |  | No | N/A
ETR-N-452 | Element Eins | Germany | Thyssengas GmbH, Gasunie Deutschland Transport Services GmbH, Tennet TSO Gm | Less-Advanced | No |  | No | N/A
ETR-N-483 | L2DG (LNG to Decarbonised Gas) | Spain | Reganosa | Less-Advanced | No |  | No | N/A
TRA-A-496 | Increase of Gas Transport to the Netherlands | Germany | Gasunie Deutschland Transport Service GmbH | Advanced | No |  | No | N/A | (1) the NDP was prepared at an earlier date and the project will be proposed for inclusion in the next NDP
ETR-N-501 | Hub País Vasco | Spain | Enagas S.A. | Less-Advanced | No |  | No | N/A
TRA-N-502 | Interconnector Romania - Ukraine | Ukraine | Joint-Stock Company | Less-Advanced | No |  | No | N/A | (4) there is no obligation at national level for such a project to be part of the NDP
ETR-A-504 | Sun2Hy | Spain | Enagas S.A. | Advanced | No |  | No | N/A
ETR-F-516 | CNG and L-CNG stations | Italy | Snam4mobility | FID | No |  | No | N/A
ETR-A-519 | Hub Baleares | Spain | Enagas S.A. | Advanced | No |  | No | N/A
ETR-N-521 | Hub Murcia | Spain | Enagas S.A. | Less-Advanced | No |  | No | N/A
ETR-F-523 | Biomethane plants development | Italy | Snam4mobility | FID | No |  | No | N/A
ETR-N-528 | Microliquefaction plants | Italy | Snam4mobility | Less-Advanced | No |  | No | N/A
ETR-N-537 | Hub Aragon | Spain | Enagas S.A. | Less-Advanced | No |  | No | N/A
ETR-F-541 | CORE LNGas hive and LNGHIVE2 Infrastructure and logistic solutions | Spain | Enagas Transporte S.A.U. | FID | No |  | No | N/A
ETR-F-546 | Jupiter 1000: first industrial demonstrator of Power to Gas in France | France | GRTgaz, Terega | FID | No |  | No | N/A
TRA-A-561 | Poland-Ukraine Interconnector (Ukrainian section) | Ukraine | PJSC UKRTRANSGAZ | Advanced | No |  | No | N/A | (2) no NDP exists in the country
ETR-N-562 | Energy Park Bad Lauchstädt | Germany | ONTRAS Gastransport GmbH | Less-Advanced | No |  | No | N/A
ETR-F-587 | West Grid Synergy | France | GRTgaz | FID | No |  | No | N/A
ETR-N-591 | Power to gas plant in the south of Italy | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | No | N/A
ETR-N-595 | Transport of hydrogen into natural gas network | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | No | N/A
TRA-N-598 | NTS developments in North-Vest Romania | Romania | SNTGN Transgaz SA | Less-Advanced | No |  | No | N/A | (1) the NDP was prepared at an earlier date and the project will be proposed for inclusion in the next NDP
ETR-F-599 | Sector coupling: hybrid compressor station | Italy | Snam Rete Gas S.p.A. | FID | No |  | No | N/A
ETR-N-616 | Renewable Methane according to NEP2020 | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | No |  | No | N/A
ETR-N-617 | Project to facilitate biomethane production plants inteconnection | Italy | Snam Rete Gas | Less-Advanced | No |  | No | N/A
ETR-N-622 | Renewable Hydrogen according to NEP2020 | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | No |  | No | N/A
ETR-N-624 | Biomethane: Reverse flow projects | France | GRTgaz | Less-Advanced | No |  | No | N/A
ETR-F-632 | Railway project roadmap. Transformation to LNG | Spain | Enagas Transporte S.A.U. | FID | No |  | No | N/A
ETR-N-633 | GETH2-ETR 1 | Germany | Nowega GmbH | Less-Advanced | No |  | No | N/A
TRA-A-655 | Eastring - Romania | Romania | SNTGN Transgaz SA | Advanced | Yes | 6.25.1 | No | N/A | (1) the NDP was prepared at an earlier date and the project will be proposed for inclusion in the next NDP
ETR-N-728 | Biomethane: connecting production units and reverse flow projects | France | TEREGA | Less-Advanced | No |  | No | N/A
ETR-F-743 | Impulse 2025 | France | Teréga | FID | No |  | No | N/A
TRA-F-780 | Baltic Pipe project – onshore section in Denmark | Denmark | Energinet | FID | Yes | 8.3.1 | No | N/A | (2) no NDP exists in the country
TRA-A-782 | TANAP X- Expansion of Trans Anatolian Natural Gas Pipeline Projec | Turkey | SOCAR (The State Oil Company of the Azerbaijan Republic) | Advanced | Yes | 7.1.1 | No | N/A | (4) there is no obligation at national level for such a project to be part of the NDP
TRA-A-808 | Additional transport of gas volumes to the Netherlands | Germany | Gasunie Deutschland Transport Services GmbH | Advanced | No |  | No | N/A | (1) the NDP was prepared at an earlier date and the project will be proposed for inclusion in the next NDP
TRA-N-810 | TAP Expansion | Greece | Trans Adriatic Pipeline AG | Less-Advanced | No |  | No | N/A | TAP Expansion is developed on a stand alone basis, however the Incremental capacity process is conducted in a coordinated manner with adjacent TSOs of TAP, in particular with Snam Rete Gas and DESFA, who are bound by the provisions of the EU CAM NC.
LNG-N-912 | Skulte LNG | Latvia | AS Skulte LNG Terminal | Less-Advanced | No |  | No | N/A | According to national legislation project can be included in NDP only after completion of EIA process. The project is currently in the middle of EIA.
TRA-F-928 | Balticconnector Finnish part | Finland | Baltic Connector Oy | FID | Yes | 8.1.1 | No | N/A | (2) no NDP exists in the country
TRA-F-937 | Nord Stream 2 | Germany | Nord Stream 2 AG | FID | No |  | No | N/A | (4) there is no obligation at national level for such a project to be part of the NDP
TRA-N-1063 | Export to Malta | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  | No | N/A | (1) the NDP was prepared at an earlier date and the project will be proposed for inclusion in the next NDP
TRA-N-1064 | Moffat Physical Reverse Flow | United Kingdom | National Grid Gas plc | Less-Advanced | Yes | 5.1.1 | No | N/A | (4) there is no obligation at national level for such a project to be part of the NDP
TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | Greece | DESFA S.A. | Less-Advanced | Yes | 6.9.1 | No | N/A | The project is not included in the National Development Plan because the Application by the promoter of the LNG terminal was submitted after the former's sumbission to the Regulator. It will be included in the NDP to be issued in July 2019.
TRA-N-1091 | Metering and Regulating station at Megalopoli | Greece | DESFA S.A. | Less-Advanced | Yes | 7.1.3 | No | N/A | The project is not included in the National development Plan because no application for capacity allocation has been made, by the promoter of the East Med (TRA-N-330) for the connection of this project to the Greek gas transmission system
TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | Greece | DESFA S.A. | Less-Advanced | Yes | 6.20.3 | No | N/A | The project is not included in the National Development Plan because no application for capacity allocation has been made, by the promoter of the UGS of S. Kavala (UGS-N-385) for the connection of this project to the Greek gas transmission system.
TRA-N-1138 | South Caucasus Pipeline Future Expansion (SCPFX) | Azerbaijan | SOCAR Midstream Operations LLC | Less-Advanced | Yes | 7.1.1 | No | N/A | (5) the country is not EU member
LNG-A-1146 | Cyprus Gas2EU | Cyprus | Ministry of Energy, Commerce and Industry (MECI) | Advanced | Yes | 7.5 | No | N/A | (2) no NDP exists in the country
TRA-N-1169 | Trans-Balkan Bi-directional Flow | Ukraine | JSC "UKRTRANSGAZ" | FID | No |  | No | N/A | (2) no NDP exists in the country
TRA-N-1181 | Connecting pipe to LNG terminal in Latvia | Latvia | JSC "Conexus Baltic Grid" | Less-Advanced | No |  | No | N/A | (4) there is no obligation at national level for such a project to be part of the NDP
LNG-A-1198 | LNG Terminal Brunsbuettel | Germany | GermanLNG Terminal GmbH | Advanced | No |  | No | N/A | (4) there is no obligation at national level for such a project to be part of the NDP
TRA-N-1202 | GCP GAZ-SYSTEM/ONTRAS - incremental capacity project | Poland | GAZ-SYSTEM S.A. | Less-Advanced | No |  | No | N/A | Project driven by CAM NC Incremental Procedure.

## CBCA & CEF
CBCA and CEF
Type | Code | Project Name | Host Country | Promoter | PCI 3rd List Code | Previous PCI List | CBCA Decision | CBCA Decision Date | CBCA decision website | Benefiting Countries | Bearer Countries | CBCA Additional Comments | Applied for CEF | Grant for studies | Amount received for studies (mil. EUR) | Grant for works | Amount received for works (mil. EUR) | Intention to apply for CEF | Financial support for other programs | CEF Additional Comments
Pipeline including CS | TRA-N-7 | Development for new import from the South (Adriatica Line) | Italy | Snam Rete Gas S.p.A. | 7.3.4 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
Pipeline including CS | TRA-N-8 | Import developments from North-East | Italy | Snam Rete Gas S.p.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-9 | Additional Southern developments | Italy | Snam Rete Gas S.p.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-A-10 | Poseidon Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | 7.3.3 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
Pipeline including CS | TRA-A-12 | GALSI Pipeline Project | Italy | Galsi S.p.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-14 | Komotini-Thesprotia pipeline | Greece | DESFA S.A. | [8 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 0.322 | No |  |  | No
Energy Transition Related Project | ETR-N-20 | GNI Renewable Gas Central Grid Injection Project | Ireland | Gas Networks Ireland | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-A-21 | Bidirectional Austrian-Czech Interconnector (BACI) | Austria | GAS CONNECT AUSTRIA GmbH | 6.4 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 0.065 | No |  |  | No
Energy Transition Related Project | ETR-N-22 | Ervia Cork CCUS | Ireland | Ervia (parent company of Gas Networks Ireland) | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-N-27 | Physical reverse flow from NI to GB and IE via SNIP pipeline | United Kingdom | Premier Transmission Limited | 5.1.2 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
LNG Terminal | LNG-A-30 | Shannon LNG Terminal and Connecting Pipeline | Ireland | Shannon LNG Ltd | 5.3 | PCI List 2015 | [5 empty] | Shannon LNG did receive a CBCA decision in connection with the early build of the Shannon Pipeline. The CBCA involved agreement by the CRU in Ireland, Utility Regulator in Northern Ireland and Ofgem in the UK. | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-A-31 | Melita TransGas Pipeline | Malta | Melita TransGas Co. Ltd. | 5.19 | PCI List 2015 |  |  | URL | Italy;#Malta | Malta | The CBCA decision jointly issued by the Maltese and Italian NRAs on the 4th June 2019, states that “Malta should bear 100% of the costs of the MTGP project and as such, no monetary transfer is needed between Italy and Malta”. | (1) Yes, we have applied for CEF and we have received a decision | Yes | 4.8 | Yes | 299.4 | No decision yet taken | Yes
LNG Terminal | LNG-A-32 | Project GO4LNG LNG terminal Gothenburg | Sweden | Swedegas AB | 8.6 | PCI List 2015 | Yes | 2015-10-01 | URL | Denmark;#Sweden | Sweden |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1.77 | No |  |  | Yes
LNG Terminal | LNG-A-50 | Gate terminal phase 3 | Netherlands | Gate | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Greece | Trans Adriatic Pipeline AG | 7.1.3 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 14 | No |  | No decision yet taken | No | Regarding CEF, TAP project requested EUR 14 018 347 in 2016, amount which was granted. In 2017, TAP requested EUR 3 314 317, amount which was not granted. EIB funding does not qualify as a 'funding programme'.
Pipeline including CS | TRA-N-53 | White Stream | Georgia | White Stream Ltd | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
LNG Terminal | LNG-A-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Greece | Gastrade S.A. | 6.9.1 | PCI List 2015 | [5 empty] | CBCA is non applicable for the Project | (1) Yes, we have applied for CEF and we have received a decision | Yes | 592418.86 | No |  | Yes, for studies only | No | The project is included in the Major Project List of the Operational Programme; eligible for grant financing from the National Strategic Reference Framework (NSRF). Notification for State Aid for the Project's financing to be submitted to DG Comp within July. Gastrade has already consulted with Jaspers the Cost Benefit Analysis (CBA) for the Project. The CBA will be submitted to DG Comp within the Notification documentation.
Pipeline including CS | TRA-A-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Greece | Gastrade S.A. | 6.9.1 | PCI List 2015 | [5 empty] | CBCA is non applicable for the Project | (1) Yes, we have applied for CEF and we have received a decision | Yes | 592418.86 | No |  | Yes, for studies only | No | The project is included in the Major Project List of the Operational Programme; eligible for grant financing from the National Strategic Reference Framework (NSRF). Notification for State Aid for the Project's financing to be submitted to DG Comp within July. Gastrade has already consulted with Jaspers the Cost Benefit Analysis (CBA) for the Project. The CBA will be submitted to DG Comp within the Notification documentation.
Energy Transition Related Project | ETR-A-64 | Biomethane reverse flow Denmark | Denmark | Energinet | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Croatia | Plinacro Ltd | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-A-68 | Ionian Adriatic Pipeline | Croatia | Plinacro Ltd | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | Yes
Pipeline including CS | TRA-A-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Croatia | Plinacro Ltd | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Croatia | Plinacro Ltd | 6.5.6 | PCI List 2015 |  |  | URL | Croatia;#Hungary;#Ukraine |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 2250000 | Yes |  |  | No
LNG Terminal | LNG-A-79 | Paldiski LNG Terminal | Estonia | Balti Gaas plc |  |  |  |  | URL | Estonia;#Finland |  | No net cost bearers were identified | (1) Yes, we have applied for CEF and we have received a decision | Yes | 137 | Yes | 137 |  | No | The CEF funding application was declined due to unclear situation with the temporary solution in Klaipeda and lack of clarity regarding the permanent solution.
Energy Transition Related Project | ETR-N-80 | Power to Gas Production with infrastructure building/enhacement in Latvia | Latvia | JSC "Conexus Baltic Grid" | [9 empty] | No |  | No |  |  | No
LNG Terminal | LNG-F-82 | LNG terminal Krk | Croatia | LNG Hrvatska d.o.o. | 6.5.1 | PCI List 2015 |  |  | URL | Croatia;#Hungary | Croatia |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 6197000 | Yes | 101400000 | No decision yet taken | Yes
Pipeline including CS | TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla) | Croatia | Plinacro Ltd | 6.26.1.1 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 4825000 | No |  | No decision yet taken | No
Pipeline including CS | TRA-F-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Croatia | Plinacro Ltd | 6.5.1 | PCI List 2015 |  |  | URL | Croatia;#Hungary;#Ukraine |  |  | (1) Yes, we have applied for CEF and we have received a decision | No |  | Yes | 16.433 |  | No
Pipeline including CS | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | Slovenia | Plinovodi d.o.o. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade | Slovenia | Plinovodi d.o.o. | 6.26.1.2 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Slovenia | Plinovodi d.o.o. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Slovenia | Plinovodi d.o.o. | 6.23 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 0.344 | No |  | No decision yet taken | No
Pipeline including CS | TRA-A-123 | Városföld CS | Hungary | FGSZ Ltd. | 6.24.4.3 | PCI List 2015 | Yes | 2015-10-06 |  | Hungary;#Romania |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 2.299 | No |  | No decision yet taken | No
Energy Transition Related Project | ETR-N-125 | Biomethane production with infrastructure building/enhancement in Latvia | Latvia | JSC "Conexus Baltic Grid" | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-N-128 | Compressor Station Kipi | Greece | DESFA S.A. | 6.8.1 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-A-133 | Bidirectional Austrian Czech Interconnection (BACI) | Czechia | NET4GAS, s.r.o. | 6.4 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 0.031 | No |  | No decision yet taken | Yes
Pipeline including CS | TRA-A-136 | Czech-Polish Gas Interconnector (CPI) | Czechia | NET4GAS, s.r.o. | 6.2.10; 6.2.12 | PCI List 2015 | Yes | 2014-10-17 | URL | Czechia;#Poland | Czechia;#Poland |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1.033 | No |  | No decision yet taken | Yes
Pipeline including CS | TRA-N-137 | Balkan Gas Hub - Interconnection Bulgaria - Serbia | Bulgaria | Bulgartransgaz EAD | 6.10 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
Storage Facility | UGS-A-138 | Balkan Gas Hub - UGS Chiren Expansion | Bulgaria | Bulgartransgaz EAD | 6.20.2 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 3900000 | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-F-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | Romania | SNTGN Transgaz SA | 6.24.10.1 | [7 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-A-161 | South Transit East Pyrenees (STEP) - ENAGAS | Spain | Enagas Transporte S.A.U. | 5.5.1 | [7 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1.7 | No |  |  | No | In January 2016, Enagás Transporte SAU received a CEF-E grant for MidCat project to carry out the engineering studies of Martorell compressor station and the engineering studies of the pipeline from Figueras to the French border. These infrastructures are now included within STEP project. In January 2018, Enagás Transporte SAU received a CEF-E grant for studiers for permit granting process of STEP. INEA webpage on CEF-E grants for MidCat https://ec.europa.eu/inea/en/connecting-europe-facility/cef-energy/projects-by-country/spain/5.5-0054-esfr-s-m-15 List of actions selected for receiving financial assistance under the 2017 CEF Energy Call for Proposals (January 2018) https://ec.europa.eu/energy/sites/ener/files/documents/list_of_actions_selected_for_receiving_financial_assistance_under_the_2017_cef_energy_call_for_proposals.pdf
LNG Terminal | LNG-F-163 | Gran Canaria LNG Terminal | Spain | Gascan | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Spain | Enagas Transporte S.A.U. | 5.4.1 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
LNG Terminal | LNG-F-178 | Musel LNG terminal | Spain | Enagas Transporte S.A.U. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
LNG Terminal | LNG-F-183 | Tenerife LNG Terminal | Spain | Gascan | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-F-190 | Poland - Slovakia interconnection | Slovakia | eustream,a.s. (a joint-stock company) | 6.2.1 | PCI List 2015 | Yes | 2014-11-28 | URL | Czechia;#Hungary;#Poland;#Slovakia;#Ukraine |  | CAPEX is modified because of a decision not to contruct new compressor units at Veľké Kapušany but to technologically modify the existing compressor station at Veľké Kapušany. This will have a positive impact on CAPEX. | (1) Yes, we have applied for CEF and we have received a decision | Yes | 2246805 | Yes | 55232400 | No, we do not plan to apply | Yes
Pipeline including CS | TRA-N-192 | Entry capacity expansion GATE terminal | Netherlands | Gasunie Transport Services B.V. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-F-208 | Reverse Flow TENP Germany | Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | 5.10 | PCI List 2015 | Yes | 2014-05-12 |  |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 0.44 | Yes | 8.665 |  | No
Pipeline including CS | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | Poland | GAZ-SYSTEM S.A. | 8.5 | PCI List 2015 | Yes | 2014-08-11 | URL | Estonia;#Latvia;#Lithuania | Poland |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 8 | Yes | 240.3 | No, we do not plan to apply | Yes
Pipeline including CS | TRA-N-224 | Gaspipeline Brod - Zenica | Bosnia Herzegovina | BH-Gas d.o.o. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No | Having in mind that BiH is not MS, but Energy Community Contracting Party, BH-Gas is not in possition to apply to CEF. Once if this criterium will be changed, we will use this opportunity.
LNG Terminal | LNG-N-225 | Montoir LNG Terminal Expansion | France | Elengy | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
Energy Transition Related Project | ETR-N-226 | Fos Tonkin LNG Terminal Evolution | France | Elengy | [9 empty] | No |  | No |  |  | No
LNG Terminal | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | France | Fosmax LNG | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
Storage Facility | UGS-A-233 | Depomures | Romania | Engie Romania SA | 6.20.4 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | Poland | GAZ-SYSTEM S.A. | 6.2.2 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | Yes
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | Poland | GAZ-SYSTEM S.A. | 6.2.11 | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes |  | No |  |  | Yes
Pipeline including CS | TRA-A-252 | South Transit East Pyrenees (STEP) - TEREGA | France | TEREGA | 5.5.1 |  |  |  | URL | Portugal;#Spain | France | Teréga is considering whether to submit a modified version of the STEP project to address the critics made the Agency. | (1) Yes, we have applied for CEF and we have received a decision | Yes | 4.15 | No |  |  | No | We will apply for a financial support from the Connecting Europe Facility for work in 2019.
Pipeline including CS | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | France | GRTgaz | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Storage Facility | UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | Italy | STOGIT | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | France | GRTgaz | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-A-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | Poland | GAZ-SYSTEM S.A. | 8.3.2 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes |  | No |  |  | Yes
LNG Terminal | LNG-F-272 | Upgrade of LNG terminal in Świnoujście | Poland | GAZ-SYSTEM S.A. | 8.7 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | No |  | No |  |  | No
Pipeline including CS | TRA-A-273 | Poland - Czech Republic Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | 6.2.10 | PCI List 2015 | Yes | 2014-06-24 | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 0.6 | No |  |  | No
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | 6.2.1 | PCI List 2015 | Yes | 2014-11-28 | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 2.267 | Yes | 52.508 |  | Yes
Pipeline including CS | TRA-A-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | Portugal | REN-Gasodutos, S.A. | 5.4.1 | PCI List 2015 | [5 empty] | The project of the 3rd Interconnection between Portugal and Spain was rescheduled due to the activities that are being developed in the High Level Group for the development of the interconnections between France, Spain and Portugal. It’s important to notice that the Portuguese project has its decision dependent on the STEP project’s decision. | (1) Yes, we have applied for CEF and we have received a decision | Yes | 505925 | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | Hungary | FGSZ Ltd. | 6.24.1.1 | PCI List 2015 | Yes | 2015-10-06 |  | Hungary;#Romania |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 2.299 | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-291 | NOWAL - Nord West Anbindungsleitung | Germany | GASCADE Gastransport GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Storage Facility | UGS-A-294 | Islandmagee Gas Storage Facility | United Kingdom | Islandmagee Storage Limited | 5.1.3 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision;#(2) Yes, we have applied for CEF, but we have not received a decision yet | Yes | 4649723 | No |  |  | No
LNG Terminal | LNG-A-295 | Mugardos LNG Terminal: Send-out Increase | Spain | Reganosa | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
LNG Terminal | LNG-A-296 | Mugardos LNG Terminal: 2nd Jetty | Spain | Reganosa | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
LNG Terminal | LNG-N-297 | Mugardos LNG Terminal: Storage Extension | Spain | Reganosa | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-F-298 | Balkan Gas Hub – Modernization and rehabilitation of the Bulgarian GTS | Bulgaria | Bulgartransgaz EAD | 6.8.2 | PCI List 2015 |  |  | URL | Bulgaria | Bulgaria |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1.032 | Yes | 27.184 | No decision yet taken | Yes
Pipeline including CS | TRA-N-299 | M3/1 Šempeter - Vodice | Slovenia | Plinovodi d.o.o. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Energy Transition Related Project | ETR-N-300 | HyOffWind Zeebrugge | Belgium | Fluxys, Eoly, Parkwind | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-A-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Croatia | Plinacro Ltd | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | Yes
Pipeline including CS | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Croatia | Plinacro Ltd | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
LNG Terminal | LNG-N-304 | Italy-Sardinia Virtual Pipeline | Italy | Snam S.p.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-305 | PEGASUS | Italy | S.G.I. SpA | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-306 | Greening of Gas (GoG) | Czechia | NET4GAS, s.r.o. | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-F-307 | H-gas exit OSZ GTG Nord | Netherlands | Gasunie Transport Services B.V. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Storage Facility | UGS-F-311 | Bilciuresti daily withdrawal capacity increase | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | Yes, for work only | No
Energy Transition Related Project | ETR-A-312 | P2G Velke Kapusany | Slovakia | NAFTA a.s. (joint stock company) | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-315 | G2F - Gas to Future | Slovakia | NAFTA a.s. (joint stock company) | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-A-320 | Carregado Compressor Station | Portugal | REN-Gasodutos, S.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Energy Transition Related Project | ETR-N-322 | North Sea Wind Power Hub | Netherlands | N.V. Nederlandse Gasunie | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-N-325 | Slovenian-Hungarian interconnector | Hungary | FGSZ Ltd. | 6.23 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | Yes |  | No decision yet taken | No
Pipeline including CS | TRA-F-329 | ZEELINK | Germany | Open Grid Europe GmbH and Thyssengas GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-A-330 | EastMed Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | 7.3.1 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 34500000 | No |  | No decision yet taken | No | IGI Poseidon is currently carrying out CEF Action 7.3.1-0023-CYEL-S-M-17, Implementation schedule: May 2018 to December 2021 The previous CEF Action for the EastMed, 7.3.1-0025-ELCY-S-M-15, Implementation schedule: May 2015 to March 2018, has been successfully carried out.
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | Croatia | Plinacro Ltd | 6.5.5 | PCI List 2015 |  |  |  |  | Croatia;#Hungary |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Croatia | Plinacro Ltd | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-A-339 | Trans-Caspian | Turkmenistan | W-Stream Caspian Pipeline Company OU | 7.1.1 | PCI List 2015 | [5 empty] | TCP 1st and 2n string are not located in any of the EU-MS nor do they impact any of the EU-MS respectively Contracting Parties to the Energy Community directly. | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1.87 | No |  |  | No
Pipeline including CS | TRA-F-340 | CS Wertingen | Germany | bayernets GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | Lithuania | AB Amber Grid | 8.5 | PCI List 2015 | Yes | 2014-08-11 | URL | Estonia;#Latvia;#Lithuania | Poland |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 2.5 | Yes | 57.9 |  | No
Pipeline including CS | TRA-A-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | Lithuania | AB Amber Grid | 8.2.1 | PCI List 2015 |  |  | URL | Estonia;#Finland;#Latvia;#Lithuania | Latvia;#Lithuania |  | (2) Yes, we have applied for CEF, but we have not received a decision yet | No |  | Yes | 7.3 |  | No
Storage Facility | UGS-N-347 | Gas storage facility Grubisno Polje | Croatia | Podzemno skladiste plina Ltd | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-354 | Interconnection with Slovenia | Italy | Snam Rete Gas S.p.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Storage Facility | UGS-A-356 | Underground Gas Storage Velke Kapusany | Slovakia | NAFTA a.s. (joint stock company) | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-F-357 | NTS developments in North-East Romania | Romania | SNTGN Transgaz SA | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase I | Romania | SNTGN Transgaz S.A. | 6.24.1.2 | PCI List 2015 | Yes | 2015-10-06 | URL | Hungary;#Romania | Hungary;#Romania |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1519342 | Yes | 179320000 |  | No
Pipeline including CS | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | Austria | GAS CONNECT AUSTRIA GmbH | 6.26.1.4 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-A-362 | Development on the Romanian territory of the Southern Transmission Corridor | Romania | SNTGN Transgaz SA | 6.24.4.5 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-370 | Hydrogen transmission backbone Netherlands | Netherlands | N.V. Nederlandse Gasunie | [9 empty] | No |  | No |  |  | No
Storage Facility | UGS-N-371 | Sarmasel undeground gas storage in Romania | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | 6.20.6 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 0.55 | No |  | Yes, for work only | No | We have applied for CEF grant for studies but it was not approved,
Storage Facility | UGS-F-374 | Enhancement of Incukalns UGS | Latvia | JSC "Conexus Baltic Grid" | 8.2.4 | PCI List 2015 | Yes | 2014-04-30 | URL | Estonia;#Latvia;#Lithuania | Latvia |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 150000 | Yes | 44 | No decision yet taken | No
Pipeline including CS | TRA-A-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | Hungary | FGSZ Ltd. | 6.24.4.6 | PCI List 2015 | Yes | 2015-10-06 |  | Hungary;#Romania |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 2.299 | No |  | No decision yet taken | No
Pipeline including CS | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | Bulgaria | ICGB a.d. | 6.8.1 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | Yes | The Bulgarian shareholder of the company is in the process of negotiation a EUR 110 mln loan financing with EIB , secured by a state guarantee in the same amount provided by Bulgaria. The loan agreement is expected to be concluded by the end of February 2019 and the loan will be trnasferred to the Project company upon the same condtions and parameters via an onlendign agreement. Further an Intergovernmental Agreement shall be signed between Greece and Bulgaria, which will establish the applicable Tax Framework for the Project. All the listed measures were subject to a notification for a state id clearance. The decision of the EC was issued on 8th of Nov. 2018 and all the measures are considered compatible with the state aid rules.
Pipeline including CS | TRA-A-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | Latvia | JSC "Conexus Baltic Grid" | 8.2.1 | PCI List 2015 |  |  | URL | Estonia;#Finland;#Latvia;#Lithuania | Lithuania |  | (1) Yes, we have applied for CEF and we have received a decision;#(2) Yes, we have applied for CEF, but we have not received a decision yet | No |  | Yes | 7.3 |  | No | We have received funds from CEF for studies and have submitted application for works
Storage Facility | UGS-N-385 | South Kavala Underground Gas Storage facility | Greece | Hellenic Republic Asset Development Fund | 6.20.3 | PCI List 2013 | [6 empty] | (2) Yes, we have applied for CEF, but we have not received a decision yet | Yes | 1.687 | No |  |  | No
Pipeline including CS | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Slovenia | Plinovodi d.o.o. | 6.26.1.5 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Slovenia | Plinovodi d.o.o. | 6.26.6 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-A-394 | Norwegian tie-in to Danish upstream system | Denmark | Energinet.dk |  |  |  |  | URL | Denmark;#Poland;#Sweden |  | The Danish NRA (DERA) approved the CBCA on the 27 February 2018. The Polish NRA (URE) approved the CBCA on the 12 March 2018. The Danish decision can be found here: http://energitilsynet.dk/gas/afgoerelser/tilsynsafgoerelser/2018/godkendelse-af-omkostningsfordelingen-mellem-polen-og-danmark-for-baltic-pipe-projektet/ The Polish decision can be found here: https://bip.ure.gov.pl/bip/taryfy-i-inne-decyzje/inne-decyzje-informacj/3634,Inne-decyzje-informacje-sprawozdania-opublikowane-w-2018-r.html?search=3253 | (3) No, we have not applied for CEF | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-396 | Djewels | Netherlands | Nouryon | [9 empty] | No |  | No |  |  | No
Storage Facility | UGS-N-398 | Ghercesti underground gas storage in Romania | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | Yes, for work only | No
Storage Facility | UGS-N-399 | Falticeni UGS | Romania | SNGN ROMGAZ SA - FILIALA DE INMAGAZINARE GAZE NATURALE DEPOGAZ PLOIESTI SRL | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | Yes, for work only | No
Energy Transition Related Project | ETR-N-401 | Antwerp@C | Belgium | Fluxys and Antwerp Port Authority | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-N-402 | TENP Security of Supply | Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Energy Transition Related Project | ETR-N-406 | hybridge - gas grid infrastructure | Germany | Open Grid Europe GmbH | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-A-408 | Wilhelmshaven LNG-Terminal Anbindungsleitung | Germany | Open Grid Europe GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-F-409 | Larino - Chieti | Italy | SGI S.p.A: | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-423 | GCA Mosonmagyaróvár | Austria | GAS CONNECT AUSTRIA GmbH | 6.24.1.3 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-424 | SAN MARCO - RECANATI | Italy | SGI S.p.A. | [7 empty] | The project is an internal connection of existing network | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Energy Transition Related Project | ETR-N-427 | P2G integrated in Reganosa NG Transmission Grid | Spain | Reganosa | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-A-429 | Adaptation L- gas - H-gas | France | GRTgaz and Storengy | 5.21 |  |  |  | URL | Belgium;#France | Belgium;#France |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 0 | Yes | 0 | No decision yet taken | No
Energy Transition Related Project | ETR-A-430 | Porthos | Netherlands | N.V. Nederlandse Gasunie | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-432 | Athos | Netherlands | N.V. Nederlandse Gasunie | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-A-437 | Supercritical water gasification facilities | Netherlands | N.V. Nederlandse Gasunie | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-N-439 | Stazione di Spinta "San Marco" | Italy | S.G.I. S.p.A. | [7 empty] | The project is an internal connection of existing network | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Energy Transition Related Project | ETR-N-449 | Hydrogen Region Lausitz | Germany | ONTRAS Gastransport GmbH | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-452 | Element Eins | Germany | Thyssengas GmbH, Gasunie Deutschland Transport Services GmbH, Tennet TSO Gm | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-483 | L2DG (LNG to Decarbonised Gas) | Spain | Reganosa | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-A-496 | Increase of Gas Transport to the Netherlands | Germany | Gasunie Deutschland Transport Service GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-F-500 | L/H Conversion Belgium | Belgium | Fluxys Belgium | 5.21 | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | No |  | Yes | 23000000 | No decision yet taken | No
Energy Transition Related Project | ETR-N-501 | Hub País Vasco | Spain | Enagas S.A. | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-N-502 | Interconnector Romania - Ukraine | Ukraine | Joint-Stock Company | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Energy Transition Related Project | ETR-A-504 | Sun2Hy | Spain | Enagas S.A. | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-F-516 | CNG and L-CNG stations | Italy | Snam4mobility | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-A-519 | Hub Baleares | Spain | Enagas S.A. | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-521 | Hub Murcia | Spain | Enagas S.A. | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-F-523 | Biomethane plants development | Italy | Snam4mobility | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Hungary | FGSZ Ltd. | 6.2.13 | [7 empty] | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
Energy Transition Related Project | ETR-N-528 | Microliquefaction plants | Italy | Snam4mobility | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-537 | Hub Aragon | Spain | Enagas S.A. | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-F-541 | CORE LNGas hive and LNGHIVE2 Infrastructure and logistic solutions | Spain | Enagas Transporte S.A.U. | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-F-546 | Jupiter 1000: first industrial demonstrator of Power to Gas in France | France | GRTgaz, Terega | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-A-561 | Poland-Ukraine Interconnector (Ukrainian section) | Ukraine | PJSC UKRTRANSGAZ | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Energy Transition Related Project | ETR-N-562 | Energy Park Bad Lauchstädt | Germany | ONTRAS Gastransport GmbH | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-F-587 | West Grid Synergy | France | GRTgaz | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-591 | Power to gas plant in the south of Italy | Italy | Snam Rete Gas S.p.A. | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-F-592 | Balkan Gas Hub-Necessary expansion of the Bulgarian gas transmission system | Bulgaria | Bulgartransgaz EAD | 6.25.4 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision;#(2) Yes, we have applied for CEF, but we have not received a decision yet | Yes | 0.92 | No |  | No decision yet taken | Yes | Grant Agreement dated 17 May 2017 for implementing Balkan Gas Hub Feasibility Study amounting to EUR 920 500. In June 2019 Bulgartransgaz EAD applied for financing within the CEF Energy call 2019 with a project proposal for design of two compressor stations – (CS Rasovo and CS Nova Provadia). Design and construction of each of the two compressor stations is a separate stage of Phase 1 of the project for the construction of Balkan Gas Hub (PCI 6.25.4). Ranking results are expected in September 2019.
Energy Transition Related Project | ETR-N-595 | Transport of hydrogen into natural gas network | Italy | Snam Rete Gas S.p.A. | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-N-596 | Interconnection between the RO and the UA gas transmission systems | Romania | SNTGN Transgaz SA | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-598 | NTS developments in North-Vest Romania | Romania | SNTGN Transgaz SA | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Energy Transition Related Project | ETR-F-599 | Sector coupling: hybrid compressor station | Italy | Snam Rete Gas S.p.A. | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-616 | Renewable Methane according to NEP2020 | Germany | Gasunie Deutschland Transport Services GmbH | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-617 | Project to facilitate biomethane production plants inteconnection | Italy | Snam Rete Gas | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-A-621 | Poland - Ukraine Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-622 | Renewable Hydrogen according to NEP2020 | Germany | Gasunie Deutschland Transport Services GmbH | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-624 | Biomethane: Reverse flow projects | France | GRTgaz | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-A-628 | Eastring - Slovakia | Slovakia | eustream, a.s. (a joint stock company) | 6.25.1 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1000000 | No |  | Yes, for studies and works | Yes
Energy Transition Related Project | ETR-F-632 | Railway project roadmap. Transformation to LNG | Spain | Enagas Transporte S.A.U. | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-N-633 | GETH2-ETR 1 | Germany | Nowega GmbH | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Hungary | FGSZ Ltd. | 6.2.13 | [7 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-A-654 | Eastring - Bulgaria | Bulgaria | Bulgartransgaz EAD | 6.25.1 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-A-655 | Eastring - Romania | Romania | SNTGN Transgaz SA | 6.25.1 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1 | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-A-656 | Eastring - Hungary | Hungary | FGSZ Ltd. | 6.25.1 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Energy Transition Related Project | ETR-N-728 | Biomethane: connecting production units and reverse flow projects | France | TEREGA | [9 empty] | No |  | No |  |  | No
Energy Transition Related Project | ETR-F-743 | Impulse 2025 | France | Teréga | [9 empty] | No |  | No |  |  | No
Pipeline including CS | TRA-F-752 | Capacity4Gas – DE/CZ | Czechia | NET4GAS, s.r.o. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-755 | CS Rimpar | Germany | GRTgaz Deutschland GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | Germany | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-780 | Baltic Pipe project – onshore section in Denmark | Denmark | Energinet | 8.3.1 | PCI List 2015 |  |  | URL | Denmark;#Poland;#Sweden |  | The Danish NRA (DERA) approved the CBCA on the 27 February 2018. The Polish NRA (URE) approved the CBCA on the 12 March 2018. The Danish decision can be found here: http://energitilsynet.dk/gas/afgoerelser/tilsynsafgoerelser/2018/godkendelse-af-omkostningsfordelingen-mellem-polen-og-danmark-for-baltic-pipe-projektet/ The Polish decision can be found here: https://bip.ure.gov.pl/bip/taryfy-i-inne-decyzje/inne-decyzje-informacj/3634,Inne-decyzje-informacje-sprawozdania-opublikowane-w-2018-r.html?search=3253 | (1) Yes, we have applied for CEF and we have received a decision | Yes |  | No |  |  | No
Pipeline including CS | TRA-A-782 | TANAP X- Expansion of Trans Anatolian Natural Gas Pipeline Projec | Turkey | SOCAR (The State Oil Company of the Azerbaijan Republic) | 7.1.1 | PCI List 2015 | [5 empty] | Our Project does not have CDCA desicion by NRA or ACER | (1) Yes, we have applied for CEF and we have received a decision | Yes | 15.371 | No |  | Yes, for studies only | No
Pipeline including CS | TRA-A-808 | Additional transport of gas volumes to the Netherlands | Germany | Gasunie Deutschland Transport Services GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-809 | Reallocation H-Gas towards NL: Bunde/Oude to Zone Oude Statenzijl H | Germany | Gasunie Deutschland Transport Services GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-810 | TAP Expansion | Greece | Trans Adriatic Pipeline AG | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-F-814 | Upgrade for IP Deutschneudorf et al. for More Capacity | Germany | ONTRAS Gastransport GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
LNG Terminal | LNG-F-824 | LNG Terminal in Klaipeda | Lithuania | AB Klaipėdos Nafta | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | Yes, for work only | No
Pipeline including CS | TRA-A-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | Ireland | Gas Networks Ireland | 5.1.1 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 925000 | No |  |  | No
Pipeline including CS | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | Bosnia Herzegovina | BH-GAS d.o.o. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | Yes
Pipeline including CS | TRA-N-873 | Additional import at Oude StatenZijl area | Netherlands | Gasunie Transport Services B.V. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-882 | Transferring L-gas infrastructure to H-gas | Netherlands | Gasunie Transport Services B.V. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-F-895 | Balticconnector | Estonia | Elering AS | 8.1.1 | PCI List 2015 | Yes | 2016-04-22 | URL | Finland;#Latvia | Estonia |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 0.77 | Yes | 98 |  | No
Pipeline including CS | TRA-F-902 | Capacity increase at IP Lanžhot entry | Slovakia | eustream,a.s. (a joint-stock company) | [7 empty] | Current technical capacity at the Czech side is 913,7 GWh/d. Incremental capacity on the Czech side based on Capacity increase at IP Lanžhot entry realization will be 333 GWh/d Current technical capacity at the Slovak side is 697 GWh/d. Incremental capacity on the Slovak side based on Capacity increase at IP Lanžhot entry realization will be 884 GWh/d It means that incremental capacity which should be taken into account for modelling is 549,7 GWh/d. | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-910 | West Interconnection BiH/CRO | Bosnia Herzegovina | BH-Gas d.o.o. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No | BH-Gas intends to apply to the available funds in order to provide necessery documentation such as FS, ESIA and Preliminary Design (WBIF)
LNG Terminal | LNG-N-912 | Skulte LNG | Latvia | AS Skulte LNG Terminal | [5 empty] | Estonia;#Finland;#Latvia;#Lithuania | Estonia;#Finland;#Latvia |  | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
Storage Facility | UGS-N-914 | UGS Damasławek | Poland | GAZ-SYSTEM S.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-F-915 | Enhancement of Estonia-Latvia interconnection | Estonia | Elering AS | 8.2.2 | PCI List 2015 | Yes | 2016-04-22 | URL | Finland;#Latvia | Estonia |  | (1) Yes, we have applied for CEF and we have received a decision | No |  | Yes | 18.6 |  | No
Pipeline including CS | TRA-F-918 | Capacity4Gas – CZ/SK | Czechia | NET4GAS, s.r.o. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-928 | Balticconnector Finnish part | Finland | Baltic Connector Oy | 8.1.1 | PCI List 2015 | Yes | 2016-04-22 | URL | Finland;#Latvia | Estonia |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 4.6 | Yes | 89.5 |  | No
Pipeline including CS | TRA-F-937 | Nord Stream 2 | Germany | Nord Stream 2 AG | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-941 | Metering and Regulating station at Nea Messimvria | Greece | DESFA S.A. | 7.1.3 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 0.486 | Yes | 7.09 | No decision yet taken | Yes
LNG Terminal | LNG-N-947 | FSRU Polish Baltic Sea Coast | Poland | GAZ-SYSTEM S.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-F-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Germany | Gastransport Nord GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-A-950 | Guitiriz - Lugo - Zamora pipeline | Spain | Reganosa | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-A-951 | Embedding CS Folmhusen in H-Gas | Germany | Gasunie Deutschland Transport Services GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-F-954 | TAG Reverse Flow | Austria | Trans Austria Gasleitung GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-955 | GUD: Complete conversion to H-gas | Germany | Gasunie Deutschland Transport Services GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | Romania | SNTGN Transgaz SA | 6.24.10.2 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
LNG Terminal | LNG-A-962 | Tallinn LNG | Estonia | Liwathon E.O.S. AS / Port of Tallinn AS | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No | We prepared a CBA for the project related to the CEF requirements in 2018.
Pipeline including CS | TRA-F-964 | New NTS developments for taking over gas from the Black Sea shore | Romania | SNTGN Transgaz SA | 6.24.10.3 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-A-967 | Nea-Messimvria to Evzoni/Gevgelija pipeline (IGNM) | Greece | DESFA S.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
Pipeline including CS | TRA-N-971 | Compressor station at Nea Messimvria | Greece | DESFA S.A. | 7.1.3 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-A-980 | Interconnection North Macedonia-Greece (North Macedonian part) | North Macedonia | MER JSC Skopje | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Croatia | Plinacro Ltd | 6.26.1.3 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 3900000 | No |  |  | No
Pipeline including CS | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Croatia | Plinacro Ltd | 6.5.6 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1220000 | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1063 | Export to Malta | Italy | Snam Rete Gas S.p.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1064 | Moffat Physical Reverse Flow | United Kingdom | National Grid Gas plc | 5.1.1 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | Greece | DESFA S.A. | 6.9.1 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1091 | Metering and Regulating station at Megalopoli | Greece | DESFA S.A. | 7.1.3 | [7 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | Greece | DESFA S.A. | 6.20.3 | PCI List 2013 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1129 | Compressor Station Kipi Increment | Greece | DESFA S.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1138 | South Caucasus Pipeline Future Expansion (SCPFX) | Azerbaijan | SOCAR Midstream Operations LLC | 7.1.1 | PCI List 2015 | [6 empty] | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
LNG Terminal | LNG-A-1146 | Cyprus Gas2EU | Cyprus | Ministry of Energy, Commerce and Industry (MECI) | 7.5 | PCI List 2015 |  |  | URL | Cyprus;#Greece | Cyprus |  | (1) Yes, we have applied for CEF and we have received a decision | No |  | Yes | 101255320 |  | Yes | www.Cynergy-project.eu
Pipeline including CS | TRA-N-1169 | Trans-Balkan Bi-directional Flow | Ukraine | JSC "UKRTRANSGAZ" | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-A-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | Poland | GAZ-SYSTEM S.A. | 8.3.2 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes |  | No |  |  | No
Pipeline including CS | TRA-N-1181 | Connecting pipe to LNG terminal in Latvia | Latvia | JSC "Conexus Baltic Grid" | [8 empty] | (3) No, we have not applied for CEF | No |  | Yes | 13 | Yes, for work only | No
Pipeline including CS | TRA-F-1193 | TAP interconnection | Italy | Snam Rete Gas S.p.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Italy | ENURA S.p.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1195 | Matagiola - Massafra pipeline | Italy | Snam Rete Gas S.p.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
LNG Terminal | LNG-A-1198 | LNG Terminal Brunsbuettel | Germany | GermanLNG Terminal GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No | We are discussion the application for funding under the „GRW, Koordinierungsrahmen der Gemeinschaftsaufgabe der regionalen Wirtschaftsstruktur“, a decision can be expected by the end of 2019.
Pipeline including CS | TRA-A-1199 | LNG Terminal Brunsbuettel - Grid Integration | Germany | Gasunie Deutschland Transport Service GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-1202 | GCP GAZ-SYSTEM/ONTRAS - incremental capacity project | Poland | GAZ-SYSTEM S.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-1227 | Gorizia plant upgrade | Italy | Snam Rete Gas S.p.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1235 | Firm transmission capacity increase at the IP Veľké Zlievce | Slovakia | eustream,a.s. | 6.2.13 | [7 empty] | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-F-1241 | Interconnection with production in Gela | Italy | Snam Rete Gas S.p.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-1246 | Greece - Italy interconnection | Italy | Snam Rete Gas S.p.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-F-1254 | CS Elten | Germany | Open Grid Europe GmbH and Thyssengas GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-1265 | Biomethane productions interconnection | Italy | Snam Rete Gas S.p.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-F-1267 | Upgrade Sülstorf station | Germany | NGT GmbH / GUD GmbH & Co. KG / Fluxys D GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-A-1268 | Romania-Serbia Interconnection | Romania | SNTGN Tranzgaz SA | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-F-1271 | Compressor Station Krummhoern | Germany | Open Grid Europe GmbH | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-1276 | Compressor station at Nea Messimvria (3rd unit) | Greece | DESFA S.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
Pipeline including CS | TRA-F-1277 | Upgrading GMS Isaccea 1 and GMS Negru Voda 1 | Romania | SNTGN Transgaz SA | [8 empty] | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1278 | Compressor station at Ambelia | Greece | DESFA S.A. | [8 empty] | (3) No, we have not applied for CEF | No |  | Yes | 32.7 | No decision yet taken | No
Pipeline including CS | TRA-A-1303 | IAEF - Vlora ccgt | Albania | Albgaz Sha |  |  |  |  | URL | Albania | Albania | We expect a positive decision any day by the National Regulatory Entity (ERE). | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-A-1322 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase II | Romania | SNTGN Transgaz SA | 6.24.4.4 | PCI List 2015 | [6 empty] | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1.52 | No |  |  | No

## Intergovernmental Agreements
Intergovernmental Agreements
Project Type | Code | Project Name | Promoter | Agreement | Signed | Signature Date | Description
Pipeline including CS | TRA-A-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagas Transporte S.A.U. | Lisbon Declaration | Yes | 2018-07-27 | European Commission, France, Portugal and Spain signed Lisbon Declaration on Friday 27th July at the Second Energy Interconnections summit.
Pipeline including CS | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagas Transporte S.A.U. | Lisbon Declaration | Yes | 2018-07-27 | European Commission, France, Portugal and Spain signed Lisbon Declaration on Friday 27th July at the Second Energy Interconnections summit.
Pipeline including CS | TRA-A-252 | South Transit East Pyrenees (STEP) - TEREGA | TEREGA | Lisbon Declaration | Yes | 2018-07-27 | European Commission, France, Portugal and Spain signed Lisbon Declaration on Friday 27th July at the Second Energy Interconnections summit.
Pipeline including CS | TRA-A-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. | Lisbon Declaration | Yes | 2018-07-27 | European Commission, France, Portugal and Spain signed Lisbon Declaration on Friday 27th July at the Second Energy Interconnections summit.
Pipeline including CS | TRA-N-137 | Balkan Gas Hub - Interconnection Bulgaria - Serbia | Bulgartransgaz EAD | Joint Commitment on the construction of gas interconnector Bulgaria-Serbia | Yes | 2018-05-17 | Bulgaria and Serbia declare their irrevocable commitment to build gas interconnection which shall be commissioned in May 2022 at the latest.
Pipeline including CS | TRA-A-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Letter of Itent | Yes | 2018-02-15 | Signed by Plinacro, Montenegro Bonus and Albgaz
Pipeline including CS | TRA-A-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Memorandum of Understanding on cooperation in relation to EastMed Pipeline | Yes | 2017-12-05 | MoU signed by Ministers of the Republic of Cyprus, the Hellenic Republic and the State of Israel and the Ambassador of the Italian Republic to Cyprus
Pipeline including CS | TRA-A-656 | Eastring - Hungary | FGSZ Ltd. | Memorandum of Understanding | Yes | 2017-10-30 | Memorandum of Understanding
Pipeline including CS | TRA-A-655 | Eastring - Romania | SNTGN Transgaz SA | 1. Memorandum of Understanding | Yes | 2017-10-30 | 1. MoU was signed by and between Slovak Economy Minister Peter Žiga and Hungarian Minister of Foreign Affairs Péter Szijjártó . The document was signed in the presence of Slovak Prime Minister Robert Fico in Košice. The Parties of the Memorandum articulat
Pipeline including CS | TRA-A-628 | Eastring - Slovakia | eustream, a.s. (a joint stock company) | Memorandum of Understanding | Yes | 2017-10-30 | Memorandum of Understanding
Pipeline including CS | TRA-A-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Plinacro Ltd | Memorandum of Understanding | Yes | 2017-04-27 | MoU between Plinacro and BH Gas
Pipeline including CS | TRA-N-137 | Balkan Gas Hub - Interconnection Bulgaria - Serbia | Bulgartransgaz EAD | Memorandum of Understanding between Bulgaria and Serbia | Yes | 2017-01-19 | Memorandum of Understanding between Bulgaria and Serbia
Pipeline including CS | TRA-A-136 | Czech-Polish Gas Interconnector (CPI) | NET4GAS, s.r.o. | Memorandum of understanding | Yes | 2016-12-12 | On project of expanded interconnection between gas transmission system of Republic of Poland and Czech Republic (STORK II)
Pipeline including CS | TRA-A-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Italiy-Greece-Cyprus-Israel Working Group | Yes | 2016-12-01
Pipeline including CS | TRA-A-136 | Czech-Polish Gas Interconnector (CPI) | NET4GAS, s.r.o. | Memorandum of understanding | Yes | 2016-09-06 | On the cooperation in the natural gas sector aimed at implementation of the Czech Republic- Poland Interconnection Project
Pipeline including CS | TRA-A-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Memorandum of Understanding and Cooperation | Yes | 2016-08-26 | signed by the Ministry of Energy and Industry of Republic of Albania, Ministry Foreign Trade and Economic Relations of Bosnia and Herzegovina, Ministry of Economy of the Republic of Croatia and Ministry of Economy of Montenegro
LNG Terminal | LNG-F-82 | LNG terminal Krk | LNG Hrvatska d.o.o. | The Three Seas initiative | Yes | 2016-08-25 | Connecting Central and Eastern European economies and infrastructure from North to South of Europe, in order to complete the single European market.
Pipeline including CS | TRA-A-656 | Eastring - Hungary | FGSZ Ltd. | Memorandum of Understanding | Yes | 2016-07-13 | Memorandum of Understanding
Pipeline including CS | TRA-A-655 | Eastring - Romania | SNTGN Transgaz SA | Memorandum of Understanding | Yes | 2016-07-13 | Peter Žiga, Minister of Economy of the Slovak Republic, and Žečo Stankov, State Secretary of the Ministry of Energy of the Bulgarian Republic, signed the Memorandum of Understanding on the Eastring project.
Pipeline including CS | TRA-A-628 | Eastring - Slovakia | eustream, a.s. (a joint stock company) | Memorandum of Understanding | Yes | 2016-07-13 | Memorandum of Understanding
Pipeline including CS | TRA-A-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Cyprus-Israel-Greece Trilateral Summit Declaration | Yes | 2016-01-28 | Agreement to "to strengthen the cooperation between our three countries in order to promote a trilateral partnership in different fields of common interest and to work together towards promoting peace, stability, security and prosperity in the Mediterran"
LNG Terminal | LNG-F-82 | LNG terminal Krk | LNG Hrvatska d.o.o. | CESEC MoU | Yes | 2015-07-10 | Memorandum of Understanding
Pipeline including CS | TRA-F-357 | NTS developments in North-East Romania | SNTGN Transgaz SA | Memorandum of Understanding | Yes | 2015-05-21 | Memorandum of understanding between the Ministry of Economy, Commerce and Business Environment in Romania and the Ministry of Economy from the Republic of Moldova related to preparing the conditions for the construction of the high pressure gas transmissi
Pipeline including CS | TRA-A-655 | Eastring - Romania | SNTGN Transgaz SA | Declaration | Yes | 2015-05-21 | The government officials of Slovakia, Hungary, Romania and Bulgaria confirmed their support for the implementation of interconnection and substantial bi-directional capacity of existing infrastructure for natural gas supply on the territory of the Republi
Pipeline including CS | TRA-A-628 | Eastring - Slovakia | eustream, a.s. (a joint stock company) | Declaration | Yes | 2015-05-21 | Governmental declaration
Pipeline including CS | TRA-A-136 | Czech-Polish Gas Interconnector (CPI) | NET4GAS, s.r.o. | Memorandum of understanding | Yes | 2015-04-20 | On the cooperation in the natural gas sector aimed at implementation of the Czech Republic- Poland Interconnection Project
Pipeline including CS | TRA-A-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagas Transporte S.A.U. | Madrid Declaration | Yes | 2015-03-04 | Commission, France, Portugal and Spain sign High Level Group agreement to break energy barriers
Pipeline including CS | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagas Transporte S.A.U. | Madrid Declaration | Yes | 2015-03-04 | Commission, France, Portugal and Spain sign High Level Group agreement to break energy barriers
Pipeline including CS | TRA-A-252 | South Transit East Pyrenees (STEP) - TEREGA | TEREGA | Madrid Declaration | Yes | 2015-03-04 | Energy Interconnections Links Summit
Pipeline including CS | TRA-A-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. | Madrid Declaration | Yes | 2015-03-04 | European Comission, Portugal, France and Spain
Pipeline including CS | TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla) | Plinacro Ltd | Memorandum of Understanding | Yes | 2014-12-28 | Signed among Plinacro, Plinovodi and Gas Connect Austria
LNG Terminal | LNG-A-79 | Paldiski LNG Terminal | Balti Gaas plc | Agreement between PMs of Estonia and Finland | Yes | 2014-11-17 | Agreement in regards to the gas infrastructure in the countries.
Pipeline including CS | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | Plinovodi d.o.o. | Agreement between PMs of Estonia and Finland | Yes | 2014-11-17 | Agreement in regards to the gas infrastructure in the countries.
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Agreement between the Government of the Republic of Poland and the Government of the Slovak Republic for cooperation on the implementation of the project of a gas pipeline connecting the Polish transmission system and Slovak transmission system. | Yes | 2014-06-11 | In Comments
Pipeline including CS | TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla) | Plinacro Ltd | Letter of Intent | Yes | 2014-05-22 | Signed between Plinacro and Plinovodi
LNG Terminal | LNG-A-79 | Paldiski LNG Terminal | Balti Gaas plc | Memorandum of Understanding | Yes | 2014-02-28 | MoU between Estonia and Finland and LNG project promoters
Pipeline including CS | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | Plinovodi d.o.o. | Memorandum of Understanding | Yes | 2014-02-28 | MoU between Estonia and Finland and LNG project promoters
Pipeline including CS | TRA-A-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Agreement to extend the Memorandum of Understanding | Yes | 2014-02-25 | Signed between Plinacro and TAP
Pipeline including CS | TRA-F-190 | Poland - Slovakia interconnection | eustream,a.s. (a joint-stock company) | Agreement between the Government of the Slovak Republic and the Government of the Republic of Poland for cooperation on the implementation of the project of a gas pipeline connecting the Slovak transmission system and Polish transmission system | Yes | 2013-11-22 | Intergovernmental agreement
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | Host-government agreement between TAP and Greece | Yes | 2013-06-26 | The HGA is designed to fill legal, regulatory and fiscal caviats to mitigate commercial risks and thereby provide the necessary investor protection to ensure that the project is built and enable construction and operation in accordance with high standards
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | Host-government agreement between TAP and Albania | Yes | 2013-04-05 | The HGA is designed to fill legal, regulatory and fiscal caviats to mitigate commercial risks and thereby provide the necessary investor protection to ensure that the project is built and enable construction and operation in accordance with high standards
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | Inter-governmental Agreements (only applicable for import pipeline projects | Yes | 2013-02-13 | An IGA between Italy, Greece and Albania has formalized the state parties’ support for the TAP project, ensure cross-country harmonization of standards in order to facilitate the implementation of TAP and provide the necessary investor protection measure
Pipeline including CS | TRA-N-137 | Balkan Gas Hub - Interconnection Bulgaria - Serbia | Bulgartransgaz EAD | Memorandum of Understanding between Bulgaria and Serbia | Yes | 2012-12-14 | Memorandum of Understanding signed in Brussels between Bulgaria and Serbia in 2012
Pipeline including CS | TRA-A-782 | TANAP X- Expansion of Trans Anatolian Natural Gas Pipeline Projec | SOCAR (The State Oil Company of the Azerbaijan Republic) | Intergovernmental Agreement between Turkey and Azerbaijan | Yes | 2012-06-26 | Intergovernmental Agreement (IGA) between the Government of the Republic of Turkey and the Government of the Republic of Azerbaijan Concerning the Trans Anatolian Natural Gas Pipeline System
Pipeline including CS | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd | Letter of Intent | Yes | 2011-04-06 | between Plinacro and BH Gas for all projects of interconnection
Pipeline including CS | TRA-A-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Plinacro Ltd | Letter of Intent | Yes | 2011-04-06 | between Plinacro and BH Gas for all projects of interconnection
Pipeline including CS | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd | Letter of Intent | Yes | 2011-04-06 | between Plinacro and BH Gas for all projects of interconnection
Pipeline including CS | TRA-A-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Memorandum of Understanding | Yes | 2011-02-05 | Signed between Plinacro and TAP
Pipeline including CS | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Memorandum of Understanding between Greece and Turkey | Yes | 2010-05-01
Pipeline including CS | TRA-N-137 | Balkan Gas Hub - Interconnection Bulgaria - Serbia | Bulgartransgaz EAD | Joint statement by Bulgaria and Serbia | Yes | 2010-03-05 | Joint statement signed in Brussels by Bulgaria and Serbia in 2010
Pipeline including CS | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. | Memorandum of Understanding (MOU) | Yes | 2009-11-27
Pipeline including CS | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Joint statement of the Italian Minister of Economic Development and the Turkish Minister of Energy and Natural Resources | Yes | 2009-11-01
Pipeline including CS | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Protocol of Cooperation between Italy and Azerbaijan | Yes | 2007-12-01
Pipeline including CS | TRA-A-12 | GALSI Pipeline Project | Galsi S.p.A. | Italy – Algeria Inter-Governmental Agreement for Galsi project | Yes | 2007-11-14 | Agreement between Italy and Algeria to promote and support the permitting, the construction and the commissioning of the Galsi Pipeline Project.
Pipeline including CS | TRA-A-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Ministerial declaration | Yes | 2007-09-27 | signed by the Ministries of enegry of Albania, Montenegro and Croatia, from dezember 2008, Bosnia and Herzegovina signed as well
Pipeline including CS | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Italy‐Greece‐Turkey Intergovernmental Agreement | Yes | 2007-07-01
Pipeline including CS | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd | Memorandum of understanding | Yes | 2006-06-26 | signed between Plinacro and BH Gas
Pipeline including CS | TRA-N-14 | Komotini-Thesprotia pipeline | DESFA S.A. | Intergovernmental Agreement between Greece and Italy for the implementation of the Interconnection Greece Italy. | Yes | 2005-11-04 | The Agreement was ratified by the Greek Parliament in 2006 (Law 3441/Government Gazette A’ 39/27.02.2006).
Pipeline including CS | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Italy‐Greece Intergovernmental Agreement | Yes | 2005-11-01
Pipeline including CS | TRA-N-137 | Balkan Gas Hub - Interconnection Bulgaria - Serbia | Bulgartransgaz EAD | Memorandum of Understanding between Bulgaria and Serbia | Yes | 2005-04-08 | Memorandum of Understanding signed in Sofia between Bulgaria and Serbia in 2005
Pipeline including CS | TRA-N-1138 | South Caucasus Pipeline Future Expansion (SCPFX) | SOCAR Midstream Operations LLC | Azerbaijan-Georgia Intergovernmental Agreement | Yes | 2001-09-29
Pipeline including CS | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. |  | No | 2019-01-16 | The Intergovernmental Agreement that shall be signed between Greece and Bulgaria will establish the applicable Tax Framework for the Project.
Pipeline including CS | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd | Memorandum of understanding | No | 2017-04-27 | MoU between Plinacro and Bh Gas
Pipeline including CS | TRA-A-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Memorandum of Understanding | No | 2016-07-13 | Memorandum of Understanding
Pipeline including CS | TRA-A-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Declaration | No | 2015-05-21 | Governmental declaration
Pipeline including CS | TRA-A-656 | Eastring - Hungary | FGSZ Ltd. | Declaration | No | 2015-05-21 | Goverment declaration
Pipeline including CS | TRA-N-325 | Slovenian-Hungarian interconnector | FGSZ Ltd. | Memorandum of Understanding (MOU) | No | 2009-11-26
Pipeline including CS | TRA-N-1138 | South Caucasus Pipeline Future Expansion (SCPFX) | SOCAR Midstream Operations LLC | Azerbaijan-Turkey Intergovernmental Agreement | No | 2001-03-12

## Third-Party Access Exemptions
Projects Having Applied for Third-Party Access Exemptions
Project Type | Code | Project Name | Promoter | Applied For Exemption | Exemption Granted | Exemption Stage Reached | Exempted % Entry | Exempted % Exit | Tariff Regime | TPA Regime Comments
Pipeline including CS | TRA-A-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Yes | Not Yet |  | 0% | 0% | Not Applicable | The promoter has obtained for the initial configuration of Poseidon Project (offshore section), a TPA exemption for 89% of the forward flow capacity from Greece to Italy.
LNG Terminal | LNG-A-30 | Shannon LNG Terminal and Connecting Pipeline | Shannon LNG Ltd | Yes | Yes |  | 0% | 0% | Negotiated
LNG Terminal | LNG-A-50 | Gate terminal phase 3 | Gate | Yes | Yes |  | 0% | 100% | Not Applicable | The exemption was applied for in March 2006; the exemption has been granted by the Dutch Minister on 14 July 2007; the EC gave its approval on 2 October 2007. Was not sure what to fill in regulated or negotiated. It is exempted
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | Yes | Yes | Exemption has been granted by the relevant regulatory authorities and the Commission. The start of the Exemption period coincides with the start of commercial operations of TAP | 100% | 100% | Negotiated | The initial capacity is exempted from TPA. Expansion capacity is subject to TPA and will be offered to the market via market tests, from no later than start of operations and subsequently every two years. In this regard, please note enclosed the exemption related materials.
LNG Terminal | LNG-A-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Gastrade S.A. | Yes | Not Yet | First phase of the Market Test completed. Please see section: “other comments” below for details. | 0% | 0% | Not Applicable | GASTRADE on 28.06.2018 submitted an Application for TPA Exemption to the NRA. According to par. 6 of Article 36 of the EU Directive 73/2009/EC, a Market Test has to be conducted in order to seek the interest of the market for the Project. On 29.06.2018 GASTRADE submitted to RAE the draft Guidelines for the first phase of the Market Test (Expression of Interest). The Guidelines were approved by RAE on 25.09.2018. Following this GASTRADE submitted to RAE for approval the draft EoI Notice which was approved on 18.10.2018. GASTRADE issued the Invitation for Expression of Interest for regasification capacity reservation in the Project on 30.10.2018. The procedure was completed on 31.12.2018 with a positive outcome. Twenty companies from SEE Europe and beyond expressed their interest for a total regasification capacity of up to 12.2 bcm/year. The second phase (request for Binding offers) will be launched once the relevant Guidelines and Notice are approved by RAE (3Q2019).
Pipeline including CS | TRA-A-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. | Yes | Not Yet | First phase of the Market Test completed. Please see section: “other comments” below for details. | 0% | 0% | Not Applicable | GASTRADE on 28.06.2018 submitted an Application for TPA Exemption to the NRA. According to par. 6 of Article 36 of the EU Directive 73/2009/EC, a Market Test has to be conducted in order to seek the interest of the market for the Project. On 29.06.2018 GASTRADE submitted to RAE the draft Guidelines for the first phase of the Market Test (Expression of Interest). The Guidelines were approved by RAE on 25.09.2018. Following this GASTRADE submitted to RAE for approval the draft EoI Notice which was approved on 18.10.2018. GASTRADE issued the Invitation for Expression of Interest for regasification capacity reservation in the Project on 30.10.2018. The procedure was completed on 31.12.2018 with a positive outcome. Twenty companies from SEE Europe and beyond expressed their interest for a total regasification capacity of up to 12.2 bcm/year. The second phase (request for Binding offers) will be launched once the relevant Guidelines and Notice are approved by RAE (3Q2019).
Pipeline including CS | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | Yes | Yes | Market Test completed with signed ARCAs; Exemption Decision issued by the regulators | 50% | 50% | Not Applicable | On 8th of August 2018 the National Regulators of Bulgaria and Greece issued a Joint Decision on the exemption of IGB from the requirements under article 36 of the European Gas Directive 2009/73/EC. The decision taken confirms the measures requested by the project company in the application filed, in particular: -Exemption from the rules for third-party access for the capacity booked under the Market test completed (almost 50% of the total capacity) -Exemption from regulated tariff for all the gas pipeline capacity for a period of 25 years. -Exemption from ownership unbundling for a period of 25 years.
Pipeline including CS | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | FGSZ Ltd. | Yes | No |  | 0% | 0% | Regulated
Pipeline including CS | TRA-F-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | Yes | Yes |  | 0% | 0% | Regulated
Pipeline including CS | TRA-N-1063 | Export to Malta | Snam Rete Gas S.p.A. | Yes | Yes |  | 0% | 0% | Regulated
LNG Terminal | LNG-A-1198 | LNG Terminal Brunsbuettel | GermanLNG Terminal GmbH | Yes | Not Yet |  | 100% | 0% | Negotiated

## PRJ Groups Main Info
PRJ Groups Main Information
PRJ Code | PRJ Name | PRJ Status | PRJ Commissioning Year First | PRJ Commissioning Year Last | PRJ Group Description | Code of individual projects | Project Name | Project Promoter | Project Host Country
PRJ-G-001 | Physical Reverse Flow at Moffat interconnection point (IE/UK) | Less-Advanced | 2020 | 2022 | Physical Reverse Flow at the Moffat interconnection point, which is currently uni-directional, supporting forward flow only from UK to IE, the Isle of Man and Northern Ireland (onshore). The planned capacity is 176.2 GWH/d. | TRA-A-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | Gas Networks Ireland | IE
[6 empty] | TRA-N-1064 | Moffat Physical Reverse Flow | National Grid Gas plc | UK
PRJ-G-002 | Bidirectional Austrian - Czech Interconnection (BACI) | Advanced | 2024 | 2024 | "The project of the Bidirectional Austrian - Czech Interconnection (BACI) is a planned pipeline to enable first direct connection of the Austrian and Czech gas transmission networks between the compressor stations Břeclav in the Czech Republic and Baumgarten in Austria, which would directly link the gas markets of both EU Member States for the first time. The project is intended to secure efficiently transmission capacity between the two countries and to enable further market integration fostering the liquidity of gas trading places and gas-to-gas competition on gas wholesale markets in the Czech Republic and Austria for more reasonable gas prices, which can also affect neighbouring gas markets positively. The projected length of the new pipeline (DN 800, PN 84) in the territory of the Czech Republic is 12 km. A final investment decision has not been taken yet. The partner to the project is the Austrian gas transmission system operator, Gas Connect Austria GmbH, on the Czech side it is | TRA-A-21 | Bidirectional Austrian-Czech Interconnector (BACI) | GAS CONNECT AUSTRIA GmbH | AT
[6 empty] | TRA-A-133 | Bidirectional Austrian Czech Interconnection (BACI) | NET4GAS, s.r.o. | CZ
PRJ-G-003 | Interconnection Slovenia-Croatia (Gas pipeline Lučko-Zabok-Rogatec) | Less-Advanced | 2021 | 2023 | New pipeline which will upgrade the existing interconnection Croatia/Slovenia. Along with the existing interconnection Karlovac-Lučko-Zabok-Rogatec, a new gas pipeline system has been planned which would significantly increase the capacity of the interconnection of the Croatian and the Slovenian gas transmission systems in this direction. Considering almost all existing and new supply directions in the surrounding region (especially LNG on the island of Krk) and the Croatian storage potentials this opens significant transit potentials in both directions. | TRA-A-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Jezerišće - Sotla) | Plinacro Ltd | HR
[6 empty] | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Plinovodi d.o.o. | SI
PRJ-G-004 | Krk LNG terminal with connecting and evacuation pipelines towards Hungary and beyond | Less-Advanced | 2020 | 2027 | Project which includes the construction of the LNG terminal on the island of Krk and the gas pipeline for the delivery of gas from the LNG terminal. LNG Project is a strategic project for the Republic of Croatia and it is of great importance for the EU. The construction of the LNG terminal on the island of Krk and the evacuation gas pipelines will provide a new supply gas route for the market of the Republic of Croatia as well as the markets of other countries of the central and southeastern Europe. It is integral part of the Baltic-Adriatic Gas Corridor. | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd | HR
[6 empty] | LNG-F-82 | LNG terminal Krk | LNG Hrvatska d.o.o. | HR
[6 empty] | TRA-F-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Plinacro Ltd | HR
[6 empty] | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Plinacro Ltd | HR
PRJ-G-008 | Poland – Slovakia Gas Interconnection | FID | 2021 | 2021 | The main goal of the PL-SK Interconnection is to create the first bi-directional cross-border pipeline between Poland and Slovakia. The projects in the group consist of Poland-Slovakia interconnector and relevant internal transmission investments in Poland and in Slovakia to ensure full functionality of the interconnection. The Project is a part of the NSI East Gas energy infrastructure priority corridor for enhancing regional diversification and security of gas supply. | TRA-F-190 | Poland - Slovakia interconnection | eustream,a.s. (a joint-stock company) | SK
[6 empty] | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | PL
PRJ-G-010 | Latvia - Lithuania interconnection | Advanced | 2023 | 2023 | The project aims at enhancing the capacity of the gas systems between Latvia and Lithuania. | TRA-A-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | AB Amber Grid | LT
[6 empty] | TRA-A-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | JSC "Conexus Baltic Grid" | LV
PRJ-G-011 | Interconnection Estonia – Finland | FID | 2019 | 2020 | New bidirectional offshore pipeline ﴾Inkoo‐Paldiski, DN500, 80 bar﴿ of 80 km, plus 55 km onshore pipeline in EE ﴾Kiili‐Paldiski pipeline, DN 700, 55 bar﴿ and 20 km onshore pipeline in FI ﴾Siuntio‐Inkoo pipeline, DN500, 80 bar﴿ including metering and compressor stations at both ends with a daily nominal capacity of 7.2 mcm/day. The power of each compressor station is about 10 MW. | TRA-F-895 | Balticconnector | Elering AS | EE
[6 empty] | TRA-F-928 | Balticconnector Finnish part | Baltic Connector Oy | FI
PRJ-G-013 | North Interconnection of BiH and Croatia | Less-Advanced | 2025 | 2025 | Interconnection gaspipeline Slobodnica - Brod - Zenica should be connected to the existing high-pressure gas pipeline in Croatia. Point of interconnection between Croatian and BiH natural gas transmission network is Brod (BiH)/Slavonski Brod (CRO). The gas pipeline is planned to be bi-directional, and together with Southern Interconnection BiH/CRO creates a part of EC Gas Ring. | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd | HR
[6 empty] | TRA-N-224 | Gaspipeline Brod - Zenica | BH-Gas d.o.o. | BA
PRJ-G-014 | South Interconnection of BiH and Croatia | Less-Advanced | 2023 | 2023 | Southern Interconnection pipeline BIH-CRO by the route Zagvozd-Posusje-Travnik with main branch to Mostar will provide BiH with new supply route receiving gas from Croatian gas transmission system and to get gas from new sources (LNG and, in case of IAP realization, from Caspian and Middle East). Project will be bidirectional and together with gaspipeline Zenica-Brod creates a part of EC Gas Ring. | TRA-A-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Plinacro Ltd | HR
[6 empty] | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | BH-GAS d.o.o. | BA
PRJ-G-015 | West Interconnection of BiH and Croatia | Less-Advanced | 2026 | 2026 | West Interconnection Pipeline Licka Jesenica (CRO) -Trzac (BiH)- Bosanska Krupa with branches to Bihac and Velika Kladusa will connect BiH with Croatian gas transmission system and will enable gasification the most developed part of Una-­Sana Canton. Main goal is to enable development of natural gas market in the west part of BiH. Project is contained in Comprehensive Energy Strategy BiH till 2035 which is in adoption process. | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd | HR
[6 empty] | TRA-N-910 | West Interconnection BiH/CRO | BH-Gas d.o.o. | BA
PRJ-G-017 | Gas Interconnection Poland-Lithuania (GIPL) | FID | 2021 | 2021 | "Gas Interconnection Poland-Lithuania (GIPL) is implemented by two project promoters - GAZ-SYSTEM S.A. and AB Amber Grid. The main aim of the project group is to establish a well-functioning, bi-directional interconnection between gas markets in Poland and Lithuania. This will integrate the Baltic and Finnish gas markets into the common EU market for gas, diversify the gas supply sources and increase the security of gas supply. Scope of investments in the project group: - Lithuania: PL-LT border - Jauniunai pipeline; - Poland: Hołowczyce - PL-LT border pipeline, compressor stations in Gustorzyn and Hołowczyce." | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. | PL
[6 empty] | TRA-F-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | AB Amber Grid | LT
PRJ-G-018 | Additional capacity at Oude Statenzijl from Germany to the Netherlands | Less-Advanced | 2020 | 2030 | Additional capacity at Oude Statenzijl from Germany to the Netherlands | TRA-F-307 | H-gas exit OSZ GTG Nord | Gasunie Transport Services B.V. | NL
[6 empty] | TRA-A-496 | Increase of Gas Transport to the Netherlands | Gasunie Deutschland Transport Service GmbH | DE
[6 empty] | TRA-A-808 | Additional transport of gas volumes to the Netherlands | Gasunie Deutschland Transport Services GmbH | DE
[6 empty] | TRA-N-809 | Reallocation H-Gas towards NL: Bunde/Oude to Zone Oude Statenzijl H | Gasunie Deutschland Transport Services GmbH | DE
[6 empty] | TRA-N-873 | Additional import at Oude StatenZijl area | Gasunie Transport Services B.V. | NL
[6 empty] | TRA-N-882 | Transferring L-gas infrastructure to H-gas | Gasunie Transport Services B.V. | NL
PRJ-G-021 | Baltic Pipe Project | Advanced | 2022 | 2022 | "The projects in the project group aim at connecting the gas transmission systems in Poland, Denmark and the upstream system in the North Sea with a view of transporting Norwegian gas to the countries in the Baltic Sea region and Central-Eastern Europe. The project will also bring the opportunity for the Danish and Swedish markets to diversify their supply potential (deliveries of LNG from the terminal in Świnoujście) in the context of declining production in the Danish part of the North Sea. The project is composed of the following main sections that are strongly mutually dependent and hence each is necessary for achieving the benefits and realisation of the Baltic Pipe project: - Baltic Pipe project – onshore section in Denmark (incl. gas compressor station) - Baltic Pipe project – offshore section - Baltic Pipe project – onshore section in Poland In addition, the projects in the project group are directly linked with the project “Norwegian tie-in to Danish upstream system” that wi | TRA-A-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | GAZ-SYSTEM S.A. | PL
[6 empty] | TRA-F-780 | Baltic Pipe project – onshore section in Denmark | Energinet | DK
[6 empty] | TRA-A-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | GAZ-SYSTEM S.A. | PL
PRJ-G-022 | Poland - Czech Republic Interconnection | Advanced | 2023 | 2023 | "The planned Poland - Czech Republic Interconnection project consists of: a) the construction of a pipeline (DN 1000, PN 73.5) that would interconnect the existing transmission systems of the Czech Republic and Poland, b) necessary enforcements of the gas transmission systems in both countries. The aim of the new bidirectional Czech-Polish pipeline project is to increase the transmission capacity, and to facilitate safe and reliable transmission of gas between the two countries. The construction of such transport corridor would not only strengthen the flexibility of natural gas transport in Central and Eastern Europe, but it will also contribute towards enhanced integration and security of gas supply in the region. The projected length of the pipeline in the territory of the Czech Republic is approximately 207 km and 246 km on the Polish side. Start of operation is planned for 2022. The partners to the project is GAZ-SYSTEM, S.A. on the Polish side and NET4GAS, s.r.o. on the Czech si | TRA-A-136 | Czech-Polish Gas Interconnector (CPI) | NET4GAS, s.r.o. | CZ
[6 empty] | TRA-A-273 | Poland - Czech Republic Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | PL
PRJ-G-023 | LNG Terminal Brunsbuettel | Advanced | 2023 | 2023 | Integration of the LNG Terminal Brunsbuettel (Area Hamburg) into the German Gas Infrastructure | LNG-A-1198 | LNG Terminal Brunsbuettel | GermanLNG Terminal GmbH | DE
[6 empty] | TRA-A-1199 | LNG Terminal Brunsbuettel - Grid Integration | Gasunie Deutschland Transport Service GmbH | DE
PRJ-G-028 | Poland - Ukraine Gas Interconnection | Advanced | 2022 | 2022 | The objective of the project is to create a large transportation corridor between Poland and Ukraine. Poland – Ukraine Gas Interconnection includes the construction of a new gas pipeline between the Hermanowice gas node on the Polish side and Bliche Volytsia UGS on the Ukrainian side. Scope of the Project on the Polish side: Hermanowice-PL/UA border pipeline; Metering station in Poland; Extenstion of CS Strachocina; Necessary additional transmission system development in Poland: Hermanowice-Strachocina pipeline; Strachocina-Pogórska Wola pipeline; Pogórska Wola-Tworzeń pipeline; Tworóg-Tworzeń pipeline. Scope of the project on the Ukrainian side: PL/UA border - Bilche Volytsya pipeline. | TRA-A-561 | Poland-Ukraine Interconnector (Ukrainian section) | PJSC UKRTRANSGAZ | UA
[6 empty] | TRA-A-621 | Poland - Ukraine Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | PL
PRJ-G-030 | Transferring L-gas infrastructure to H-gas | Less-Advanced | 2020 | 2030 | "Due to the of production of the Groningen field, L-gas export from the Netherlands to Germany is reduced. This projects enables the flow of H-gas via the existing L-gas border station, the first ones being Oude Statenzijl and Zevenaar. Other IPs may follow in the future. The first project is linked to initiatives of Gasunie Deutschland and GTG Nord." | TRA-F-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | DE
[6 empty] | TRA-A-951 | Embedding CS Folmhusen in H-Gas | Gasunie Deutschland Transport Services GmbH | DE
[6 empty] | TRA-N-955 | GUD: Complete conversion to H-gas | Gasunie Deutschland Transport Services GmbH | DE
PRJ-G-034 | More capacity – DE/CZ Capacity4Gas Project | FID | 2019 | 2023 | The objective of the More capacity – DE/CZ Capacity4Gas Project is to satisfy market demand that was expressed through binding long-term capacity bookings. The project consists of new infrastructure within Germany and the Czech Republic. It will reliably strengthen the supply of natural gas to Europe. The German EUGAL project will extend the German network by 480 km, running from the Baltic Sea through Mecklenburg-Western Pomerania and Brandenburg to southern Saxony and from there over the border to the Czech Republic. A part of the transported gas enters the existing German infrastructure along EUGAL through new connections in order to supply Germany and Western Europe. This also requires new infrastructure elements within the existing German network. In the Czech Republic most of the Capacity4Gas project (152 km) will be located in the Ústí and Pilsen Region. | TRA-F-752 | Capacity4Gas – DE/CZ | NET4GAS, s.r.o. | CZ
[6 empty] | TRA-F-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | DE
[6 empty] | TRA-F-814 | Upgrade for IP Deutschneudorf et al. for More Capacity | ONTRAS Gastransport GmbH | DE
PRJ-G-036 | Interconnection ES-PT (3rd interconnection) | Less-Advanced | 2025 | 2025 | "The 3rd Interconnection between Portugal and Spain is developed in 2 phases: -&nbsp;&nbsp; The 1st phase consists on a pipeline connecting both countries, between Celorico da Beira (PT) and Zamora (ES),&nbsp; with DN700 (28”) and a&nbsp; total length of 248 km, 162 in Portugal and 86 km Spain,&nbsp; and a compression reinforcement in the Zamora Compressor Station (ES). The first phase of the 3rd Interconnection Portugal – Spain will have a capacity from Spain to Portugal of 70.0 GWh/d and from Portugal to Spain of 70.0 GWh/d. The commissioning date for this infrastructure is the beginning of 2023. -&nbsp;&nbsp; The 2nd phase, in Portugal, will include, the installation of a compression station in Cantanhede, with a capacity of 12 MW and a construction of a second gas pipeline, with approximately 67 km of extension, parallel to the pipeline between the Cantanhede and Mangualde stations. In Spain, this 2nd phase comprises the construction of a Guitiriz-Zamora-Adradas gas pipeline with | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagas Transporte S.A.U. | ES
[6 empty] | TRA-A-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. | PT
PRJ-G-039 | STEP (South Transit East Pyrenees) | Advanced | 2024 | 2024 | "STEP project&nbsp; consist in the third&nbsp; interconnection between France and Spain on the eastern part of the Pyrenees:&nbsp; - On the French side, the project consists on a pipeline between Barbaira and the Spanish border (120 km, 36“/900 mm)&nbsp; and the adaptation of the compressor station located in Barbaira - On the Spanish side, the project consists on a pipeline between Hostalrich and Figueras (79 km, 36’’/900 mm), a pipeline between Figueras and the French border (28 km, 36’’/900 mm) and a compressor station in Martorell (36 MW). The project provides up to the following capacities: 230 GWh/d from Spain to France and 180 GWh/d from France to Spain. In the French side, these capacities are interruptible. In the Spanish side, the project provides the following firm capacities: 110 GWh/d from France to Spain and 120 GWh/d from Spain to France, being the rest interruptible. Project promoters are Enagás Transporte SAU (ES) and TIGF (FR)." | TRA-A-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagas Transporte S.A.U. | ES
[6 empty] | TRA-A-252 | South Transit East Pyrenees (STEP) - TEREGA | TEREGA | FR
PRJ-G-041 | Pipeline system from Bulgaria via Romania and Hungary to Slovakia [currently known as "Eastring“ | Advanced | 2025 | 2030 | Project Eastring is a new concept of a pan-EU bi-directional transmission pipeline. Technically it will connect existing gas transmission infrastructure in Slovakia with existing interconnection points (or new) at the external border of the EU on the territory of Bulgaria, e.g. Turkey or Black Sea coast. Key benefit of the Project is utilization of the existing infrastructure as much as possible and thus minimize the potential of stranded investment. Conceptually, it will serve as an interconnection between West EU liquid hubs and the Balkan region (an area with a potential to be a highly liquid region offering new gas sources from Caspian/eastern Mediterranean/Middle East region). The area where the Project is developed suffers from a highest dependency on a single gas source/import route which creates threats to the security of supply and limits competition in the region. | TRA-A-628 | Eastring - Slovakia | eustream, a.s. (a joint stock company) | SK
[6 empty] | TRA-A-654 | Eastring - Bulgaria | Bulgartransgaz EAD | BG
[6 empty] | TRA-A-655 | Eastring - Romania | SNTGN Transgaz SA | RO
[6 empty] | TRA-A-656 | Eastring - Hungary | FGSZ Ltd. | HU
PRJ-G-045 | Enhancement of the capacity at SK-HU interconnector | Less-Advanced | 2022 | 2022 | The purpose of the project is to expand the capacity of the border crossing point at Balassagyarmat/Veľké Zlievce in both transmission directions, and to offer the increased capacities as non-interruptible capacities, for the development of the N-S gas corridor due to expected changes of the gas flow directions in the future. | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | FGSZ Ltd. | HU
[6 empty] | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | FGSZ Ltd. | HU
[6 empty] | TRA-N-1235 | Firm transmission capacity increase at the IP Veľké Zlievce | eustream,a.s. | SK
PRJ-G-047 | RO-HU Transmission Corridor | Advanced | 2019 | 2022 | The transmission Corridor ensures bidirectional capacity between Romania and Hungary. | TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | FGSZ Ltd. | HU
[6 empty] | TRA-A-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | FGSZ Ltd. | HU
[6 empty] | TRA-A-1322 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase II | SNTGN Transgaz SA | RO
PRJ-G-049 | Fos Cavaou LNG Terminal Expansion | Less-Advanced | 2023 | 2026 | The project aims to expand the LNG terminal capacity from 8.25 bcm/y up to 16.5 bcm/y, with intermediate steps | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | Fosmax LNG | FR
[6 empty] | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | FR
PRJ-G-050 | Montoir LNG Terminal Expansion | Less-Advanced | 2023 | 2025 | The project aims to expand the Montoir de Bretagne LNG terminal capacity by 2.5 bcm/y, from 10 bcm/y to 12.5 bcm/y. | LNG-N-225 | Montoir LNG Terminal Expansion | Elengy | FR
[6 empty] | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | GRTgaz | FR
PRJ-G-054 | LNG | Less-Advanced | 2022 | 2024 | Gate expansion | LNG-A-50 | Gate terminal phase 3 | Gate | NL
[6 empty] | TRA-N-192 | Entry capacity expansion GATE terminal | Gasunie Transport Services B.V. | NL
PRJ-G-055 | LNG terminal in northern Greece / Alexandroupolis | Advanced | 2022 | 2022 | "The project consists of an LNG offshore Floating Storage Regasification Unit, a Mooring & a Pipeline system (24km Subsea and 4km Onshore), connecting the floating unit to the Greek National Natural Gas System at the area of Amfitriti, 5.5km NE of Alexandroupolis where, DESFA, the NNGS TSO, will build and operate a metering & regulating station. The floating unit, will be stationed in the sea of Thrace, 17.6km SW of Alexandroupolis in NE Greece, at an offshore distance of 5.4 n.m. from the nearest shore. It will have up to 170.000m3 LNG storage capacity and a gas send out capacity of up to 900.000 Nm3/h corresponding to 8.3 bcm/y. " | LNG-A-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Gastrade S.A. | GR
[6 empty] | TRA-A-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. | GR
PRJ-G-060 | Hungary – Slovenia interconnection | Less-Advanced | 2023 | 2025 | "Interconnector between the Hungarian and Slovenian transmission systems on the route Nagykanizsa - Tornyiszentmiklós (HU) - Lendava (SI) – Kidričevo, enabling access to underground storages in Hungary for Slovenian gas suppliers, to LNG terminals in northern Adriatic and other gas sources for Hungarian gas suppliers. [PCI 6.23. Hungary – Slovenia interconnection (Nagykanizsa - Tornyiszentmiklós (HU) - Lendava (SI) - Kidričevo)]" | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. | SI
[6 empty] | TRA-N-325 | Slovenian-Hungarian interconnector | FGSZ Ltd. | HU
PRJ-G-066 | Bidirectional gas route Austria-Slovenia | Less-Advanced | 2023 | 2023 | The project enables incremental capacity at the IP Murfeld/Ceršak in both directions (from AT to SI and from SI to AT). Moreover, physical RF capacity at the IP Murfeld/Ceršak is achieved. | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | GAS CONNECT AUSTRIA GmbH | AT
[6 empty] | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Plinovodi d.o.o. | SI
PRJ-G-105 | Hydrogen network northwest Europe | Less-Advanced | 2030 | 2032 | The hydrogen Network aims to connect renewable electricity through P2g with hydrogen customers in northwest Europe. | ETR-N-322 | North Sea Wind Power Hub | N.V. Nederlandse Gasunie | NL
[6 empty] | ETR-N-370 | Hydrogen transmission backbone Netherlands | N.V. Nederlandse Gasunie | NL
[6 empty] | ETR-N-396 | Djewels | Nouryon | NL
PRJ-G-107 | UGS Velke Kapusany | Advanced | 2023 | 2023 | The unique connection of storage and ETR project projected to reach a storage capacity of 340 mil.m3 with 3.75 mil.m3 of daily injection and withdrawal rate. The Underground Gas Storage Velke Kapusany project aims to construct an underground gas storage in a depleted gas field in the east of Slovakia in close vicinity of Ukraine (1 km), Hungary (15 km) and Poland (70 km). The storage is located directly at the Ukraine-Slovakia entry/exit point Velke Kapusany, and at the center of the soon-to-be NSI East Gas corridor. UGS would ensure the long-term sustainability of production and using the renewable energy - it will allow to store the energy from the RES in form of H2 in the mixture with the natural gas. | ETR-A-312 | P2G Velke Kapusany | NAFTA a.s. (joint stock company) | SK
[6 empty] | UGS-A-356 | Underground Gas Storage Velke Kapusany | NAFTA a.s. (joint stock company) | SK
PRJ-G-108 | LNG terminal in Latvia | Less-Advanced | 2021 | 2023 | Latvian situation is unique due to the natural gas storage facility in Inchukalns and proximity to the sea routes in Baltic Sea, Riga Bay. There are ways how to utilize geographically favorable opportunity and participate in LNG market with mid-size LNG terminal. Flexible/modular technological solution for the terminal was chosen as the best alternative for cost-effective, environmentally friendly and easy operations. | LNG-N-912 | Skulte LNG | AS Skulte LNG Terminal | LV
[6 empty] | TRA-N-1181 | Connecting pipe to LNG terminal in Latvia | JSC "Conexus Baltic Grid" | LV
PRJ-G-115 | CCS/U Netherlands | Less-Advanced | 2023 | 2026 | Carbon capture and storage projects in the Netherlands | ETR-A-430 | Porthos | N.V. Nederlandse Gasunie | NL
[6 empty] | ETR-N-432 | Athos | N.V. Nederlandse Gasunie | NL
PRJ-G-118 | Biomethane: reverse flow projets in France | Less-Advanced | 2019 | 2028 | Reverse flow projects to ensure biomethane injection into the grid | ETR-F-587 | West Grid Synergy | GRTgaz | FR
[6 empty] | ETR-N-624 | Biomethane: Reverse flow projects | GRTgaz | FR
PRJ-G-121 | Romania - Ukraine Gas Interconnection | Less-Advanced | 2025 | 2025 | "The project is one of the main element of North-South Gas Corridor, which is very important for European gas market and security of supply of Southern and Central European region. The main aim of the project is creation of physical capabilities for gas flow in both directions via future gas pipeline in the region of Khotyn in order to increase interconnectivity, market integration and SoS of Ukraine and Romania. From Romanian side the project entails the achievement of the gas transmission infrastructure in the direction Gheraesti - Siret in order to create a new interconnection with Ukraine. From Ukrainian side the project involves construction of new pipeline from area of CS Hotyn to Romanian – Ukraine border – length 30 km DN 700. The project allows to transport 58.1 GWh/d in Romania – Ukraine direction and 87.1 GWh/d in Ukraine – Romania direction." | TRA-N-502 | Interconnector Romania - Ukraine | Joint-Stock Company | UA
[6 empty] | TRA-N-596 | Interconnection between the RO and the UA gas transmission systems | SNTGN Transgaz SA | RO
PRJ-G-122 | Incremental capacity between Greece and Italy | Less-Advanced | 2024 | 2025 | On the basis of the capacity requests received in the non-binding demand indication phase, SNAM and DESFA have coordinated for the development of a preliminary technical study identifying different possible alternatives to make available transportation capacity between Greece and Italy to fulfil the non-binding demand indication. The PRJ represent one of the identified solutions to transport gas from Turkish border toward Italy | TRA-N-14 | Komotini-Thesprotia pipeline | DESFA S.A. | GR
[6 empty] | TRA-N-1129 | Compressor Station Kipi Increment | DESFA S.A. | GR
[6 empty] | TRA-N-1246 | Greece - Italy interconnection | Snam Rete Gas S.p.A. | IT
PRJ-G-127 | Italian biomethane production | Less-Advanced | 2022 | 2023 | The group consists in the realization of 5 biomethane production plant and in the developing all the facilities needed to guarantee better conditions to make possible new biomethane production plant to be connected to the gas network. | ETR-F-523 | Biomethane plants development | Snam4mobility | IT
[6 empty] | ETR-N-617 | Project to facilitate biomethane production plants inteconnection | Snam Rete Gas | IT