## Project Information
TYNDP Project Code | Project Name | Promoter | Hosting Country | Project Status | 4th PCI List Code | First Comm Year | Last Comm. Year | Compared to TYNP 2018
TRA-A-0123 | Városföld CS | FGSZ | HU | Advanced | 6.24.4.1 | - | - | Deleted
TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase I | SNTGN Transgaz SA | RO | FID | 6.24.1.1 | 2019 | 2020 | Completed
TRA-A-362 | Development on the Romanian territory of the Southern Transmission Corridor | SNTGN Transgaz SA | RO | Advanced | 6.24.4.3 | 2020 | 2022 | Delayed
TRA-A-0377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | FGSZ | HU | Advanced | 6.24.4.4 | 2022 | 2025 | Rescheduled
TRA-N-0524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | FGSZ | HU | Less-Advanced | 6.2.13 | 2022 | 2025 | Rescheduled
TRA-F-0286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | FGSZ | HU | FID | - | 2019 | 2019 | Completed
TRA-A-1322 | Development on the Romanian territory of the NTS (BG–RO-HU-AT)-Phase II | SNTGN Transgaz SA | RO | Advanced | 6.24.4.2 | 2022 | 2022 | Delayed
TRA-N-1235 | Firm transmission capacity increase at the IP Veľké Zlievce | Eustream,a.s. | SK | Less-Advanced | 6.2.13 | 2022 | 2022 | On time
TYNDP Project Code | Diameter [mm] | Length [km] | Compressor Power [MW]
TRA-A-0123 | - | - | 6
TRA-A-362 | 1200/1000 | 308 | -
TRA-A-0377 | - | - | 4
TRA-A-1322 | 800 | 50 | 14
TRA-F-0286 | - | - | 9
TRA-F-0358 | 800 | 479 | 28
TRA-N-0524 | 800 | 92 | -
TRA-N-0524 | 800 | 18 | -
TYNDP Project Code | Point Name | Operator | From System | Exit Capacity [GWh/d] | Increment Comm. Year | To System | Entry Capacity [GWh/d] | Increment Comm. Year
TRA-A-1322 | Csanadpalota | SNTGN Transgaz S.A. | Transmission Romania | 75.88 | 2022 | Transmission Hungary (MGP) | 78.12 | 2022
TRA-A-377 | Csanadpalota | FGSZ Ltd. | Transmission Hungary (MGP) | 76.5 | 2022 | Transmission Romania | 76.5 | 2025
TRA-F-286 | Csanadpalota | FGSZ Ltd. | Transmission Romania | 0 | - | Transmission Hungary (MGP) | 48.9 | 2019
TRA-F-358 | Ruse (BG) / Giurgiu (RO) | SNTGN Transgaz S.A. | Transmission Romania | 20.8 | 2019 | Transmission Bulgaria (NGTS) | 0 | -
TRA-F-358 | Csanadpalota | SNTGN Transgaz S.A. | Transmission Romania | 47.75 | 2020 | Transmission Hungary (MGP) | 0 | -
TRA-F-358 | Ruse (BG) / Giurgiu (RO) | SNTGN Transgaz S.A. | Transmission Romania | 20.75 | 2020 | Transmission Bulgaria (NGTS) | 0 | -
TRA-N-1235 | Balassagyarmat (HU) / Velké Zlievce (SK) | eustream, a.s. | Transmission Slovakia | 25.4 | 2022 | Transmission Hungary (SK-HU Interconnector) | 102.2 | 2022
TRA-N-524 | Balassagyarmat (HU) / Velké Zlievce (SK) | FGSZ | Transmission Hungary (SK-HU Interconnector) | 102 | 2022 | Transmission Slovakia | 26 | 2022
|  | TRA-A-123 | TRA-A-1322 | TRA-A-362 | TRA-A-377 | TRA-F-286(**) | TRA-N-358 | TRA-N-524 | TRA-N-1235 | Total Cost
| CAPEX | 20 | 68.8 | 360.4 | 14.4 | - | 478.6 | 58 | 26.18 | 1026.38
[min, EUR]
| OPEX | 3.1 | 7.85 | 0.83 | 3.7 | - | 11.77 | 0.11 | 1.95 | 29.31
[min, EUR/y]
| Range CAPEX (%) | 25 | 10 | 10 | 25 | 20 | 10 | 30 | 25 | -
| Range OPEX (%) | 15 | 15 | 15 | 15 | 10 | 15 | 30 | 25 | -

## Quantitative benefits-NT
EXISTING
Sum of Value | Column Labels
| 2020 |  |  | 2025 | [5 empty] | 2030 |  |  | 2040
| BE |  |  | CBG |  |  | GBC |  |  | NT |  |  | NT
Row Labels | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA
Competition
Commercial Supply Access (CSA)
Bulgaria | 1 | 2 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1
Germany | [12 empty] | 200% | 300% | 100%
North Noth Macedonia | [6 empty] | 2 | 3 | 1
Romania |  |  |  | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1
LNG and Interconnection Capacity Diversification (LICD)
Hungary |  |  |  | 4531.895 | 3165.9378 | -1365.9572 | 4531.895 | 3165.9378 | -1365.9572 | 4531.895 | 3165.9378 | -1365.9572 | 4531.895 | 3165.9378 | -1365.9572
Slovakia |  |  |  | 3905.4747 | 3334.2842 | -571.1905 | 3937.7022 | 3338.2241 | -599.4782 | 3897.7711 | 3333.7925 | -563.9786 | 3846.5794 | 3333.3333 | -513.2461
MASD-RU
Austria |  |  |  | 43.07% | 40.01% | -3.1% | 46% | 43.05% | -2.9% | 43.1% | 40% | -3.1%
Bosnia Herzegovina |  |  |  | 44% | 40.83% | -3.2% | 46% | 42.83% | -3.2% | 42.83% | 40% | -2.8%
Bulgaria | 48.32% | 28.5% | -19.8% | 24.2% | 10.72% | -13.5% | 26.08% | 14.5% | -11.6%
Croatia |  |  |  | 44% | 41.24% | -2.8% | 46% | 43.17% | -2.8% | 43.07% | 40% | -3.1%
Czech Republic |  |  |  | 43.28% | 40.15% | -3.1% |  |  |  | 43.21% | 40% | -3.2%
Denmark |  |  |  | 43.1% | 40% | -3.1% | 45.09% | 42% | -3.1% | 42% | 39.1% | -2.9%
Germany |  |  |  | 41.07% | 38.3% | -2.8% | 43.34% | 40.75% | -2.6% | 41.77% | 39.07% | -2.7%
Hungary |  |  |  | 44% | 41.2% | -2.8% | 46% | 43.21% | -2.8% | 43.26% | 40% | -3.3%
North Noth Macedonia | 49.02% | 29.02% | -20% | 24.95% | 10.74% | -14.2% | 26.92% | 13.51% | -13.4%
Poland | [6 empty] | 45.55% | 43.06% | -2.5% | 43.06% | 40% | -3.1%
Romania |  |  |  | 29.06% | 6% | -23.1% | 30.86% | 8.337% | -22.5% | 43.07% | 39.07% | -4% | 54.63% | 45.06% | -9.6%
Serbia |  |  |  | 44% | 41.07% | -2.9% | 46% | 43.07% | -2.9% | 43.06% | 40% | -3.1%
Slovakia |  |  |  | 43.95% | 41.23% | -2.7% | 46% | 43.21% | -2.8% | 43.18% | 40% | -3.2%
Slovenia | [6 empty] | 46% | 43.06% | -2.9% | 43.07% | 40% | -3.1%
Sweden |  |  |  | 43.08% | 40% | -3.1% | 45.08% | 42% | -3.1% | 42% | 39.08% | -2.9%
Security of Supply
Remaining Flexibility 2-Week Cold Spell (%)
Romania | 89.12% | 92.28% | 3.163% | 65.24% | 100% | 34.76% | 64.95% | 100% | 35.05% | 61.73% | 100% | 38.27% | 33.52% | 51.97% | 18.46%
Remaining Flexibility 2-Week Cold Spell (%) --- DF
Romania |  |  |  | 64.56% | 100% | 35.44% | 64.72% | 100% | 35.28% | 54.18% | 92.23% | 38.05% | 31.85% | 50.08% | 18.23%
Remaining Flexibility Peak day (%)
France | [6 empty] | 44.73% | 51.73% | 6.999% |  |  |  | 72.94% | 76.89% | 3.951%
Germany |  |  |  | 34.93% | 38.58% | 3.657% | 25.36% | 29.33% | 3.968% | 34.62% | 36.9% | 2.281% | 26.3% | 27.84% | 1.544%
Hungary |  |  |  | 72.26% | 90.67% | 18.41% | 63.91% | 81.49% | 17.59%
Netherlands |  |  |  | 60.08% | 66.37% | 6.29% | 43.54% | 50.36% | 6.813% |  |  |  | 67.52% | 71.58% | 4.058%
Romania | 55.24% | 57.8% | 2.561% | 42.51% | 88.96% | 46.45% | 42.18% | 88.52% | 46.34% | 32.31% | 64.53% | 32.23% | 14% | 29.59% | 15.58%
Slovenia | [12 empty] | 39.13% | 40.67% | 1.543%
Single Largest Infrastructure Disruption (SLID)-Romania
Romania | [9 empty] | 4.703% | 0% | -4.703% | 21.27% | 5.681% | -15.58%
Ukraine Disruption Curtailment Rate 2-Week Cold Spell (%)
Romania | [9 empty] | -5.528% | 0% | 5.528% | -27.77% | -9.313% | 18.46%
Ukraine Disruption Curtailment Rate 2-Week Cold Spell (%) --- DF
Romania | [9 empty] | -9.937% | 0% | 9.937% | -28.67% | -10.44% | 18.23%
Ukraine Disruption Curtailment Rate Peak Day (%)
Bosnia Herzegovina | -4% | -2% | 2%
Croatia | -4% | -2% | 2% |  |  |  | -4% | -1.132% | 2.868%
Hungary | [6 empty] | -2.773% | 0% | 2.773%
Romania | -3.285% | -2% | 1.285% | -11.02% | 0% | 11.02% | -11.23% | 0% | 11.23% | -22% | 0% | 22% | -37.75% | -22.16% | 15.58%
Serbia | -4% | -2% | 2%
Market Integration
Bi-directionality - Country
BGn <=> RO | 6.061% | 84.85% | 78.79% | 6.061% | 98.51% | 92.45% | 6.061% | 98.51% | 92.45% | 6.061% | 98.51% | 92.45% | 6.061% | 98.51% | 92.45%
HU <=> RO |  |  |  | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28%
HU <=> SK |  |  |  | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57%
Bi-directionality - Point
Balassagyarmat (HU) / Velké Zlievce (SK) |  |  |  | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99%
Csanadpalota |  |  |  | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2%
Ruse (BG) / Giurgiu (RO) | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75%
LOW
Sum of Value | Column Labels
| 2020 |  |  | 2025 | [5 empty] | 2030 |  |  | 2040
| BE |  |  | CBG |  |  | GBC |  |  | NT |  |  | NT
Row Labels | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA
Competition
Commercial Supply Access (CSA)
Bulgaria |  |  |  | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1
Greece |  |  |  | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1
North Noth Macedonia |  |  |  | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1
Romania |  |  |  | 3 | 4 | 1 | 2 | 4 | 2 | 3 | 4 | 1 | 2 | 3 | 1
LNG and Interconnection Capacity Diversification (LICD)
Bulgaria |  |  |  | 8589.8258 | 5724.2023 | -2865.6235 | 8589.8258 | 5724.2023 | -2865.6235 | 8589.8258 | 5724.2023 | -2865.6235 | 8589.8258 | 5724.2023 | -2865.6235
Hungary |  |  |  | 3745.7328 | 2774.4172 | -971.3157 | 3745.7328 | 2774.4172 | -971.3157 | 3745.7328 | 2774.4172 | -971.3157 | 3745.7328 | 2774.4172 | -971.3157
Slovakia |  |  |  | 2808.5886 | 2503.8379 | -304.7507 | 2826.4637 | 2508.9545 | -317.5092 | 2804.6926 | 2503.0133 | -301.6793 | 2782.5344 | 2500.0809 | -282.4535
MASD-RU
Austria |  |  |  | 31.07% | 28% | -3.1% | 34% | 31.65% | -2.3% | 31.1% | 28% | -3.1%
Bosnia Herzegovina |  |  |  | 24% | 17.31% | -6.7% | 28% | 20.14% | -7.9%
Bulgaria |  |  |  | 24% | 18.34% | -5.7% | 28% | 21.42% | -6.6%
Czech Republic |  |  |  | 31.28% | 28% | -3.3% | 34% | 31.26% | -2.7% | 31.21% | 28% | -3.2%
Germany |  |  |  | 30.4% | 28% | -2.4% | 33.42% | 31.05% | -2.4% | 30.37% | 27.62% | -2.7%
Hungary |  |  |  | 31.2% | 28.46% | -2.7% |  |  |  | 31.26% | 28.22% | -3%
North Noth Macedonia |  |  |  | 24% | 17.79% | -6.2% | 28% | 20.59% | -7.4%
Romania |  |  |  | 29.06% | 13.67% | -15.4% | 30.86% | 15.76% | -15.1% | 31.07% | 28% | -3.1% | 54.63% | 31.06% | -23.6%
Serbia |  |  |  | 24% | 18.3% | -5.7% | 28% | 21.37% | -6.6%
Slovenia | [9 empty] | 31.07% | 28% | -3.1%
Security of Supply
Remaining Flexibility 2-Week Cold Spell (%)
Romania |  |  |  | 65.24% | 100% | 34.76% | 64.95% | 100% | 35.05% | 69.59% | 100% | 30.41% | 41.36% | 59.82% | 18.46%
Remaining Flexibility 2-Week Cold Spell (%) --- DF
Romania |  |  |  | 64.56% | 100% | 35.44% | 64.72% | 100% | 35.28% | 61.68% | 99.46% | 37.78% | 39.6% | 57.82% | 18.23%
Remaining Flexibility Peak day (%)
France | [6 empty] | 45% | 51.98% | 6.978% |  |  |  | 72.58% | 78.82% | 6.244%
Germany |  |  |  | 35.12% | 39.08% | 3.958% | 25.51% | 29.47% | 3.956% | 36.26% | 38.33% | 2.069% | 25.69% | 28.18% | 2.497%
Hungary | [6 empty] | 90% | 100% | 10%
Netherlands | [6 empty] | 43.8% | 50.6% | 6.793% |  |  |  | 65.95% | 72.37% | 6.413%
Romania |  |  |  | 42.51% | 88.96% | 46.45% | 42.18% | 88.52% | 46.34% | 39.18% | 72.51% | 33.34% | 21.12% | 36.7% | 15.58%
Single Largest Infrastructure Disruption (SLID)-Romania
Romania | [12 empty] | 14.15% | 0% | -14.15%
Ukraine Disruption Curtailment Rate 2-Week Cold Spell (%)
Romania | [12 empty] | -19.93% | -1.749% | 18.18%
Ukraine Disruption Curtailment Rate 2-Week Cold Spell (%) --- DF
Romania | [9 empty] | -2.44% | 0% | 2.44% | -20.93% | -2.699% | 18.23%
Ukraine Disruption Curtailment Rate Peak Day (%)
Romania |  |  |  | -11.02% | 0% | 11.02% | -11.23% | 0% | 11.23% | -15.13% | 0% | 15.13% | -30.63% | -15.05% | 15.58%
Market Integration
Bi-directionality - Country
BGn <=> RO | 6.061% | 84.85% | 78.79% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12%
HU <=> RO |  |  |  | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28%
HU <=> SK |  |  |  | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57%
Bi-directionality - Point
Balassagyarmat (HU) / Velké Zlievce (SK) |  |  |  | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99%
Csanadpalota |  |  |  | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2%
Ruse (BG) / Giurgiu (RO) | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75%
ADVANCED
Sum of Value | Column Labels
| 2020 |  |  | 2025 | [5 empty] | 2030 |  |  | 2040
| BE |  |  | CBG |  |  | GBC |  |  | NT |  |  | NT
Row Labels | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA
Competition
LNG and Interconnection Capacity Diversification (LICD)
Bulgaria |  |  |  | 8589.8258 | 5724.2023 | -2865.6235 | 8589.8258 | 5724.2023 | -2865.6235 | 7084.7833 | 4625.9715 | -2458.8118 | 7037.1065 | 4580.7744 | -2456.3321
Hungary |  |  |  | 3745.7328 | 2774.4172 | -971.3157 | 3745.7328 | 2774.4172 | -971.3157 | 3061.1051 | 2372.0616 | -689.0435 | 2814.5702 | 2214.0307 | -600.5395
Romania | [9 empty] | 371561% | 339376% | -32184% | 371561% | 339376% | -32184%
Slovakia |  |  |  | 2808.5886 | 2503.8379 | -304.7507 | 2826.4637 | 2508.9545 | -317.5092 | 2804.6926 | 2503.0133 | -301.6793 | 2782.5344 | 2500.0809 | -282.4535
MASD-RU
Austria |  |  |  | 25.07% | 22% | -3.1%
Belgium | [6 empty] | 28% | 25.91% | -2.1%
Bosnia Herzegovina |  |  |  | 24.83% | 20.83% | -4% | 28% | 24.83% | -3.2%
Bulgaria |  |  |  | 24% | 21.08% | -2.9% | 28% | 25.08% | -2.9%
Croatia |  |  |  | 24.06% | 22% | -2.1% | 28% | 25.17% | -2.8%
Czech Republic |  |  |  | 25.28% | 22% | -3.3%
France |  |  |  | 24% | 21.48% | -2.5% | 28% | 25.2% | -2.8%
Greece |  |  |  | 24% | 20.83% | -3.2% | 28% | 24.83% | -3.2%
Hungary |  |  |  | 25.2% | 22% | -3.2% | 29.21% | 26% | -3.2%
North Noth Macedonia |  |  |  | 24% | 20.95% | -3.1% | 28% | 24.92% | -3.1%
Poland |  |  |  | 24.61% | 22% | -2.6%
Romania |  |  |  | 25.06% | 21.06% | -4% | 28% | 25.06% | -2.9%
Serbia |  |  |  | 24% | 21.07% | -2.9% | 28% | 25.07% | -2.9%
Slovakia |  |  |  | 25.23% | 22% | -3.2% | 28.5% | 26% | -2.5%
Slovenia |  |  |  | 25.07% | 22% | -3.1%
Security of Supply
Remaining Flexibility 2-Week Cold Spell (%)
Croatia |  |  |  | 81.2% | 83.59% | 2.382% | 73.86% | 75.69% | 1.824%
Romania |  |  |  | 78.04% | 100% | 21.96% | 77.73% | 100% | 22.27% |  |  |  | 78.18% | 96.58% | 18.4%
Remaining Flexibility 2-Week Cold Spell (%) --- DF
Croatia |  |  |  | 77.1% | 79.43% | 2.328% | 70.69% | 72.48% | 1.79%
Romania |  |  |  | 77.31% | 100% | 22.69% | 77.49% | 100% | 22.51% | 99.08% | 100% | 0.9161% | 75.96% | 94.13% | 18.17%
Remaining Flexibility Peak day (%)
Croatia |  |  |  | 67.99% | 70.32% | 2.332% | 62.42% | 64.11% | 1.685%
Germany |  |  |  | 44.23% | 48.34% | 4.112% | 35.12% | 39.21% | 4.098% | 46.66% | 48.17% | 1.515%
Hungary | [6 empty] | 96.32% | 100% | 3.679%
Romania |  |  |  | 53.54% | 99.99% | 46.45% | 53.19% | 99.53% | 46.34% | 72.18% | 100% | 27.82% | 52.09% | 67.58% | 15.49%
Market Integration
Bi-directionality - Country
BGn <=> RO | 6.061% | 84.85% | 78.79% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12%
HU <=> RO |  |  |  | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28%
HU <=> SK |  |  |  | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57%
Bi-directionality - Point
Balassagyarmat (HU) / Velké Zlievce (SK) |  |  |  | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99%
Csanadpalota |  |  |  | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2%
Ruse (BG) / Giurgiu (RO) | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75%

## Quantitative benefits-DE
EXISTING
Sum of Value | Column Labels
| 2020 |  |  | 2025 | [5 empty] | 2030 |  |  | 2040
| BE |  |  | CBG |  |  | GBC |  |  | DE |  |  | DE
Row Labels | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA
Competition
Commercial Supply Access (CSA)
Bosnia Herzegovina | [9 empty] | 2 | 3 | 1
Bulgaria | 1 | 2 | 1 | 2 | 3 | 1 | 2 | 3 | 1
Croatia | [9 empty] | 2 | 3 | 1
Hungary | [9 empty] | 2 | 3 | 1
North Noth Macedonia | [6 empty] | 2 | 3 | 1
Romania |  |  |  | 2 | 3 | 1 | 2 | 3 | 1 |  |  |  | 3 | 4 | 1
Serbia | [9 empty] | 2 | 3 | 1
LNG and Interconnection Capacity Diversification (LICD)
Hungary |  |  |  | 4531.895 | 3165.9378 | -1365.9572 | 4531.895 | 3165.9378 | -1365.9572 | 4531.895 | 3165.9378 | -1365.9572 | 4531.895 | 3165.9378 | -1365.9572
Slovakia |  |  |  | 3905.4747 | 3334.2842 | -571.1905 | 3937.7022 | 3338.2241 | -599.4782 | 3792.0936 | 3333.3333 | -458.7603 | 3761.7426 | 3333.3333 | -428.4093
MASD-RU
Austria |  |  |  | 43.07% | 40.01% | -3.1% | 46% | 43.05% | -2.9% | 42% | 39.08% | -2.9%
Bosnia Herzegovina |  |  |  | 44% | 40.83% | -3.2% | 46% | 42.83% | -3.2% | 42% | 38.83% | -3.2%
Bulgaria | 48.32% | 28.5% | -19.8% | 24.2% | 10.72% | -13.5% | 26.08% | 14.5% | -11.6%
Croatia |  |  |  | 44% | 41.24% | -2.8% | 46% | 43.17% | -2.8% | 42% | 39.09% | -2.9%
Czech Republic |  |  |  | 43.28% | 40.15% | -3.1% |  |  |  | 42% | 39.28% | -2.7%
Denmark |  |  |  | 43.1% | 40% | -3.1% | 45.09% | 42% | -3.1%
Germany |  |  |  | 41.07% | 38.3% | -2.8% | 43.34% | 40.75% | -2.6% | 41.13% | 38.35% | -2.8%
Hungary |  |  |  | 44% | 41.2% | -2.8% | 46% | 43.21% | -2.8% | 42% | 39.3% | -2.7%
North Noth Macedonia | 49.02% | 29.02% | -20% | 24.95% | 10.74% | -14.2% | 26.92% | 13.51% | -13.4%
Poland | [6 empty] | 45.55% | 43.06% | -2.5% | 42% | 39.69% | -2.3%
Romania |  |  |  | 29.06% | 6% | -23.1% | 30.86% | 8.337% | -22.5% | 17.43% | 11.76% | -5.7%
Serbia |  |  |  | 44% | 41.07% | -2.9% | 46% | 43.07% | -2.9% | 42% | 39.06% | -2.9%
Slovakia |  |  |  | 43.95% | 41.23% | -2.7% | 46% | 43.21% | -2.8% | 42% | 39.21% | -2.8%
Slovenia | [6 empty] | 46% | 43.06% | -2.9% | 42% | 39.02% | -3%
Sweden |  |  |  | 43.08% | 40% | -3.1% | 45.08% | 42% | -3.1%
Security of Supply
Remaining Flexibility 2-Week Cold Spell (%)
Romania | 89.12% | 92.28% | 3.163% | 65.24% | 100% | 34.76% | 64.95% | 100% | 35.05%
Remaining Flexibility 2-Week Cold Spell (%) --- DF
Romania |  |  |  | 64.56% | 100% | 35.44% | 64.72% | 100% | 35.28% |  |  |  | 72.35% | 94.2% | 21.85%
Remaining Flexibility Peak day (%)
France | [6 empty] | 44.73% | 51.73% | 6.999%
Germany |  |  |  | 34.93% | 38.58% | 3.657% | 25.36% | 29.33% | 3.968% | 56.71% | 59.11% | 2.397%
Hungary |  |  |  | 72.26% | 90.67% | 18.41% | 63.91% | 81.49% | 17.59%
Netherlands |  |  |  | 60.08% | 66.37% | 6.29% | 43.54% | 50.36% | 6.813% | 77.17% | 78.05% | 0.8792%
Romania | 55.24% | 57.8% | 2.561% | 42.51% | 88.96% | 46.45% | 42.18% | 88.52% | 46.34% | 85.32% | 100% | 14.68% | 67.96% | 88.33% | 20.37%
Ukraine Disruption Curtailment Rate 2-Week Cold Spell (%) --- DF
Romania | [12 empty] | -1.9% | 0% | 1.9%
Ukraine Disruption Curtailment Rate Peak Day (%)
Bosnia Herzegovina | -4% | -2% | 2%
Croatia | -4% | -2% | 2% |  |  |  | -4% | -1.132% | 2.868%
Hungary | [6 empty] | -2.773% | 0% | 2.773%
Romania | -3.285% | -2% | 1.285% | -11.02% | 0% | 11.02% | -11.23% | 0% | 11.23%
Serbia | -4% | -2% | 2%
Market Integration
Bi-directionality - Country
BGn <=> RO | 6.061% | 84.85% | 78.79% | 6.061% | 98.51% | 92.45% | 6.061% | 98.51% | 92.45% | 6.061% | 98.51% | 92.45% | 6.061% | 98.51% | 92.45%
HU <=> RO |  |  |  | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28%
HU <=> SK |  |  |  | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57%
Bi-directionality - Point
Balassagyarmat (HU) / Velké Zlievce (SK) |  |  |  | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99%
Csanadpalota |  |  |  | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2%
Ruse (BG) / Giurgiu (RO) | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75%
LOW
Sum of Value | Column Labels
| 2020 |  |  | 2025 | [5 empty] | 2030 |  |  | 2040
| BE |  |  | CBG |  |  | GBC |  |  | DE |  |  | DE
Row Labels | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA
Competition
Commercial Supply Access (CSA)
Bosnia Herzegovina | [9 empty] | 3 | 4 | 1
Bulgaria |  |  |  | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 4 | 2
Croatia | [9 empty] | 3 | 4 | 1
Greece |  |  |  | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 4 | 2
Hungary | [9 empty] | 3 | 4 | 1
North Noth Macedonia |  |  |  | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 4 | 2
Romania |  |  |  | 3 | 4 | 1 | 2 | 4 | 2
Serbia | [9 empty] | 3 | 4 | 1
LNG and Interconnection Capacity Diversification (LICD)
Bulgaria |  |  |  | 8589.8258 | 5724.2023 | -2865.6235 | 8589.8258 | 5724.2023 | -2865.6235 | 8589.8258 | 5724.2023 | -2865.6235 | 8589.8258 | 5724.2023 | -2865.6235
Hungary |  |  |  | 3745.7328 | 2774.4172 | -971.3157 | 3745.7328 | 2774.4172 | -971.3157 | 3745.7328 | 2774.4172 | -971.3157 | 3745.7328 | 2774.4172 | -971.3157
Slovakia |  |  |  | 2808.5886 | 2503.8379 | -304.7507 | 2826.4637 | 2508.9545 | -317.5092 | 2755.6748 | 2500 | -255.6748 | 2739.7515 | 2500 | -239.7515
MASD-RU
Austria |  |  |  | 31.07% | 28% | -3.1% | 34% | 31.65% | -2.3%
Bosnia Herzegovina |  |  |  | 24% | 17.31% | -6.7% | 28% | 20.14% | -7.9%
Bulgaria |  |  |  | 24% | 18.34% | -5.7% | 28% | 21.42% | -6.6%
Czech Republic |  |  |  | 31.28% | 28% | -3.3% | 34% | 31.26% | -2.7%
Estonia | [9 empty] | 30% | 27.06% | -2.9%
Finland | [9 empty] | 30% | 27.02% | -3%
Germany |  |  |  | 30.4% | 28% | -2.4% | 33.42% | 31.05% | -2.4%
Hungary |  |  |  | 31.2% | 28.46% | -2.7% |  |  |  | 29.3% | 26.19% | -3.1%
Latvia | [9 empty] | 29.65% | 27.04% | -2.6%
Netherlands | [9 empty] | 29.07% | 26% | -3.1%
North Noth Macedonia |  |  |  | 24% | 17.79% | -6.2% | 28% | 20.59% | -7.4%
Poland | [9 empty] | 29.49% | 27% | -2.5%
Romania |  |  |  | 29.06% | 13.67% | -15.4% | 30.86% | 15.76% | -15.1% | 17.43% | 15.05% | -2.4%
Serbia |  |  |  | 24% | 18.3% | -5.7% | 28% | 21.37% | -6.6%
Security of Supply
Remaining Flexibility 2-Week Cold Spell (%)
Romania |  |  |  | 65.24% | 100% | 34.76% | 64.95% | 100% | 35.05%
Remaining Flexibility 2-Week Cold Spell (%) --- DF
Romania |  |  |  | 64.56% | 100% | 35.44% | 64.72% | 100% | 35.28% |  |  |  | 81.28% | 100% | 18.72%
Remaining Flexibility Peak day (%)
France | [6 empty] | 45% | 51.98% | 6.978%
Germany |  |  |  | 35.12% | 39.08% | 3.958% | 25.51% | 29.47% | 3.956% | 51.75% | 54.13% | 2.381%
Hungary | [6 empty] | 90% | 100% | 10%
Netherlands | [6 empty] | 43.8% | 50.6% | 6.793%
Romania |  |  |  | 42.51% | 88.96% | 46.45% | 42.18% | 88.52% | 46.34% | 95.16% | 100% | 4.837% | 76.93% | 97.3% | 20.37%
Ukraine Disruption Curtailment Rate Peak Day (%)
Romania |  |  |  | -11.02% | 0% | 11.02% | -11.23% | 0% | 11.23%
Market Integration
Bi-directionality - Country
BGn <=> RO | 6.061% | 84.85% | 78.79% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12%
HU <=> RO |  |  |  | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28%
HU <=> SK |  |  |  | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57%
Bi-directionality - Point
Balassagyarmat (HU) / Velké Zlievce (SK) |  |  |  | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99%
Csanadpalota |  |  |  | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2%
Ruse (BG) / Giurgiu (RO) | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75%
ADVANCED
Sum of Value | Column Labels
| 2020 |  |  | 2025 | [5 empty] | 2030 |  |  | 2040
| BE |  |  | CBG |  |  | GBC |  |  | DE |  |  | DE
Row Labels | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA
Competition
Commercial Supply Access (CSA)
North Noth Macedonia | [9 empty] | 3 | 4 | 1
LNG and Interconnection Capacity Diversification (LICD)
Bulgaria |  |  |  | 8589.8258 | 5724.2023 | -2865.6235 | 8589.8258 | 5724.2023 | -2865.6235 | 6791.2423 | 4364.7578 | -2426.4845 | 6928.3571 | 4481.7299 | -2446.6271
Hungary |  |  |  | 3745.7328 | 2774.4172 | -971.3157 | 3745.7328 | 2774.4172 | -971.3157 | 2878.873 | 2252.6352 | -626.2378 | 2802.832 | 2207.3246 | -595.5075
Romania | [9 empty] | 371561% | 339376% | -32184% | 371561% | 339376% | -32184%
Slovakia |  |  |  | 2808.5886 | 2503.8379 | -304.7507 | 2826.4637 | 2508.9545 | -317.5092 | 2755.6748 | 2500 | -255.6748 | 2739.7515 | 2500 | -239.7515
MASD-RU
Austria |  |  |  | 25.07% | 22% | -3.1%
Belgium | [6 empty] | 28% | 25.91% | -2.1%
Bosnia Herzegovina |  |  |  | 24.83% | 20.83% | -4% | 28% | 24.83% | -3.2%
Bulgaria |  |  |  | 24% | 21.08% | -2.9% | 28% | 25.08% | -2.9%
Croatia |  |  |  | 24.06% | 22% | -2.1% | 28% | 25.17% | -2.8%
Czech Republic |  |  |  | 25.28% | 22% | -3.3%
France |  |  |  | 24% | 21.48% | -2.5% | 28% | 25.2% | -2.8%
Greece |  |  |  | 24% | 20.83% | -3.2% | 28% | 24.83% | -3.2%
Hungary |  |  |  | 25.2% | 22% | -3.2% | 29.21% | 26% | -3.2%
North Noth Macedonia |  |  |  | 24% | 20.95% | -3.1% | 28% | 24.92% | -3.1%
Poland |  |  |  | 24.61% | 22% | -2.6%
Romania |  |  |  | 25.06% | 21.06% | -4% | 28% | 25.06% | -2.9%
Serbia |  |  |  | 24% | 21.07% | -2.9% | 28% | 25.07% | -2.9%
Slovakia |  |  |  | 25.23% | 22% | -3.2% | 28.5% | 26% | -2.5%
Slovenia |  |  |  | 25.07% | 22% | -3.1%
Security of Supply
Remaining Flexibility 2-Week Cold Spell (%)
Croatia |  |  |  | 81.2% | 83.59% | 2.382% | 73.86% | 75.69% | 1.824%
Romania |  |  |  | 78.04% | 100% | 21.96% | 77.73% | 100% | 22.27%
Remaining Flexibility 2-Week Cold Spell (%) --- DF
Croatia |  |  |  | 77.1% | 79.43% | 2.328% | 70.69% | 72.48% | 1.79%
Romania |  |  |  | 77.31% | 100% | 22.69% | 77.49% | 100% | 22.51%
Remaining Flexibility Peak day (%)
Croatia |  |  |  | 67.99% | 70.32% | 2.332% | 62.42% | 64.11% | 1.685%
Germany |  |  |  | 44.23% | 48.34% | 4.112% | 35.12% | 39.21% | 4.098% | 62.81% | 65% | 2.191%
Hungary | [6 empty] | 96.32% | 100% | 3.679%
Romania |  |  |  | 53.54% | 99.99% | 46.45% | 53.19% | 99.53% | 46.34%
Market Integration
Bi-directionality - Country
BGn <=> RO | 6.061% | 84.85% | 78.79% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12%
HU <=> RO |  |  |  | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28%
HU <=> SK |  |  |  | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57%
Bi-directionality - Point
Balassagyarmat (HU) / Velké Zlievce (SK) |  |  |  | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99%
Csanadpalota |  |  |  | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2%
Ruse (BG) / Giurgiu (RO) | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75%

## Quantitative benefits-GA
EXISTING
Sum of Value | Column Labels
| 2020 |  |  | 2025 | [5 empty] | 2030 |  |  | 2040
| BE |  |  | CBG |  |  | GBC |  |  | GA |  |  | GA
Row Labels | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA
Competition
Commercial Supply Access (CSA)
Austria | [12 empty] | 200% | 300% | 100%
Bulgaria | 1 | 2 | 1 | 2 | 3 | 1 | 2 | 3 | 1
Germany | [12 empty] | 200% | 300% | 100%
North Noth Macedonia | [6 empty] | 2 | 3 | 1
Romania |  |  |  | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1
LNG and Interconnection Capacity Diversification (LICD)
Hungary |  |  |  | 4531.895 | 3165.9378 | -1365.9572 | 4531.895 | 3165.9378 | -1365.9572 | 4531.895 | 3165.9378 | -1365.9572 | 4531.895 | 3165.9378 | -1365.9572
Slovakia |  |  |  | 3905.4747 | 3334.2842 | -571.1905 | 3937.7022 | 3338.2241 | -599.4782 | 3824.8499 | 3333.3333 | -491.5165 | 3806.0155 | 3333.3333 | -472.6821
MASD-RU
Austria |  |  |  | 43.07% | 40.01% | -3.1% | 46% | 43.05% | -2.9% | 47.1% | 44% | -3.1%
Bosnia Herzegovina |  |  |  | 44% | 40.83% | -3.2% | 46% | 42.83% | -3.2% | 48% | 44.83% | -3.2%
Bulgaria | 48.32% | 28.5% | -19.8% | 24.2% | 10.72% | -13.5% | 26.08% | 14.5% | -11.6%
Croatia |  |  |  | 44% | 41.24% | -2.8% | 46% | 43.17% | -2.8%
Czech Republic |  |  |  | 43.28% | 40.15% | -3.1%
Denmark |  |  |  | 43.1% | 40% | -3.1% | 45.09% | 42% | -3.1% | 47.09% | 44% | -3.1%
Germany |  |  |  | 41.07% | 38.3% | -2.8% | 43.34% | 40.75% | -2.6% | 46.31% | 43.88% | -2.4%
Hungary |  |  |  | 44% | 41.2% | -2.8% | 46% | 43.21% | -2.8%
North Noth Macedonia | 49.02% | 29.02% | -20% | 24.95% | 10.74% | -14.2% | 26.92% | 13.51% | -13.4%
Poland | [6 empty] | 45.55% | 43.06% | -2.5% | 47.85% | 45.02% | -2.8%
Romania |  |  |  | 29.06% | 6% | -23.1% | 30.86% | 8.337% | -22.5% | 27.62% | 24% | -3.6%
Serbia |  |  |  | 44% | 41.07% | -2.9% | 46% | 43.07% | -2.9% | 48% | 45.06% | -2.9%
Slovakia |  |  |  | 43.95% | 41.23% | -2.7% | 46% | 43.21% | -2.8%
Slovenia | [6 empty] | 46% | 43.06% | -2.9% | 47.04% | 44.06% | -3%
Sweden |  |  |  | 43.08% | 40% | -3.1% | 45.08% | 42% | -3.1%
Security of Supply
Remaining Flexibility 2-Week Cold Spell (%)
Romania | 89.12% | 92.28% | 3.163% | 65.24% | 100% | 34.76% | 64.95% | 100% | 35.05% | 90.3% | 100% | 9.699% | 89.79% | 100% | 10.21%
Remaining Flexibility 2-Week Cold Spell (%) --- DF
Romania |  |  |  | 64.56% | 100% | 35.44% | 64.72% | 100% | 35.28% | 88.45% | 100% | 11.55% | 76.5% | 98.68% | 22.18%
Remaining Flexibility Peak day (%)
Belgium | [9 empty] | 74.61% | 83.84% | 9.23%
France | [6 empty] | 44.73% | 51.73% | 6.999% | 28.3% | 31.8% | 3.501% | 50.42% | 52.24% | 1.82%
Germany |  |  |  | 34.93% | 38.58% | 3.657% | 25.36% | 29.33% | 3.968% | 15.64% | 17.57% | 1.935% | 25.13% | 26.04% | 0.9073%
Hungary |  |  |  | 72.26% | 90.67% | 18.41% | 63.91% | 81.49% | 17.59%
Netherlands |  |  |  | 60.08% | 66.37% | 6.29% | 43.54% | 50.36% | 6.813% | 33.96% | 38.16% | 4.201% | 60.77% | 62.96% | 2.194%
Romania | 55.24% | 57.8% | 2.561% | 42.51% | 88.96% | 46.45% | 42.18% | 88.52% | 46.34% | 71.69% | 100% | 28.31% | 65.27% | 85.99% | 20.72%
United Kingdom | [9 empty] | 25.68% | 28.85% | 3.177%
Single Largest Infrastructure Disruption (SLID)-Slovakia
Austria | [9 empty] | 24% | 19.34% | -4.655%
Czechia | [9 empty] | 24% | 18% | -6%
Slovakia | [9 empty] | 24% | 18% | -6%
Ukraine Disruption Curtailment Rate Peak Day (%)
Bosnia Herzegovina | -4% | -2% | 2%
Croatia | -4% | -2% | 2% |  |  |  | -4% | -1.132% | 2.868%
Hungary | [6 empty] | -2.773% | 0% | 2.773%
Italy | [9 empty] | -4% | -2.013% | 1.987%
Romania | -3.285% | -2% | 1.285% | -11.02% | 0% | 11.02% | -11.23% | 0% | 11.23% |  |  |  | -3.516% | 0% | 3.516%
Serbia | -4% | -2% | 2%
Market Integration
Bi-directionality - Country
BGn <=> RO | 6.061% | 84.85% | 78.79% | 6.061% | 98.51% | 92.45% | 6.061% | 98.51% | 92.45% | 6.061% | 98.51% | 92.45% | 6.061% | 98.51% | 92.45%
HU <=> RO |  |  |  | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28%
HU <=> SK |  |  |  | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57%
Bi-directionality - Point
Balassagyarmat (HU) / Velké Zlievce (SK) |  |  |  | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99%
Csanadpalota |  |  |  | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2%
Ruse (BG) / Giurgiu (RO) | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75%
LOW
Sum of Value | Column Labels
| 2020 |  |  | 2025 | [5 empty] | 2030 |  |  | 2040
| BE |  |  | CBG |  |  | GBC |  |  | GA |  |  | GA
Row Labels | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA
Competition
Commercial Supply Access (CSA)
Bosnia Herzegovina | [9 empty] | 3 | 4 | 1
Bulgaria |  |  |  | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 4 | 2
Croatia | [9 empty] | 3 | 4 | 1 | 3 | 4 | 1
Greece |  |  |  | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 4 | 2 | 3 | 4 | 1
Hungary | [9 empty] | 3 | 4 | 1 | 3 | 4 | 1
North Noth Macedonia |  |  |  | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 4 | 2
Romania |  |  |  | 3 | 4 | 1 | 2 | 4 | 2 | 3 | 4 | 1
Serbia | [9 empty] | 3 | 4 | 1
LNG and Interconnection Capacity Diversification (LICD)
Bulgaria |  |  |  | 8589.8258 | 5724.2023 | -2865.6235 | 8589.8258 | 5724.2023 | -2865.6235 | 8589.8258 | 5724.2023 | -2865.6235 | 8589.8258 | 5724.2023 | -2865.6235
Hungary |  |  |  | 3745.7328 | 2774.4172 | -971.3157 | 3745.7328 | 2774.4172 | -971.3157 | 3745.7328 | 2774.4172 | -971.3157 | 3745.7328 | 2774.4172 | -971.3157
Slovakia |  |  |  | 2808.5886 | 2503.8379 | -304.7507 | 2826.4637 | 2508.9545 | -317.5092 | 2772.7512 | 2500 | -272.7512 | 2762.946 | 2500 | -262.946
MASD-RU
Austria |  |  |  | 31.07% | 28% | -3.1% | 34% | 31.65% | -2.3%
Bosnia Herzegovina |  |  |  | 24% | 17.31% | -6.7% | 28% | 20.14% | -7.9%
Bulgaria |  |  |  | 24% | 18.34% | -5.7% | 28% | 21.42% | -6.6%
Czech Republic |  |  |  | 31.28% | 28% | -3.3% | 34% | 31.26% | -2.7%
Germany |  |  |  | 30.4% | 28% | -2.4% | 33.42% | 31.05% | -2.4% | 33.48% | 31.18% | -2.3%
Hungary |  |  |  | 31.2% | 28.46% | -2.7% |  |  |  | 34% | 31.31% | -2.7%
Lithuania | [9 empty] | 34% | 31.12% | -2.9%
Netherlands | [9 empty] | 33.23% | 31.08% | -2.1%
North Noth Macedonia |  |  |  | 24% | 17.79% | -6.2% | 28% | 20.59% | -7.4%
Romania |  |  |  | 29.06% | 13.67% | -15.4% | 30.86% | 15.76% | -15.1%
Serbia |  |  |  | 24% | 18.3% | -5.7% | 28% | 21.37% | -6.6%
Security of Supply
Remaining Flexibility 2-Week Cold Spell (%)
Romania |  |  |  | 65.24% | 100% | 34.76% | 64.95% | 100% | 35.05% | 98.88% | 100% | 1.117% | 99.06% | 100% | 0.9423%
Remaining Flexibility 2-Week Cold Spell (%) --- DF
Romania |  |  |  | 64.56% | 100% | 35.44% | 64.72% | 100% | 35.28% | 97.93% | 100% | 2.072% | 85.99% | 100% | 14.01%
Remaining Flexibility Peak day (%)
Belgium | [9 empty] | 50.52% | 60.3% | 9.784%
France | [6 empty] | 45% | 51.98% | 6.978% | 19.16% | 22.87% | 3.711% | 43.2% | 47.11% | 3.912%
Germany |  |  |  | 35.12% | 39.08% | 3.958% | 25.51% | 29.47% | 3.956% | 10.59% | 12.64% | 2.051% | 21.54% | 23.49% | 1.95%
Hungary | [6 empty] | 90% | 100% | 10%
Italy | [9 empty] | 14.39% | 17.18% | 2.787% | 34.27% | 37.37% | 3.102%
Netherlands | [6 empty] | 43.8% | 50.6% | 6.793% | 22.99% | 27.44% | 4.453% | 52.07% | 56.78% | 4.714%
Romania |  |  |  | 42.51% | 88.96% | 46.45% | 42.18% | 88.52% | 46.34% | 81.23% | 100% | 18.77% | 74.62% | 97.61% | 22.99%
United Kingdom | [9 empty] | 17.39% | 20.75% | 3.367%
Single Largest Infrastructure Disruption (SLID)-United Kingdoom
Belgium | [9 empty] | 2% | 0% | -2%
Ireland | [9 empty] | 4% | 2% | -2%
Netherlands | [9 empty] | 2% | 0% | -2%
Ukraine Disruption Curtailment Rate Peak Day (%)
Romania |  |  |  | -11.02% | 0% | 11.02% | -11.23% | 0% | 11.23%
Market Integration
Bi-directionality - Country
BGn <=> RO | 6.061% | 84.85% | 78.79% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12%
HU <=> RO |  |  |  | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28%
HU <=> SK |  |  |  | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57%
Bi-directionality - Point
Balassagyarmat (HU) / Velké Zlievce (SK) |  |  |  | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99%
Csanadpalota |  |  |  | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2%
Ruse (BG) / Giurgiu (RO) | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75%
ADVANCED
Sum of Value | Column Labels
| 2020 |  |  | 2025 | [5 empty] | 2030 |  |  | 2040
| BE |  |  | CBG |  |  | GBC |  |  | GA |  |  | GA
Row Labels | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA | WITHOUT | WITH | DELTA
Competition
Commercial Supply Access (CSA)
Cyprus | [12 empty] | 400% | 500% | 100%
LNG and Interconnection Capacity Diversification (LICD)
Bulgaria |  |  |  | 8589.8258 | 5724.2023 | -2865.6235 | 8589.8258 | 5724.2023 | -2865.6235 | 6826.0572 | 4393.6313 | -2432.4259 | 6911.8796 | 4467.2097 | -2444.6699
Hungary |  |  |  | 3745.7328 | 2774.4172 | -971.3157 | 3745.7328 | 2774.4172 | -971.3157 | 2881.0775 | 2254.0027 | -627.0748 | 2822.1901 | 2218.4521 | -603.738
Romania | [9 empty] | 371561% | 339376% | -32184% | 371561% | 339376% | -32184%
Slovakia |  |  |  | 2808.5886 | 2503.8379 | -304.7507 | 2826.4637 | 2508.9545 | -317.5092 | 2772.7512 | 2500 | -272.7512 | 2762.946 | 2500 | -262.946
MASD-RU
Austria |  |  |  | 25.07% | 22% | -3.1%
Belgium | [6 empty] | 28% | 25.91% | -2.1%
Bosnia Herzegovina |  |  |  | 24.83% | 20.83% | -4% | 28% | 24.83% | -3.2%
Bulgaria |  |  |  | 24% | 21.08% | -2.9% | 28% | 25.08% | -2.9%
Croatia |  |  |  | 24.06% | 22% | -2.1% | 28% | 25.17% | -2.8%
Czech Republic |  |  |  | 25.28% | 22% | -3.3%
France |  |  |  | 24% | 21.48% | -2.5% | 28% | 25.2% | -2.8%
Greece |  |  |  | 24% | 20.83% | -3.2% | 28% | 24.83% | -3.2%
Hungary |  |  |  | 25.2% | 22% | -3.2% | 29.21% | 26% | -3.2%
North Noth Macedonia |  |  |  | 24% | 20.95% | -3.1% | 28% | 24.92% | -3.1%
Poland |  |  |  | 24.61% | 22% | -2.6%
Romania |  |  |  | 25.06% | 21.06% | -4% | 28% | 25.06% | -2.9%
Serbia |  |  |  | 24% | 21.07% | -2.9% | 28% | 25.07% | -2.9%
Slovakia |  |  |  | 25.23% | 22% | -3.2% | 28.5% | 26% | -2.5%
Slovenia |  |  |  | 25.07% | 22% | -3.1%
Security of Supply
Remaining Flexibility 2-Week Cold Spell (%)
Romania |  |  |  | 78.04% | 100% | 21.96% | 77.73% | 100% | 22.27%
Remaining Flexibility 2-Week Cold Spell (%) --- DF
Romania |  |  |  | 77.31% | 100% | 22.69% | 77.49% | 100% | 22.51%
Remaining Flexibility Peak day (%)
Croatia |  |  |  | 67.99% | 70.32% | 2.332% | 62.42% | 64.11% | 1.685%
France | [9 empty] | 45.51% | 47.03% | 1.52% | 53.25% | 56.04% | 2.781%
Germany |  |  |  | 44.23% | 48.34% | 4.112% | 35.12% | 39.21% | 4.098% | 25.15% | 26.63% | 1.476% | 26.55% | 27.93% | 1.386%
Hungary | [6 empty] | 96.32% | 100% | 3.679%
Netherlands | [9 empty] | 54.61% | 57.81% | 3.205% | 64.19% | 66.44% | 2.251%
Romania |  |  |  | 53.54% | 99.99% | 46.45% | 53.19% | 99.53% | 46.34%
Market Integration
Bi-directionality - Country
BGn <=> RO | 6.061% | 84.85% | 78.79% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12% | 6.061% | 61.18% | 55.12%
HU <=> RO |  |  |  | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28% | 4.798% | 98.08% | 93.28%
HU <=> SK |  |  |  | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57% | 40.01% | 99.58% | 59.57%
Bi-directionality - Point
Balassagyarmat (HU) / Velké Zlievce (SK) |  |  |  | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99% | 40.01% | 100% | 59.99%
Csanadpalota |  |  |  | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2% | 4.798% | 100% | 95.2%
Ruse (BG) / Giurgiu (RO) | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75% | 20.25% | 100% | 79.75%

## Monetized benefits
Reference
|  | EXISTING |  |  | LOW |  |  | ADVANCED | [7 empty] | Reference
Benefits (Meur/year) |  | NATIONAL TRENDS | DISTRIBUTED ENERGY | GLOBAL AMBITION | NATIONAL TRENDS | DISTRIBUTED ENERGY | GLOBAL AMBITION | NATIONAL TRENDS | DISTRIBUTED ENERGY | GLOBAL AMBITION |  |  |  | Sustainability |  | EXISTING |  |  | LOW |  |  | ADVANCED
EU Bill benefits With Tariffs | Reference Supply | 208.2478 | 195.5959 | 208.3443 | 236.9374 | 217.9495 | 239.3172 | 232.1721 | 217.5243 | 233.0823 |  |  |  | CO2 and Other externalities (KtCO2 eq/y) | Reference | 0 / 2 | 6 / 11 | 3 / 8 | 0 / 2 | 4 / 7 | 3 / 7 | 0 / 0 | 2 / 3 | 1 / 2
| Supply Maximization | 265.1979 | 248.2332 | 266.1149 | 296.7243 | 268.9868 | 298.1082 | 281.1665 | 258.8695 | 284.0803 |  |  |  |  | Lower Tariff Sensitivity | 0 / 2 | 8 / 13 | 3 / 8 | 2 / 6 | 5 / 10 | 3 / 7 | 1 / 3 | 2 / 3 | 1 / 2
Security of Supply | Design Case | 4.7053 | 0.70822 | 2.9865 | 4.3066 | 0.65516 | 2.2739 | 0.012904 | 0.012904 | 0.012904 |  |  |  |  | Higher Tariff Sensitivity | 0 / 2 | 6 / 10 | 3 / 8 | 0 / 2 | 4 / 7 | 3 / 7 | 0 / 0 | 0 / 0 | 0 / 0
| 2-weeks Cold Spell | 20.8158 | 0 | 0 | 24.0287 | 0 | 0 | 0 | 0 | 0
| 2-weeks Cold Spell DF | 25.125 | 2.1212 | 0.42038 | 18.2032 | 0 | 0 | 0 | 0 | 0
Sustainability | CO2 and Other externalities savings | 0 / 0.1 | 0.4 / 0.7 | 0.1 / 0.4 | 0 / 0.1 | 0.2 / 0.4 | 0.1 / 0.3 | 0 / 0 | 0.1 / 0.2 | 0 / 0.1 | [24 empty] | Commissioning Year Sensitivity |  |  | Lower Tariff Sensitivity | Higher Tariff Sensitivity | Cost of Disruption Sensitivity
| Additional benefit (Promoter) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [23 empty] | CO2 and Other externalities savings (ktCO2eq/y) | 0 / 2 | 0 / 11 | 0 / 8 |  |  | 0 / 2 | 6 / 11 | 3 / 8
[34 empty] | CO2 and Other externalities savings (ktCO2eq/y) | 0 / 1 | 0 / 7 | 0 / 7 |  |  | 0 / 2 | 4 / 7 | 3 / 7
[34 empty] | CO2 and Other externalities savings (ktCO2eq/y) | 0 / 0 | 0 / 3 | 0 / 2 |  |  | 0 / 0 | 2 / 3 | 1 / 2
[14 empty] | Year of assessment |  | 2020 | [8 empty] | 2025
|  | EXISTING Infrastructure Level | [13 empty] | EXISTING |  |  | LOW |  |  | ADVANCED |  |  | EXISTING |  |  | LOW |  |  | ADVANCED
|  | Commissioning Year Sensitivity |  |  | Lower Tariff Sensitivity |  |  | Higher Tariff Sensitivity |  |  | Cost of Disruption Sensitivity |  |  | Benefits (Meur/year) |  | NT | DE | GA | NT | DE | GA | NT | DE | GA | NT | DE | GA | NT | DE | GA | NT | DE | GA
Benefits (Meur/year) |  | NATIONAL TRENDS | DISTRIBUTED ENERGY | GLOBAL AMBITION | NATIONAL TRENDS | DISTRIBUTED ENERGY | GLOBAL AMBITION | NATIONAL TRENDS | DISTRIBUTED ENERGY | GLOBAL AMBITION | NATIONAL TRENDS | DISTRIBUTED ENERGY | GLOBAL AMBITION | EU Bill benefits With Tariffs | Reference Supply | 36.0902 | 36.0902 | 36.0902 | 0 | 0 | 0 | 0 | 0 | 0 | 488.2539 | 488.2539 | 488.2539 | 473.399 | 473.399 | 473.399 | 480.5429 | 480.5429 | 480.5429
EU Bill benefits With Tariffs | Reference Supply | 231.9922 | 216.5837 | 231.8364 | 213.4923 | 203.1259 | 214.0831 | 201.3969 | 180.8502 | 197.7151 | 208.2478 | 195.5959 | 208.3443 |  | Supply Maximization | 38.4123 | 38.4123 | 38.4123 | 0 | 0 | 0 | 0 | 0 | 0 | 621.5567 | 621.5567 | 621.5567 | 591.4989 | 591.4989 | 591.4989 | 591.1828 | 591.1828 | 591.1828
| Supply Maximization | 296.2522 | 276.0675 | 296.9586 | 270.5917 | 254.5432 | 271.4412 | 257.6038 | 235.6076 | 256.3397 | 265.1979 | 248.2332 | 266.1149 | Security of Supply | Design Case | 0.5178 | 0.5178 | 0.5178 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2304 | 32.304 | 3.2304 | 2.3399 | 2.3399 | 2.3399 | 0.046086 | 0.046086 | 0.046086
Security of Supply | Design Case | 3.6689 | 0.7753 | 1.9567 | 4.7053 | 0.70822 | 2.9865 | 4.7053 | 0.70822 | 2.9865 | 7.6248 | 1.6626 | 4.7785 |  | 2-weeks Cold Spell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2-weeks Cold Spell | 26.4455 | 0 | 0 | 20.8158 | 0 | 0 | 20.8158 | 0 | 0 | 49.8122 | 0 | 0 |  | 2-weeks Cold Spell DF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2-weeks Cold Spell DF | 30.7547 | 2.6107 | 0.51738 | 25.125 | 2.1212 | 0.42038 | 25.125 | 2.1212 | 0.42038 | 60.1241 | 5.0761 | 1.006 | Sustainability | CO2 and Other externalities savings | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0
Sustainability | CO2 and Other externalities savings | 0 / 0.1 | 0.5 / 0.8 | 0.1 / 0.3 | 0 / 0.1 | 0.5 / 0.9 | 0.1 / 0.3 | 0 / 0.1 | 0.4 / 0.7 | 0.1 / 0.3 | 0 / 0.1 | 0.4 / 0.7 | 0.1 / 0.4 |  | Additional benefit (Promoter) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Additional benefit (Promoter) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LOW Infrastructure Level
|  | Commissioning Year Sensitivity |  |  | Lower Tariff Sensitivity |  |  | Higher Tariff Sensitivity |  |  | Cost of Disruption Sensitivity |  |  | Year of assessment |  | 2030 | [8 empty] | 2040
Benefits (Meur/year) |  | NATIONAL TRENDS | DISTRIBUTED ENERGY | GLOBAL AMBITION | NATIONAL TRENDS | DISTRIBUTED ENERGY | GLOBAL AMBITION | NATIONAL TRENDS | DISTRIBUTED ENERGY | GLOBAL AMBITION | NATIONAL TRENDS | DISTRIBUTED ENERGY | GLOBAL AMBITION |  |  | EXISTING |  |  | LOW |  |  | ADVANCED |  |  | EXISTING |  |  | LOW |  |  | ADVANCED
EU Bill benefits With Tariffs | Reference Supply | 226.4596 | 204.2385 | 228.6599 | 240.3245 | 219.9916 | 240.6931 | 231.0786 | 205.7798 | 230.022 | 236.9374 | 217.9495 | 239.3172 | Benefits (Meur/year) |  | NT | DE | GA | NT | DE | GA | NT | DE | GA | NT | DE | GA | NT | DE | GA | NT | DE | GA
| Supply Maximization | 283.6459 | 251.4491 | 284.8521 | 298.9764 | 271.9567 | 299.4859 | 291.8073 | 258.1227 | 290.3703 | 296.7243 | 268.9868 | 298.1082 | EU Bill benefits With Tariffs | Reference Supply | 273.5166 | 257.3788 | 276.2217 | 268.0698 | 235.3117 | 277.6973 | 248.2783 | 220.4256 | 255.5345 | 71.2094 | 48.2372 | 69.1064 | 70.4846 | 43.5419 | 68.9891 | 68.0488 | 49.5431 | 64.3234
Security of Supply | Design Case | 3.033 | 0.56157 | 1.6188 | 4.3066 | 0.65516 | 2.2739 | 4.3066 | 0.65516 | 2.2739 | 6.5197 | 1.5678 | 1.5678 |  | Supply Maximization | 352.2423 | 326.1048 | 357.2875 | 337.0783 | 286.7352 | 343.37 | 289.6592 | 251.6747 | 308.7193 | 90.0128 | 63.1793 | 88.2582 | 88.1797 | 51.0192 | 86.6986 | 84.5223 | 52.4586 | 76.2744
| 2-weeks Cold Spell | 29.5738 | 0 | 0 | 24.0287 | 0 | 0 | 24.0287 | 0 | 0 | 57.5007 | 0 | 0 | Security of Supply | Design Case | 5.471 | 0 | 6.132 | 3.0999 | 0 | 5.1709 | 0 | 0 | 0 | 6.702 | 0 | 0.56875 | 6.3936 | 0 | 0 | 0 | 0 | 0
| 2-weeks Cold Spell DF | 23.8329 | 0 | 0 | 18.2032 | 0 | 0 | 18.2032 | 0 | 0 | 43.5603 | 0 | 0 |  | 2-weeks Cold Spell | 12.8028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.914 | 0 | 0 | 46.209 | 0 | 0 | 0 | 0 | 0
Sustainability | CO2 and Other externalities savings | 0 / 0.1 | 0.2 / 0.4 | 0.1 / 0.3 | 0.1 / 0.3 | 0.4 / 0.6 | 0.1 / 0.3 | 0 / 0.1 | 0.2 / 0.4 | 0.1 / 0.3 | 0 / 0.1 | 0.2 / 0.4 | 0.1 / 0.3 |  | 2-weeks Cold Spell DF | 24.1428 | 0 | 0 | 5.9275 | 0 | 0 | 0 | 0 | 0 | 46.914 | 4.0793 | 0.80841 | 46.914 | 0 | 0 | 0 | 0 | 0
| Additional benefit (Promoter) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sustainability | CO2 and Other externalities savings | 0 / 0 | 1 / 1 | 0 / 1 | 0 / 0 | 1 / 1 | 0 / 1 | 0 / 0 | 0 / 1 | 0 / 0 | 0 / 0 | 0 / 1 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0
|  | ADVANCED Infrastructure Level | [12 empty] | Additional benefit (Promoter) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Commissioning Year Sensitivity |  |  | Lower Tariff Sensitivity |  |  | Higher Tariff Sensitivity |  |  | Cost of Disruption Sensitivity
Benefits (Meur/year) |  | NATIONAL TRENDS | DISTRIBUTED ENERGY | GLOBAL AMBITION | NATIONAL TRENDS | DISTRIBUTED ENERGY | GLOBAL AMBITION | NATIONAL TRENDS | DISTRIBUTED ENERGY | GLOBAL AMBITION | NATIONAL TRENDS | DISTRIBUTED ENERGY | GLOBAL AMBITION
EU Bill benefits With Tariffs | Reference Supply | 232.1721 | 217.5243 | 233.0823 | 234.7149 | 217.5243 | 234.9744 | 228.6842 | 211.567 | 229.0649 | 232.1721 | 217.5243 | 233.0823
| Supply Maximization | 281.1665 | 258.8695 | 284.0803 | 391.7707 | 365.6064 | 396.1336 | 278.8653 | 253.3447 | 280.4474 | 281.1665 | 258.8695 | 284.0803
Security of Supply | Design Case | 0.012904 | 0.012904 | 0.012904 | 0.012904 | 0.012904 | 0.012904 | 0.012904 | 0.012904 | 0.012904 | 0.030879 | 0.030879 | 0.030879
| 2-weeks Cold Spell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.5007 | 0 | 0
| 2-weeks Cold Spell DF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.5603 | 0 | 0
Sustainability | CO2 and Other externalities savings | 0 / 0 | 0.1 / 0.2 | 0 / 0.1 | 0.1 / 0.1 | 0.1 / 0.2 | 0 / 0.1 | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 0 | 0.1 / 0.2 | 0 / 0.1
| Additional benefit (Promoter) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0